## Slide 1
Project Activities in MSD
Mayling Wong-Squires
AD Operations Friday 9am Meeting
22 September 2023

## Slide 2: Purpose of this report
Report on MSD activities on projects that involve personnel who are tied to accelerator operations
Highlight potential scheduling conflicts between accelerator shutdown activities and project activities
Note: many more activities are not listed here because there is not a conflict with accelerator activities

## Slide 3: MSD Report - 22 Sept 2023
LBNF
Horn B RAW system skid: component / piping layout almost complete
Absorber RAW skid: piping assembly drawings in checking
C0 gas prototype: wiring of two pumps in progress; await assignment of reviewers of pressure vessel notes
Horn C, Target Hall and Absorber Hall: intermediate system construction drawings in progress
Target Bunker, Target Utility Corridor, and RAW room: supplied new material estimates for interconnecting piping to create BCR
Primary Beam Enclosure: checking drawings for support stands; design of LCW, FCC, and conduit to this area from MI-14
Primary Beamline: design, analysis, drawings, engineering notes and other engineering oversight for beamline vacuum components, structural supports, LCW; release of kicker ceramic tube drawings; sample coating of ceramic tiles in progress
LBNF-05 power supply room: work continues
Instrumentation: BPM design, spool piece drawing review, support stand engineering note in review
Primary beam window: final cartridge design in progress
PIP-II
RF cavities and PA’s: receiving of components and seeking additional storage, assembly of new MI cavity’s dual PA, design of new 53-MHz RR cavity
BTL collimator: steel plate drawings in progress; preparing for upcoming Production Readiness Review
Instrumentation: engineering and component procurement in progress for instruments and and stands
Vacuum: BTL and LPM design, drafting, and analysis; BTL evaluating dipole and septum vacuum chambers fabrication options as part of upcoming BTL Final Design Review; preparing for upcoming Integrated Vacuum Systems Final Design Review
Mu2e
Septa: await arrival of stand parts