## Slide 1
Jonathan Lewis for Mandy Kiburg
AD 9am Meeting
22 September 2023
Decay Pipe and Absorber Complex Status

## Slide 2: Overview of Decay Pipe and Absorber Complex
Absorber Complex
(LBNF-30)
Target
Complex
(LBNF-20)
Primary Beam Service Building
(LBNF-5)
Decay Region
Primary
Beamline
Enclosure
Fermilab
Main Injector
Tunnel
Proton Beam
From MI-10
Neutrino Beam
to SURF, SD
Extraction
Enclosure
Major
Vehicle
Access
Includes the Absorber, Instrumentation,
DS end of Decay pipe
Includes the US Decay Pipe window
The Primary beam window, Instrumentation

## Slide 3: Decay Pipe and Beam Windows
Decay pipe is CF scope – most of the design work is done or outside AD
Beam window design is nearly complete
  Primary Beam window and Decay Pipe Upstream Window
Beam window support structures in Preliminary design
  Primary beam window cartridge being prototyped and final design questions being answered
  US Decay pipe window change mechanism preliminary design and prototyping in progress
    To be finished late October

## Slide 4: Absorber
Currently in Final Design
  Final design review set for Feb/March 2024
Work includes
  Transportation fixtures
  Drawings for absorber components
  Installation planning
Concrete blocks
Steel shielding and support module
256”
360”

## Slide 5: Neutrino Beam Instrumentation
Includes detectors for beam-based alignment and monitoring
Currently preparing for Final design Review for Target Hall instrumentation
  TPT, Crosshairs
  HLS