## Slide 1
Dean (Chip) Edstrom
09/29/2023
IOTA Proton Injector Update

## Slide 2: FAST Schedule
2024
2025
2026
2027
2028
2023
p+ source commissioning
RFQ+MEBT installation
2.5-MeV p+ from RFQ
IOTA p+ commissioning
IOTA Run-5 (p+)
NIO+
NIO & SC
IOTA Run-7 (p+)
Shutdowns
E-lens development
E-lens in IOTA
AI/ML controls integration
TBD
IOTA/FAST Run-5 (e)
OSC+
TBD
Run-7 (e)
GREENS+
IOTA/FAST Run-6 (e)
TBD
Run 8 (e)
Run 8 (p+)

## Slide 3: IPI Project Schedule
Notable Progress (or lack thereof)
  MEBT Girder 1 & 2 on order (Dave, Geoff, Steve)… Girder 3 WebReq Approved.
  WebReq 53729 in progress for cable pull… Still aiming for 10/16?
  Bend Chambers: Still no PO…
    WebReq 52486 submitted 07/03/2023
    Requisition 346933 entered 07/11/2023

## Slide 4: Goals by the end of…
  September 2023
    Source ready for Protons
      Bell Jar Check-Out (✔)
      Filament assembly with new/coated/activated filament mesh (❌)
        Still working through IMPACT HA approval process
      All HV Enclosure component control established/tested (❌)
      All Hydrogen Distribution component control established/tested (❌)
    Cable Pull locked in for 10/16 (❌)
      WebReq 53729 approved (✔), HA/Impact, PO generated
      LCW/tray Supports Installed around the IPI RF Penetration (✔)
      Current electron run ending on/before 09/29. (❌)
      MEBT Support Stands in purchasing or on-order (✔)
      Engineering notes complete (✔… Under Review)
      CDC contactor started (?)
    HLRF
      Interlock chassis started (?)

## Slide 5: Goals by the end of…
  October
    Girders installed
    Cable pull
    Klystron interlocks checkout begins
  November
    Girders loaded (Except Dipole Bend Chamber)
    Protons from Source (30 – 50 keV)… Be working towards > 48 keV
    HLRF Distribution Complete
    Connections to Buncher & RFQ
    Klystron interlocks complete
    Cable terminations complete
  December
    Klystron conditioned
    RF to Buncher Cavity / RFQ