## Slide 1: Planning Schedule & Milestones
E. Jensen (CERN) – just reporting, the work is done by many!
April 8 – April 10, 2013

## Slide 2: Master Schedule – unchanged!
now
NB (from my experience): things left of the blue line don’t move, but those right of the blue line tend to move further to the right; … except for the years!
NB (rumour – against my experience): Maybe detectors need interruption earlier, i.e. an advanced LS2…
Global scheme with elliptical CC is plan B.
Test in LHC IR4 is not yet decided.

## Slide 3: Long-term goals
Hi-Lumi Beam Commissioning/“Operation”: 2024+
Hi-Lumi Installation: 2022+
CC Commissioning: 2021+
CC production: 2017-2021
CC Validation run in SPS: 2016-2017
I’ll concentrate on the planning up to here
The following was prepared by Alick Macpherson, who is leading the coordination/integration effort towards the LHC CC SPS Validation.
To this end, Alick chairs the “Crab Cavity Technical Coordination working group”.

## Slide 4: Crab cavities - Why we want them in the LHC
Crab Cavities: Transverse deflecting cavities that rotate bunches to optimize the geometrical reduction factor in luminosity for colliding beams with a non-zero crossing angle.
Motivation for HL-LHC
  Can optimize luminosity production
    Gives a factor ~2 in Luminosity reach
  Can be used for luminosity leveling
  Can moderate longitudinal vertex density
LHC Prerequisites
  Show that crab cavities can work effectively in LHC environment
  Ensure machine protection aspects are compatible with LHC operation
Demonstration of feasibility with proton machines: SPS validation is essential

## Slide 5: Crab Cavities in the SPS:
SPS Validation program - Objectives
  Validate Crab cavity design for proton beams
  Validate operational functionality & Machine protection mechanisms
  Overall goal => set inputs for final design
SPS tests considered essential to finalize design + operational scenarios
  SPS crab cavity tests not foreseen before 2016
Crab cavity prototypes:
  Compact superconducting transverse deflecting cavities
    complicated geometry, compact, made from solid Niobium sheets.
Operational Constraint: Cavities must not block normal SPS operation
  Must be possible to remove from beam line on short time scale.

## Slide 6: SPS Crab Cavity Validation Program
Stand alone validation
  Full characterization of cryomodule & cavities prior to installation in SPS
Invisibility Tests
  Crab Cavities must be transparent to operation when detuned
Beam loaded measurements
  Cavity performance with beam: cavity response, heat loads, RF noise etc.
Validation of cavity operational cycle with beam
  LLRF permits cycling multiple cavities through operational states
Crabbing functionality:
  Validation of crabbing, performance analysis vs. beam parameters
Machine Protection Aspects
  Detection of failure modes and mitigations/interlocks associated with LLRF

## Slide 7: Crab Cavity layout
LHC: Local crabbing scheme: 3 cavities per beam on each side of the IP
D2
Q4
Q4
D2
IP
LHC
11 m
SPS
3 m
Beam
SPS: Possible to test of both local or global crabbing schemes
2 identical cavities per cryomodule, 1 RF amplifier per cavity
Cavities can only stay in beam line if superconducting state maintained
SPS tests: Only horizontal crabbing (LHC: crabbing in both H & V)

## Slide 8: SPS crab cavity location
SPS Location: LSS4
  Cryogenics Infrastructure
    Only SPS Pt 4 is feasible
  LLRF can be close (35 m)
    Experimental cavern (ECX4)
  Facility for switching cavities in/out
  Crab Cavity space not free till 2015
  Limited access to SPS zone after SPS long shutdown (2013-2014)
  SPS Extraction pt for LHC beam 2
8

## Slide 9: SPS LSS4 Layout
LLRF
ECX4(35 m)
CC CM

## Slide 10: SPS Integration - Space available
RF Amplifiers
& Circulators
Support Table
Cryomodule
Envelope
Crab Cavity
Support
Infrastructure
Integration Issues
Transport Lane respected
Support table: size ~5 m x 3 m
  Transverse motion = 510 mm
Constrained cryomodule volume
RF amplifiers mounted on support table
  Rigid connections between RF amplifiers and cryomodule
Rigid cryo lines onto cryomodule to minimize heat load
Based on 3D model built from
Dec 2012 scans of as-installed geometry

## Slide 11: Integration in the SPS – operational aspects
Crab Cavity module switchable from in-beam to out-of-beam position
   Mechanical Y-Chamber, CC mounted on support table
Y-chamber movement: reproducible 0.51 m transverse movement in < 1hr
  Must be remote controlled (i.e. no access required) and allow
      Safety incorporated into support structure design
      Mechanical movement of helium vessels, cryo-lines etc.
SPS operation must be independent of crab cavity operational availability
510 mm
Dummy LHC Beam Pipe
3000 mm

## Slide 12: SPS Operational Constraints
SPS Extraction bump prohibits CC in beam when filling LHC
  CCs in beam: Blocks LHC filling. Aperture bottleneck for normal SPS operation
   Y-Chamber needed so cavities can be bypassed when not under test
Crab Cavity
SPS LSS4: LHC Extraction bump (Q20 optics)

## Slide 13: SPS Cryogenic Issues
Cryo infrastructure for 2 K operation
  Existing 4.5 K cryo station, but concerns over liquefaction capacity
0.7
0.85
1.2
Predicted Liquefaction capacity line [g/s]
Static heat load -> 0.55-0.65 g/s
  Install 200 l LHe buffer tank: ensures > 8 h MD operation with beam @ 2 K
Equipment | Heat load @ 2K | Source of capacity
cryostat -static | ~ 7W @ 2K | TCF20 -> 0.35 g/s
cryostat -dynamic | ~ 5-10 W @2K | TCF20/Buffer tank
Service module | ~1-2 W @ 2K | TCF20 -> 0.1 g/s
Buffer tank | ~1-2 W @ 4.5 K | TCF20 -> 0.1 g/s
Transfer lines | ~2 W @ 4.5 K | TCF20 -> 0.1 g/s
    Helium Liquefaction capacity measurement mandatory
    Static and dynamic heat loads to be reviewed (cavities + infrastructure)
MS: June 2013!

## Slide 14: Crab Cavity Cryogenics in the SPS
black –> existing [4.5 K]
red –> to be built/installed [2 K]
CC x 2
Service module
Coupler intercept
End cone intercept
End cone intercept
Screen
Screen
R
LT
TT
PT
JT
EH
TT
EH
Buffer tank
From LN2
pre-cooler
CC cryostat
Cold Box

## Slide 15: Cryogenics Layout
Electrical
equipment
TCF20
Pump
Buffer
Heater
SM
CC
LLRF
ECX4( 35m)

## Slide 16: Cryogenics - infrastructure for real
2 K pumping groups recovered from AMS
Renovated compressor + elec. motor
Cold box TCF20
New power supply panel for compressor station
Revised, labeled and qualified pressure control system / oil removal system
TCF20 Cold box
SPS BA4 4.5 K cryogenics last used 8 years ago (COLDEX). Refurbishment + upgrade for 2 K – is underway

## Slide 17: Cavity Tuners – concepts
Up/down motion
± 2μm → 1 kHz
Push/pull on cavity body
Scissor jack type mechanism
CEBAF Tuner
Double lever
(Saclay type)
Modified screw/nut
(SOLEIL type)
  Detuning range: LHC = ±5.5 kHz (half frev). Lorentz Detuning ~O(1 MHz)
SM
SM
SM

## Slide 18: Cavity Tuners - Implementation
Up/down motion
± 2μm → 1 kHz
Push/pull on cavity body
Scissor jack type mechanism
each cavity prototype requires its own cryomodule design

## Slide 19: Cryomodule Design
SPS tests: 2 identical cavities per cryomodule
Cryo modules for SPS not final LHC design
Cryogenic and power coupler ports to be top mounted
SPS integration imposes design restrictions
~3000mm
1000mm
2160mm
SPS tests: 2 identical cavities in 1 cryomodule
LHC Alignment tolerances :
  Cavity tilt: roll 
  Cavity tilt: pitch/yaw 
  Transverse inter-cavity alignment: 0.7 mm
to be x-checked

## Slide 20: Fundamental Power coupler
Fundamental power coupler: Design nearing completion
  2 Cavity types with E-field coupling, 1 with B-field coupling
Power coupler fabrication and testing take time
  Not expected before Q2 of 2015
Interface to cryo module still being resolved
Assembly constraint:
connection from top
Cavity must be able to support coupler weight (with WG) [ ~35 kg]

## Slide 21: RF Power
RF amplifier: One 400 MHz - 50 kW SPS Tetrode per cavity.
TX power vs. QEXT
Blue trace  1 mm offset
Red Trace  0 mm offset
50 kW
106
    1 mm offset: power is “flat” at ~QEXT in 25 kW range for QEXT in [4x106, 1.5 x106]
Inter Cavity Alignment
1 mm tolerance is OK for power converter in a reasonable QEXT range
  Machine protection
If QEXT = 106  τVoltage ~800 μs while TBeam dump = ~ 3 LHC turns ~ 270 μs
 Most failure modes slow (due to QL) => OK for LHC beam dump system
 For fast failure, look to nested feed back loops to mitigate failure!

## Slide 22: Multiple Cavity Control and MP algorithms: LLRF
Cavity Controller: Strong feedback to regulate individual cavities
  Feedback loop delay < 1µs
Global Feedback: regulates crabbing-uncrabbing & MPS mitigations
  Feedback loop delay ~5 µs << 1 LHC turn
LHC Control loops and MPS algorithms to be developed and tested in SPS
LHC

## Slide 23: Schedule - Longer term view
SPS validation run
2016 & 2017?
Final Design and production

## Slide 24: Schedule up to Installation in the SPS
Power coupler design completed: Q1 of 2013
SM18 - Vertical tests of prototype cavities: start Q2 of 2013
Verification He liquefaction capacity: June 2013
Cryostat design ready: Q4 of 2013
Cryogenic infrastructure installed in SPS LSS4 : End of SPS LS1 (June 2014)
Cabling infrastructure in SPS: Q1 of 2014
Power Couplers available for cryostat: Q2 of 2015
Cryomodule fully dressed: Q2 of 2015
Cryomodule fully tested in SM18: Q3 of 2015
Cryomodule installed in SPS: 2015-2016 Christmas stop.
Crab Cavity validation MDs: SPS Run 2016 and maybe 2017
SM18
Cold Test
Installation
2013
2014
2015
2016
~ Now
Couplers
Ready
Cryo
Installed
Coupler
Designed
Cryostat
Design
Crab Cavity
Validation Run
Cavity
Testing

## Slide 25
Thank you for your attention!
… and special thanks to Alick Macpherson and Rama Calaga for preparing this!