## Slide 1: Muon Campus Operation Report
Jim Morgan
Friday 09:00 Operation Meeting
October 20, 2023

## Slide 2: Muon Campus status
KPS5A PFL Repair
Intentional Accelerator
Standby Period
MC-1 Controlled Access
Study – Alternative M5 optics
G-2 Trolley Run
<------------Week Days -------------------
Study – M1-M3 Optics
Wall Current relocation from Delivery Ring to 907 in M4 Line
  Vacuum pump-down began lasts Friday, looks good
  Wall Current Monitor and vacuum pipe aligned, V907 surveyed
D30 straight section surveyed
ESS1 Electrostatic Septum at NWA
  Vacuum got good enough for a low voltage power test
  Turned on to 5 kV yesterday, will be increased next week
Electrostatic Septum ESS2 remains isolated and under vacuum
  Venting to reconnect to Delivery Ring vacuum depends on ESS1 progress
Working on plan for draining AP-0 RAW systems
  Still need Vault access to confirm isolation valve locations
  Will keep Dump system filled and running for possible future Mu2e target test
Pre-Target exhaust blower EF1 replacement VFD controller on order
  ISD ordered spare unit 8/30, part expected to arrive next week
AP-0 Air Conditioner Replacement work continues to be paused
  Waiting on contractors to return and finish installation
  Only a week or two of work needed before system can be tested

## Slide 3: Mu2e Electrostatic Septa
Q203

## Slide 4: AP-30 transformer jumper replacement

## Slide 5: Upcoming work
AP-30 Transformer jumper replacement this Monday 10/23
  Power off by 09:00, ion pumps turned off by 08:00, controls crates without power
Replace two LCW sub-header braided hoses in Delivery Ring Enclosure
Replace four leaking NSA Sextupoles in the Delivery Ring
ESS1 at NWA, power testing has begun, conditioning starts next week
Survey and Alignment jobs
  D30 survey and V907 area alignment and survey completed!
  If ESS1 installed in Delivery Ring later this Fall, will need to be aligned
Finish plans for draining AP-0 RAW systems and schedule work
AP-0 A/C work on hold, awaiting return of contractor
Replace EF1 Pre-Target rad air exhaust VFD Controller when replacement arrives
Grey Zone proposed work
  ESS1 installation, new compact ESS vacuum layout with new Q203 pipe
  Rad hard Q205 magnet swap, new Q205 vacuum pipe that’s easier to service
  Three rad hard quadrupole swaps in D30?