## Slide 1
MI/RR General
10/20/2023
MI Department Meeting | D. Morris
1
Working on LAM61 cables and Recycler 620 sextupole cables right now.
RF maintenance continues.
Finished the cavity water path rework. Preparing to install this cavity into RF#12,
which will be removed for water path and dual PA modifications.
MI-60 Test Cave anode PS transformer replacement is delayed.
Work around the MI/MI-8 berms for cathotic protection and valve maintenance.
Working on a schedule to get LCW on next week to start cleaning up the resistivity
Goal is to verify coil motion for the new style IQCB.
Need to finish all PS work
Need to complete LCW hose and valve work

## Slide 2
Tunnel Work
10/20/2023
MI Department Meeting | D. Morris
2
Recycler 620 Sextupoles installed and aligned.
Cable pulls in progress.
Finishing up connections at Q333 and Q319.
All connections complete
Simpson’s good
Water valves still closed (fitting on jumper connection)
Upgrading MI RF#4 to dual PA operations.
Final tunnel cable connections being made
Most of the LCW hoses have been replaced.
Finished behind the NuMI line and overhead at 616-618.
Working in 60 straight
Q302 Klixon harness damaged, needs replacing.
LCW valve at Q229 needs repairs.
Clorica cleaning in progress
Absorber RAW skid pump repair
Abort line roughing pump oil change