## Slide 1
Dean (Chip) Edstrom
10/20/2023
IOTA Proton Injector Update

## Slide 2: Goals by the end of…
  October 2023
    Source ready for Protons
      Filament assembly with new/coated/activated filament mesh.
        IMPACT approved... Need Acetone before proceeding (ordered).
        Bare filament tested to 21A in the bell jar. (✔)
      All HV Enclosure component control established/tested.
        Plasma cup vacuum gauge found broken… Replacements ordered.
      All Hydrogen Distribution component control established/tested.
        Established… Needs Testing.
      Beam produced under new RGD registration.
        Course AD000190/CR/01 Submitted.
    Cable Pull
      Included in PO 681206… Beginning date unannounced as of yet… (HA?)
      Electron run ending ≥ 2 Weeks ahead of cable pull start. (10/22)
      MEBT Girder 3 Assembled.
      MEBT Girders 1 & 2 Installation Underway.
      CDC contactor underway (✔… ??? Matt Kuffer & Jon Holmes)

## Slide 3: Goals by the end of…
  October 2023 (continued)
    HLRF
      HLRF Switch in progress
        Request to add ±1” lateral adjustment to switch
      LLRF Switch in progress
        Ding has been focusing on the Buncher SSA
      Begin klystron interlocks checkout

## Slide 4: Goals by the end of…
  November
    Girders loaded (Except Dipole Bend Chamber)
    Protons from Source (30 – 50 keV)… Be working towards > 48 keV
    HLRF Distribution Complete
    Connections to Buncher & RFQ
    Klystron interlocks complete
    Cable terminations complete
  December
    Klystron conditioned
    RF to Buncher Cavity / RFQ
  Expectations & schedule will be updated once the cable pull has a firmer date…

## Slide 5: FAST Schedule
2024
2025
2026
2027
2028
2023
p+ source commissioning
RFQ+MEBT installation
2.5-MeV p+ from RFQ
IOTA p+ commissioning
IOTA Run-5 (p+)
NIO+
NIO & SC
IOTA Run-7 (p+)
Shutdowns
E-lens development
E-lens in IOTA
AI/ML controls integration
TBD
IOTA/FAST Run-5 (e)
OSC+
TBD
Run-7 (e)
GREENS+
IOTA/FAST Run-6 (e)
TBD
Run 8 (e)
Run 8 (p+)