## Slide 1
MI/RR General
10/26/2023
MI Department Meeting | D. Morris
1
Finishing up LAM61 cables.
Need polarity check and hipot.
RF maintenance continues.
MI RF#12 cavity removed for water path rework.
Reworked cavity installed in its place.
MI-60 Test Cave anode PS transformer replacement is delayed.
Working on getting LCW on today
Can CUB support MI make-up?
Re-core to Operational keys Nov. 3rd (may move up to Nov. 1st)
Safety System tests Monday, Nov. 6th.
Remove LOTO locks from the MI-10 and MI-20 to 62 LOTO boxes when appropriate.
Working to get to a MI bus hipot:
ESS, LOTO box clear, EE Support walk throughs/signoffs, LCW cleaned up etc.

## Slide 2
Tunnel Work
10/26/2023
MI Department Meeting | D. Morris
2
Verifying all tunnel LCW valves.
Q302 Klixon harness replacement.
LCW valve at Q229 repaired.
Clorica cleaning has been completed.
Absorber RAW skid pump repair in progress.
Abort line roughing pump oil change completed.
Next week returning to MI-8 line collimators