## Slide 1: Muon Campus Operation Report
Jim Morgan
Friday 09:00 Operation Meeting
October 27, 2023

## Slide 2: Muon Campus status
KPS5A PFL Repair
Intentional Accelerator
Standby Period
MC-1 Controlled Access
Study – Alternative M5 optics
G-2 Trolley Run
<------------Week Days -------------------
Study – M1-M3 Optics
ESS1 Electrostatic Septum at NWA
  Began powering septum at 5 kV on Thursday, 10/19
  Septum conditioning began late on Monday, 10/23
AP-30 transformer braided connections were replaced on Monday, 10/23
  Circuit breakers for D:V906 and D:V907 checked while power off
LCW sub-header braided hoses were replaced
Electrostatic Septum ESS2 remains isolated and under vacuum
  Venting to reconnect to Delivery Ring vacuum depends on ESS1 progress
Working on plan for draining AP-0 RAW systems
  HA has been approved, Vault access early next week to review procedure
  Will keep Dump system filled and running for possible future Mu2e target test
Pre-Target exhaust blower EF1 VFD controller has arrived
  Waiting for repair to be scheduled
AP-0 Air Conditioner Replacement work continues to be paused
  Waiting on contractors to return and finish installation
  Only a week or two of work needed before system can be tested

## Slide 3: Mu2e Electrostatic Septa ESS1 conditioning
Voltage
Current

## Slide 4: AP-30 transformer jumper replacement, before and after
Picture courtesy of Ryan Crawford

## Slide 5: Upcoming work
ESS1 high voltage conditioning continues at NWA
Replace four leaking NSA Sextupoles in the Delivery Ring
Survey and Alignment jobs, done for now
  If ESS1 installed in Delivery Ring later this Fall, will need to be aligned
Vault access to finalize plans for draining AP-0 RAW systems
AP-0 A/C work on hold, awaiting return of contractor
Replace EF1 Pre-Target rad air exhaust VFD Controller when scheduled by ISD
  Try to fix old unit?
Grey Zone proposed work
  ESS1 installation, new compact ESS vacuum layout with new Q203 pipe
  Rad hard Q205 magnet swap, new Q205 vacuum pipe that’s easier to service
  Receive three rad hard quadrupoles from TD, then swap with three in D30