## Slide 1
Cons Gattuso
2023 Summer Shutdown
11/3/23

## Slide 2: Current Status and Projected Work Schedule
Grey Period

## Slide 3: Enclosure Status
We will be completing valid secures of the following areas.
  MI-8, MI-10, MI20-62
  MTA
MI Re-coring will this afternoon
  Please be out of the tunnel by 13:30 hrs
  Return long term keys to MCR
Safety System Testing
  Monday Nov 6th
    MI-8/MI10/ Mi20-62
    No access into MI while testing is occurring.
      Testing to start ~07:30- ~03:30
  Next week we will start other locations
    Order and sequencing TBD.

## Slide 4: Major Activities
MI Q319 and Main power Supplies Ramps Studies
Grey Period
  Time from when the Shutdown is over until we have permission to run beam
  Shifting from Shutdown activities to Project drive activities
  Grey work to be completed by Dec 15th
  Accelerator will be placed in a standby state
    “ALL” Tunnel activities complete
    Safety System test completed
    System Start-Up Sign-off sheets complete
    Power Supply tests completed
  Once we get closer to running beam focus will be put back on the accelerators
    Typically, we will start this process 1-2 weeks prior to projected beam delivery date
Wild cards still in play
Gate installation to isolate the accelerator complex with the rest of the lab
Fencing around some buildings
  Muon Campus
  BNB
  Booster
  Ect.
These Activities are now scheduled to be complex by Nov 30th

## Slide 5: Grey Period Tasks
Linac
  Klystron swap at the Debuncher
  KRF2 Klystron tuning
Booster
  BLM calibration
  BPM impedance resistor repair
  GMPS transformer heater installation
  Corrector control chassis checkout
  New Low level system testing
  New GMPS FE testing
MI/RR
  8 Gev line Multi Wire relocations
  Dual PA Conversion for PIP II
  Building new PIP-II era modulator power supplies
  VCB replacement
  PS studies
F-sector
  Removal of Tevatron magnets in the F3 Tevatron sector where the PIP-II Beam Transfer Line will cross the Main Ring tunnel.
Muon Campus
  Final installation of the extraction section
    Opening and closing AP40 hatch
    Remove EKIK (g-2 kicker)
    Install ESS1
    Change beam pipe in Q203
    Re-introduce ESS2 to the DR vacuum system (it has been isolated since July)
    Replace Q205 with rad hard replacement.
    Complete De-oxygenation skid
SY
  LCW HX Cleaning in F-Sector
  LCW Leak Repairs
  Lower M00U-1 and Q230 in F3 manhole and replace with beam pipe.
  Inspect MSEP2D motor
  Refill and Restart MS2 LCW System
  MT5VT2 LCW Leak Repair
  H202-4 Alignment
FAST/IOTA
  Final LCW connections from beamline to header
  Test LCW system
  Build cooling lines for extension of proton driver
Finish SD work
Projector Support

## Slide 6: Da Plan
Linac
  Maintain the secure status of the enclosure.
  Continue with RF3 studies if needed.
  Continue with turning on and checkout other RF stations.
Booster
  Work planning for Water leak repair on Period 1 Girder 2 manifold
  Work planning for Q9 Quad replacement
    Quad has a water leak that cannot be fixed in place.
MI/RR
  The main goal and priority for today and week is to the get the MILCW system up and running in preparation of establishing a MI ramp next week to test the Q333 Bolted quad.
  Fill LCW system for magnets and get water circulating.
  Friday ~13:00 hrs
    Re-coring of the MI10, 20-62 and MI-8 enclosures back to operational key core sets. During this time no access are permitted in the above enclosures except the re-core crew.
    If you have a long term key, please return it to the MCR. Also remove your locks from the LOTO Boxes in the MCR.
  Weekend
    Ops will complete a valid search and secure of the MI10, MI20-62 and Mi-8 enclosures.
    Continue to monitor MI resistivity of the LCW system in MI.
    Complete walk throughs of MI service building looking for water leaks.
  Monday November 6th
    Safety system testing will take place all day in MI. Keys to be issued only to the Interlocks group that day.
Muon Campus
  Water leak repair in the Delivery Ring
  Various Sextupole magnets that are leaking water are being changed out.
External Beam lines
  As time and people become free, we will start addressing the water leaks and other mechanical issues.

## Slide 7: Stuff I forgot….
…
…
….
?

## Slide 8: Electrical Walkthroughs
The value of completing electrical walk throughs.
Not at Fermilab

## Slide 9
Any Questions ?

## Slide 10: Schedule
End of Grey period
Booster
Linac
8 GeV
Muon Campus
F-sector &
Switchyard
PIPII
FAST/IOTA
Critical Path
Today
Dec 15
Nov
Thanksgiving
Jan 15
Dec
Jan
Stand By or
Ready State

## Slide 11: Transitioning to Operations
New RunCo’s
  George Deinlein
    External Beam Delivery Department: Muon Campus
    Email: deinlein@fnal.gov
    X 6436
  Jason Crnkovic
    External Beam Delivery Department: Neutrino and Test Beam lines
    Email: jcrnkovi@fnal.gov
    x2469
  Will occur once Beam has been established to BNB/NuMI
  RunCo will handle day to day beam operations
  ShutCo will help from behind the scenes with remaining shutdown/startup work.

## Slide 12: Dosimetry
3125
Opening Survey
MI Magnet Hose change
NuMI Target hall work
MI Magnet Water leak repairs
in 30 straight section
There are some corrections that need to be made.
Two individuals look like that are adding absolute values from pocket dosimeters instead of differential.

## Slide 13: Shut down Job Summer
Tasks
  Tasks Completed 1033 ~93%
    Maintenance activities
      Accelerator 30
      Infrastructure 48
  Total number of job 1111
    No rad coverage needed 903 82 %
    RCT coverage 105 9 %
    RWP 77 7 %
    ALARA Plan 23 2 %
Power outage (Completed 95.8 %)
  Scheduled 72
  Re-Scheduled/completed 6
  Completed 69
  Deferred until next year 4 (Tenant's request)