## Slide 1: Muon Campus Operation Report
Jim Morgan
Friday 09:00 Operation Meeting
November 3, 2023

## Slide 2: Muon Campus status
KPS5A PFL Repair
Intentional Accelerator
Standby Period
MC-1 Controlled Access
Study – Alternative M5 optics
G-2 Trolley Run
<------------Week Days -------------------
Study – M1-M3 Optics
ESS1 Electrostatic Septum at NWA
  Slow but steady progress over the past week, now at 71.3 kV
  At least a month before septum could be ready to be moved for installation in D30
LCW sub-header braided hoses were replaced
  On hold last week waiting for rad coverage
Electrostatic Septum ESS2 remains isolated and under vacuum
  Venting to reconnect to Delivery Ring vacuum depends on ESS1 progress
Working on plan for draining AP-0 RAW systems
  Still waiting on RWP and personnel availability
  Will keep Dump system filled and running for possible future Mu2e target test
Pre-Target exhaust blower EF1 VFD controller has been mounted to wall
  Still needs to have wiring finished and to be programmed
AP-0 Air Conditioner Replacement work continues to be paused
  Waiting on contractors to return and finish installation
  Only a week or two of work needed before system can be tested

## Slide 3: Mu2e Electrostatic Septa ESS1 conditioning
P.S. Voltage
P.S. Current
Ion Gauge
Ion Pump
Spark Counter

## Slide 4: Example of NSA sextupoles in Delivery Ring
NSA sextupoles

## Slide 5: Upcoming work
ESS1 high voltage conditioning continues at NWA
AP-10 120 Volt 20 Amp circuit breaker replacement
Remove M4 Extinction Collimator from tunnel for modification
Replace four leaking NSA Sextupoles in the Delivery Ring
  Magnet selection and staging first, then hook up to LCW system to test for leaks
Survey and Alignment jobs, done for now
  If ESS1 installed in Delivery Ring later this Fall, will need to be aligned
Vault access to finalize plans for draining AP-0 RAW systems
AP-0 A/C work on hold, awaiting return of contractor
Finish installing EF1 Pre-Target rad air exhaust VFD Controller
  Try to fix old VFD Controller
Grey Zone proposed work
  ESS1 installation, new compact ESS vacuum layout with new Q203 pipe
  Rad hard Q205 magnet swap, new Q205 vacuum pipe that’s easier to service
  Receive three rad hard quadrupoles from TD, then swap with three in D30