## Slide 1
Installation and Commissioning of the IOTA Proton Injector
Dean (Chip) Edstrom
IOTA/FAST Collaboration Meeting
13 March 2024

## Slide 2: The IOTA Proton Injector (IPI)
Objective: Build a short proton linac for beam to IOTA
2.5 MeV Protons for use in the IOTA ring at the FAST Facility
  Installation In Progress
  50 keV extraction from the Duoplasmatron Source
  Acceleration to 2.5 MeV through the RFQ
Primarily Reused / Borrowed Components
  HINS: Duoplasmatron Ion Source, LEBT Solenoids, RFQ, Buncher, Toroids, Faraday Cup
  PIP-II IT: LEBT/MEBT Allison Scanners, Scanning Wires, Bias Current Electronics
  IOTA Electron Injector Beamline: LE Quadrupoles, LE Bend Dipoles, Wall Current Monitor
  IOTA: Combined Function (H/V/SQ) magnets
Relatively few new systems
  MEBT BPMs: Instrumentation Technologies / Bevatech
  325 MHz LLRF: Euclid Techlabs, LLC

## Slide 3: Beamline Overview
IS LEBT RFQ MEBT
IOTA
D600
Electron Beamline
D604

## Slide 4: Duoplasmatron Source

## Slide 5: Source Commissioning
In Five Easy™ Steps:
  Assemble the source
  Insert good filament
  Perform leak-check
  Condition to ≥ 48 keV
      (Ideally 50 kV, but…)
  Establish beam to Faraday Cup

## Slide 6: Filaments
Filament Prep
Coat w/ Carbonate Mixture
Install in Bell Jar
Heat to 900°C (White Heat)
Check activation w/ HV bias (~100VDC)

## Slide 7: Duoplasmatron Source Commissioning / Characterization
A Plan in 3 Steps:
Faraday Cup
Faraday Cup
Toroid
Bend Magnet
LEBT Allison
Scanner
ORC 2011




## Slide 8: IPI Source – Radiation Generating Device (RGD) Registration
New Requirement
  In compliance with DOE Order 420.2D
Registration is currently awaiting final approval from FSO
ES&H Training Course Available
  IPI Source Operation [AD000190/CR/01]
  Audience: All RGD Source Operators
ORC 2011 approved
  Allows for Step #1 of Commissioning

## Slide 9: HLRF Distribution
2” Conduits
(500MCM)
4” Conduits
1.5” Conduit
(Fiber)
RFQ WG
Buncher WG
Penetration

## Slide 10: IOTA Overview: RFQ
Damaged cooling coil prohibited long-pulse operation…
Not (as big of) a problem for short pulse:
  5.6 kHz / 8 Hr @ 100 W CW
Commissioning needed to assess

## Slide 11: Installation In Progress
Cable Pulls Complete
  Over 300 Cables / 17 Miles Pulled
  Terminations In Progress
Beamline Element Installation in Progress
  Installed: MEBT Magnets, RFQ

## Slide 12
2023
2024

## Slide 13: Instrumentation
Repeller
Scraper
EID
Bias Current
Electronics
B310
RFQ Probes (x12)
B312
T310
(Toroid)
MEBT Allison Scanner
W315
(Scanning Wire)
Beam Position Monitors
X333
(Diamond Detector)
T322
(WCM)
B322
B332
T344
(Toroid)
W343
(Scanning Wire)
B345

## Slide 14: New Instrumentation – LLRF & BPMs
325 MHz LLRF by Euclid Techlabs
For RFQ & Buncher with Relative Phase Shift
Integrated EPICS IOC
BPMs by Instrumentation Technologies
Insert Fabrication by Bevatech
PreAmp Assemblies by AD/Inst
Integrated EPICS IOC

## Slide 15: Timing
IPI Timing Assumes:
  30 μs for Arc
  600 μs to LEBT Neutralization
    (Suppress Emittance Growth)
  15 μs to RFQ Fill
  5 μs to Stabilize
  2 μs for Beam to IOTA

## Slide 16: IOTA Proton Injector – Remaining
Source / Low Energy Beam Transport
  Duoplasmatron Proton Source
    50 keV Conditioning / Commissioning
    Source Characterization
325 MHz RF (post-FPCs)
  Installation of RF distribution
  Controls/Instrumentation Electronics
    Slow (PLC) RF protection system
    Fast (VME) RF protection systems
    Timing and Readback (HRM)
  Klystron Hook-up / Commissioning ***
    Critical Path Item (~ June 2024)
  RFQ / Buncher commissioning
Fabrication / Installation
    Vacuum / Instrumentation crosses
    Bend dipole vacuum chambers
  Alignment
    RFQ / Beamline Element Alignment
  Beamline Commissioning
Administrative: in progress ***
    SAD Update / MCI Calc. / RGA Reg.
    Critical Path Items (~ June 2024)
*** Note: Critical path item estimates are optimistic.

## Slide 17: Thank you…
For your attention,
And to everyone working to make the IPI a reality!
Any Questions?