## Slide 1
MI/RR Update
Marty Murphy presented by Denton Morris
AD 0900 Scheduling Meeting
01 Dec. 2023

## Slide 2: Current Status
  MI in supervised access.
  MI-8 Safety system tests complete.
  MI Group LOTO procedure is being written and there is some level of convergence on the approval process.
  Dial indicators are installed on Q319; cameras in place.
  Various tunnel jobs working to completion.
    MI-8 MW mechanical work is complete. EE Support needs to add extension and adapter for the gate valve. This will happen next week.
    MIRF04 work continues in the tunnel. RF will also replace cavity shorts to RR 53RF.
    Tunnel tours
    LAM61 cabling is complete in the tunnel and will resume upstairs at the PS, likely starting next week.

## Slide 3: Next Week
  Electricians on LAM61 PS to land new cables from tunnel load Monday or Tuesday – they need five days and I plan to give it to them.
  Continue writing the MI LOTO procedures.
  Wrap any remaining tunnel work.
  If LAM61 PS work is done and MI LOTO procedures are complete by end of Friday, we will switch on at KRSS and close VCBs to cook transformers over the weekend (Dec. 9-10).