## Slide 1: OTE Building PMG Report January 7, 2013 Rhonda Merchut

## Slide 2: Agenda
Coordination
OTE Building Project State Activities
Schedule & Fiscal
Summary Action Items

## Slide 3
IASU Update (IGPP)
Phase 2 scope approximately 85% complete.
CDF Coordination
OTE work inside CDF complete and returned to CDF use.
West ramp is open for Lab use (w/ prior arrangements with contractor).

## Slide 4: CDF Refurbishment
Project schedule has been accelerated.
Project manager is Steve Dixon, FESS-Eng.
$3.2M GPP project initiated in FY13 for fire and life safety.
Scope Study for multi-year project underway.

## Slide 5: OTE Outfitting GPP
Project Plan draft in final review.
There are three main components to the OTE Outfitting Project: Equipment, Furnishings, and Contingency.
* No indirect costs budgeted for $ 1M OTE contingency work which is capped exempt construction.

## Slide 6: OTE Outfitting GPP

## Slide 7: OTE Project Status:
Shop drawing review well underway. Approx 70% through anticipated 800+ submittals.
More than 200 RFI’s rec’d from contractor have been responded to.
Subcontractor’s BIM model completed for coordination.
Schedule analysis, reporting, and cost curve continues.
Safety procedures continue to be expanded as more subs come onto the project.

## Slide 8: OTE Project Status:
LEED procedures & Action Plan implemented.
  Contractor reporting 99% construction waste has been recycled.
  On track to meet goal of 20% (by cost) of regionally manufactured materials.
  On track to meet goal of 20% (by cost) of recycled content in materials used.

## Slide 9: OTE Building Construction Status:
Superstructure complete
  Roof and floor decks poured
  Slabs on grade poured
Interior CDF roof reinforcement & Bridge complete
Structural steel studs for exterior enclosure underway
Elevator steel underway
Stairway installation underway

## Slide 10: Lecture Hall
Lobby

## Slide 11
Tech Area

## Slide 12
East Ground Floor

## Slide 13
CDF Bridge
Polished Concrete mockups

## Slide 14
Polished Concrete mockup
Roof Deck

## Slide 15
Ext. Structural Tubes
Structural Stud infill

## Slide 16: Two Week Look Ahead
Roof parapet & 2nd 3rd floor structural studs continue
Elevator steel, over run
Above ceiling piping, racks, electrical
Storm lines
Temporary enclosure
Polished concrete

## Slide 17: State DCEO Activities
DCEO quarterly report to State 12/26/12 for quarter ending 11/30/12
  33% facility construction activity task complete
  Total Grant Expense to Date:
    $4,942,528/$17M
    $1,501,894/$3M

## Slide 18: Schedule Adjustments
24 additional days for underground work (SA05 & SA07)
Anticipated revised MS 3, Project Complete: 12/17/13

## Slide 19: Schedule

## Slide 20
BCWS & ACWP Cost Curve
33% costed
33% time

## Slide 21: Financial – Grant & GPP Budget (Does not include IGPP)
* + $1M VoIP, networking, security, etc.
*
2010

## Slide 22: Financial – Grant & GPP Budget (Does not include IGPP)

## Slide 23: Financial – OTE BMC PO a/o 12/20/12

## Slide 24: Contingency Management
Sources available to fund change orders:
  IGPP;
  De-scope from anticipated T&M work;
  De-scope from A/E support work;
  DOE backstop (GPP Outfitting project);
  De-scope from main construction work (will not recover all funds);
  Value engineering main construction work

## Slide 25: Summary Action Items
Continue contingency opportunities identification.
Continue cost loaded schedule evaluation & cost curve analysis with Subcontractor.
Continue shop drawing & change order review, RFI responses
Continue construction coordination & oversight.
Engineering design for Outfitting GPP including VoIP, networking, furnishings