## Slide 1
Dean (Chip) Edstrom
12/08/2023
IOTA Proton Injector Update

## Slide 2: Points of Contact
There are lots of activities with more than one (valid & incompatible) opinions on how things should be done…
Overall Cable Pull – Chip Edstrom
  Questions on cable list/labels/types/destinations/problems
  Relying upon Jamie primarily as Electrician/contract liaison
Overall Beamline Component Installation – Sasha Romanov
  Questions on beamline stand/components
Overall Support Department Liaison – Jinhao Ruan
  Questions on support for Mechanical/Electrical/RF
Overall Commissioning – Chip Edstrom
  RGD Registration, ORC, etc…
  Source Commissioning / Characterization

## Slide 3: Cable Pull Status
Cable Pull in Progress
  Penetration Ready (with one pair of 500 MCM already pulled)
    Need to consider how best to terminate these... (Junction boxes)
  Several cables already pulled to ESB
    Still awaiting Cat6 / Heliax / RG58 at least
    Need to consider how best to terminate 8-pair magnet/turbo cables
  On-hold mid-week because of safety stand-down.
    Work resumed this morning

## Slide 4: Commissioning Status
Arranging ORC Review for Full Source Operation
  Source Ready for Operation
    We have a Filament & Pressure Gauge, Oscilloscope is Repaired
    Identified a power issue for Oscilloscope (weak power supply)
    0.5 V AC signal from VAT valve was making for noisy readbacks
    Broken readback from Pres repaired (cable replaced)
  Visit by the Committee (may require follow-up)
    Requested initially without location… Moving forward again?
  RGD Registration
    Our paperwork is in… We’re currently waiting on FSO approval
  ES&H Monitoring Plan
    RCT presence for initial turn-on / for any increase in max voltage
    Passive monitoring (badges/chipmunks)

## Slide 5: Beamline Installation
MEBT Stands Anchored & RFQ moved to near final position
Thanks Dave/Geoff, Daniel/Sasha/PPD Crew!

## Slide 6: Support Departments
EE Support
  CDC Contactor Progress
RF Support
  Ding is being pulled away for PIP2
Mechanical Support
  Steve Wesseln is being pulled away for PIP2
Instrumentation
  Bogie will assist with Heliax terminations, etc
  Brian Felenz will assist with racktops / signal manifolds / pigtails
Controls
  Pierrick Hanlet assisting with EPICS integration

## Slide 7: FAST Schedule
2024
2025
2026
2027
2028
2023
p+ source commissioning
RFQ+MEBT installation
2.5-MeV p+ from RFQ
IOTA p+ commissioning
IOTA Run-5 (p+)
NIO+
NIO & SC
IOTA Run-7 (p+)
Shutdowns
E-lens development
E-lens in IOTA
AI/ML controls integration
TBD
IOTA/FAST Run-5 (e)
OSC+
TBD
Run-7 (e)
GREENS+
IOTA/FAST Run-6 (e)
TBD
Run 8 (e)
Run 8 (p+)