## Slide 1: LBNF - Beamline – Target Complex
Horns
  Continued work on drawings of inner and outer conductors of Horns B & C.
  Fabrication of redesigned electrical break between Horn A Prototype outer conductor and the collection water tank is in progress
  Friction Stir Welding vendor verification continues
    SDSMT is to rework weld
    German vendor samples returned and will now be x-ray (QA./QC)
    Negotiating with PNNL to do samples
Horns Power Supply
  Many purchase requisitions being generated for full power supply for the Horns Test Stand at MI-8.
    Components are arriving
  Electrical work has started at MI-8 to support Test stand power supply and water-cooling system.

## Slide 2: LBNF - Beamline – Target Complex
Test Stand
  Frame at MI-8 was aligned and leveled.
Stripline
  Modeling of segment to go through 5-foot thick wall between Power Supply Room and Target Hall
Water Cooling Systems
  Design work continues for
    Intermediate Systems for the TC & AC
    Horn B RAW
    Horn C RAW
    Controls
      Horn Test Stand
      Absorber Complex
  Completed
    Absorber RAW
    Horn Test Stand Specifications for fabrication
      Now with Procurement
  Prototype Gas Control System
    Electrical connections needed

## Slide 3: Interface Work
Meetings continue about busy area above target and Horn A
  Target helium cooling piping
  Horn A water cooling piping
  Horn A Stripline connection
  Stripline Block nitrogen cooling ducting
  Instrumentation cabling to target and Horn A
  Horn Level System
  Location
    Heat Exchanger He to H2O
    Battlement utility feed trhus
  Future ALARA considerations
    Ability to remove everything