## query (1)
RI-ID | Project | Title | Summary | Risk Type | RBS:Risk Area | I&I | Owner | WBS / Operations Activity | Risk Status | Approval Status | Start Date | Expiration Date | Conditions for closing risk | Probability | Technical Impact | Impact (k$) - Function | Impact (k$) - Min | Impact (k$) | Impact (k$) - Max | Impact (months) - Function | Impact (months) - Min | Impact (months) | Impact (months) - Max | Impacted Activities | Explanation of Estimate | Quality of Risk Estimates | Cause or Trigger | Risk Mitigations | Risk Responses | Link to more details | Probability Score | Impact Score - Cost | Impact Score - Schedule | Risk Rank | Impact (k$) - Mean | Impact (months) - Mean | P * Impact (k$) | P * Impact (months) | Modified | Modified By | Item Type | Path | CMAX | CBIN3 | CBIN2 | CBIN1 | SMAX | SBIN3 | SBIN2 | SBIN1 | IS | PS
RO-131-FDC-FD-149 | LBNF / DUNE | Opportunity for cost reduction if the SLAC CRYO ASIC is used | ​If in Summer 2021 DUNE decides to use the 3-in-1 solution for the ASIC to be mounted on the Front-End Motherboards, there will be a significant cost reduction, without any impact on the schedule. | Opportunity | Management Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 0 - obsolete | 2020-09-14 | 2021-03-15 | ​This risk will be closed once the DUNE Executive Board will take the final decision on the set of ASIC(s) to be used for the construction of the Front-End Motherboards. Until then we will continue in parallel the development of two sets of ASICs and perform system tests to ensure that one or both solutions meet the DUNE requirements. At the latest in Summer 2021 (after the completion of system tests on the 2nd generation of prototypes of both sets of ASICs), DUNE will have to select the type of ASIC to be used for the detector construction. | 15% | 0 (N) - negligible technical impact | 3-point - triangular | 1400 | 1750 | 2100 | 1-point - single value | 0 |  |  | 13122.2004.132.330 (initial purchase of FEMBs) | ​The cost reduction will occur because the ASIC fabrication is cheaper for the SLAC CRYO solution compared to the 3 ASIC solution (cheaper fabrication technology, fewer ASICs to be tested, simpler fabrication costs for the FEMBs).​ We originally estimated (September 2018) both options for the construction of the single phase TPC far detector. The cost saving that can be realized when building the FEMBs using the SLAC CRYO instead of 3 separate ASICs is approximately $2.1M ($1.75M for the first detector, and $350k for the second detector). There is not going to be any significant time gain, because the construction schedule is not driven by the availability of the cold electronics (the first detector may be ready a few months earlier, but the second detector will be ready at the same date). We have assigned a 21% uncertainty in the cost reduction because we have a 15% uncertainty on each cost estimate (the cost estimates are well understood, since the fabrication costs of ASICs and the resources required for testing the ASICs are well known). ​No schedule impact, the cost impact should be counted for 80% at the beginning of the constructon of the first detector, and the remaining 20% at the beginning of the construction of the second detector.​ | 3 - Solid estimate | ​This opportunity for savings might be realized once the DUNE executive board takes the decision of using the SLAC CRYO ASIC instead of the 3 ASIC solution. This decision will be taken after two rounds of prototypes of the ASICs and of the corresponding FEMBs have been fabricated and tested, including the results from system tests. This decision is expected to be taken at the earliest in Summer 2021. | ​We do not want to mitigate an opportunity of saving $2.1M. The fact that we are pursuing two options for the ASICs is in itself a risk mitigation strategy. ​OPTION: The only other possible action (if time allows) is to make a 3rd round of prototypes to ensure the success of the SLAC CRYO option. The 3rd round of prototypes however would cost (including the ASIC development, fabrication, and testing, the FEMB fabrication and testing, and system tests) another $500k, reducing the possible gain. | ​The savings realized if the SLAC CRYO ASIC is selected could be used to offset additional costs elsewhere in the project or extend the scope. |  | 2 (L) | 2 (M) | 0 (N) | 2 (Medium) | 1750 | 0 | 262.5 | 0 | 2023-12-12 07:44 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FD-147 | LBNF / DUNE | Issues with funding of technical coordination activities | ​If the agreements for international funding of the technical coordination activitiesare not in place by CD-2 then DUNE-US project must take over those activities, increasing the total US cost​ | Opportunity | Management Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 4 - approved |  |  | ​Agreements between funding agencies are in place to cover the expenses of technical coordination and the possible cost overruns. | 25% | 0 (N) - negligible technical impact | 3-point - triangular | 500 | 1000 | 5000 | 2-point - flat range |  |  |  | 13122.04.03.195 - Install TPC, Detector #1​​​ | This needs to be refined once there is a cost estimate for the activities that are to be funded via technical coordination. The delay of a few month is assumed to represent the time it takes to redirect funds from other areas into technical coordination | 1 - Rough guess | ​This risk would be caused by a delay in setting in place the funding for the activities of technical coordination, or in agreeing on what these activities are. It could also be caused by one or more international partners failing to provide their contributions to the common fund of the experiment or paying only after a delay | ​Sufficient planning. Agreement from some funding agencies to cover for the contributions of other funding agencies while addressing issues. Accelerate one agreement to resolve any problems, and translate those learnings to future agreements. | ​​If the risk is realized DOE and/or Fermilab may have to step in and redirect funds to the DUNE project to avoid construction / commissioning delays |  | 3 (M) | 2 (M) | 0 (N) | 2 (Medium) | 2166.6667 | 0 | 541.7 | 0 | 2022-08-10 08:26 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-101 | LBNF / DUNE | Delays in contractual agreement with membrane cryostat vendor | ​RETIRE THIS RISK: CERN now has contract with GTT If the contractual agreement with the membrane cryostat vendor takes longer than planned then the procurement of the membrane cryostat will take longer | Threat | External Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 20% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 3 | 6 | 12 | Cryostat #1 install |  | 1 - Rough guess |  | ​CERN is working closely with GTT initially through SBN and CERN prototyping program to ensure contracting model is understood. Monitor this to see if LBNF work can proceed per the plan. |  |  | 2 (L) | 0 (N) | 2 (M) | 2 (Medium) | 0 | 7 | 0 | 1.4 | 2023-12-12 07:47 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-CR-002 | LBNF / DUNE | [CRYO] Potential partner to fund FS Receiving Facility | ​​If a partner has a strong desire to contribute to the FS Receiving Facilities work then DOE may have to procure fewer items.​ | Opportunity | External Risk | NO | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-04-01 | 2024-12-31 | ​A partner provides funding for receiving facility items | 20% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | -705 | -3058 | 1-point - single value |  | 0 |  | Risk hook: 13122.OBMS92480 --> RO-131-FDC-CR-002 --> 131123.02.03.1551 ​ | Most likely is value of 2 tanks. Max cost impact based on value of items in plan. Discussed probability with Hema R on Mar 4, 2021. Agreed that 50% is good. As of Jan 2023, revised P estimate to 20% | 2 - Reasonable estimate | ​Commitment from Czech Republic | ​Work with Directorate and potential international partners to leverage interest​​. |  |  | 2 (L) | 2 (M) | 0 (N) | 2 (Medium) | -1254.3333 | 0 | -250.9 | 0 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-102 | LBNF / DUNE | LN2 underground storage | ​If the size of LN2 storage dewars is affected by the ability to transfer them down the shaft then additional underground space, and higher heat load will cause increased cost and excavation. | Threat | Technical Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 30% | 1 (L) - somewhat substandard | 2-point - flat range | 0 |  | 1000 | 3-point - triangular | 2 | 3 | 4 | 131123.04.04.02.167​ - Install Nitrogen Storage Dewars​ |  | 0 - Wild guess |  |  |  |  | 3 (M) | 1 (L) | 1 (L) | 1 (Low) | 500 | 3 | 150 | 0.9 | 2023-12-12 07:47 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-103 | LBNF / DUNE | LAr market risk | ​If the Nitrogen/Oxygen supply/demand market is unbalanced when filling is planned to begin then the costs may increase. This US exposure from this risk is spread over the the filling activities of the first two detectors. | Threat | External Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  | ​New estimates have allowed this risk to be closed. Uncertainty regarding cost of LAr will now be carried only in the estimate uncertainty field in the schedule. | 50% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 1650 | 1-point - single value |  |  |  | LAr #1 filling | Cost: ​It has been determined that the initial volatility to the inflation rate based on Fermilab's rates changing from the 1.9% standard rate to 3% would be $16.58M (LAr per Cryostat) times 1.1625 (2023 Projected escalation rate) yielding a price of $1.67M for all 4 Cryostats. Adding this number to the $9.4 spigot potential and the $6.6M price margin potential and the total for all cryostats equals $17.67M and a value of $8.8M for the DOE portion which is Cryostats 1 and 2. | 2 - Reasonable estimate | ​Nitrogen/Oxygen market continues to be depressed | ​Long-term contractual relationship with a vendor. Vendor buy-in, discussions are held at the highest level with the vendor. We are engaging in a services contract with a consultant specialized in noble gases market and supply to refine the current estimates and develop a path for the actual acquisition. It will take several years of effort to engange with the right people at the right level (CEO) to negotatie contracts for the required amount. Time was added through CRs, for additional LAr dewars to mitigate the schedule impact, as well as a CR for extended filling. |  | DUNE docdb#153 | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 825 | 0 | 412.5 | 0 | 2023-12-12 07:47 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-100 | LBNF / DUNE | Fermilab has insufficient labor for specialized cryogenic engineering | ​If there is competition with other Fermilab projects then LBNF will not have necessary manpower for cryogenic engineering design work | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  |  | 50% | 2 (M) - significantly substandard | 2-point - flat range | 0 |  | 1000 | 2-point - flat range | 0 |  | 9 | Cryogenics design​ | ​The internal resources currently scheduled for design work (preliminary, final, oversight during procurement, safety) total $1M in $FY16. The current design effort spans across ~4 years. Based on the recent experience we believe that 9 months are enough to contract the necessary resources to continue the work should Fermilab labor not be available. | 2 - Reasonable estimate |  | Secure Fermilab resources in advance. Hire contractors dedicated to LBNF. Outsource the design work to a company or design+fabrication. | ​Hire contractors. |  | 4 (H) | 1 (L) | 2 (M) | 3 (High) | 500 | 4.5 | 250 | 2.25 | 2023-12-12 07:47 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-109 | LBNF / DUNE | Purification System for DUNE Cryostat | ​A prototype membrane cryostat along with operating cryogenic system will need to demonstrate that high purity can be achieved. The LBNF/DUNE design will need to be improved resulting in a cost and schedule increase. | Threat | Technical Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  |  | 10% | 1 (L) - somewhat substandard | 2-point - flat range | 0 |  | 500 | 2-point - flat range | 0 |  | 6 | 131123.02.01.31MS - T5 MS - Cryogenic Equipment Preliminary Design Complete​ |  | 1 - Rough guess |  | Fermilab and CERN are engaged in an R&D program that will provide input on various stages of the design. |  |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 250 | 3 | 25 | 0.3 | 2023-12-12 07:47 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-107 | LBNF / DUNE | Lack of manpower with specialized cryogenic expertise | If sufficiently skilled individuals are not available the design will progress slower and the chance of failure increases. Continuity of design through construction will be lost. Construction phase will take longer and be less efficient. | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 4 - approved |  |  |  | 40% | 1 (L) - somewhat substandard | 2-point - flat range | 500 |  | 5000 | 2-point - flat range | 2 |  | 6 | Nitrogen refrig plants install |  | 1 - Rough guess |  | We will speak with Division heads and provide them the needs and wants of the Project. Secondly, we will reach out to associated collaborative Universities to gauge the availability of experienced Cryogenics Engineers. As a third option, we will work with outside contracted labor that will be best matched to add value to the Project. |  |  | 4 (H) | 2 (M) | 1 (L) | 3 (High) | 2750 | 4 | 1100 | 1.6 | 2023-12-12 07:47 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-106 | LBNF / DUNE | N2 System: Efficiency of delivering materials and working underground is underestimated. | If the productivity factors used by Jacobs for the Nitrogen system work is incorrect, cost and schedule of the installation will be impacted. | Threat | Technical Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  | ​Closed after the contract is awarded. | 20% | 1 (L) - somewhat substandard | 2-point - flat range | 500 |  | 3000 | 2-point - flat range | 2 |  | 4 | 131123.04.04.02.28 - Option 3: Nitrogen Refrigeration - Install Cold Box Module #1 (ELM 3000)​ | ​Based on $9M installation cost. High cost impact is 30% labor extension | 1 - Rough guess | ​Optimistic estimating, receipt of quotations for Nitrogen work | Vendor site visits to understand working situation. A plan will be developed to work with the CM at SURF to detail the underground work plan. Talk with SURF experts about their experience working underground on previous projects. Project funding for host lab activities is being developed and will be reviewed by HEP in fall 2019. |  |  | 2 (L) | 2 (M) | 1 (L) | 2 (Medium) | 1750 | 3 | 350 | 0.6 | 2023-12-12 07:47 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-CR-004 | LBNF / DUNE | [CRYO]: Poland/WUST to deliver Internal Cryogenics | ​If Poland/WUST obtains funds to deliver the Internal Cryogenics THEN the equipment will be descoped from the DOE project and funds become available for other scope. | Opportunity | Management Risk | NO | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Proposed | 1 - draft |  |  | ​Poland/WUST to deliver scope. Scope acquired by DOE delivered on site at SD receiving warehouse. | 1% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | 1228 | 3048 | 1-point - single value |  | 2 |  | ​13141.A81110 ​13141.A83110 | ​Poland has been unable to secure funds until now. Fermilab continues to engage with WUST to help secure funds, but at this time the contribution is very unlikely to materialize, hence the very low probability. Cost impact: Min is zero: nothing changes. Most likely is the internal cryogenics for FD-2 (including design). Max is thethe internal cryogenics for FD-1 and FD-2 (including design). Schedule impact: 2 mo to ramp up activities and transfer what has been done up to that moment, which is already significant. They should be able to hit the ground running in a relatively short amount of time. | 3 - Solid estimate | ​Negotiations among parties (Fermilab, WUST and funding agencies) are successful and WUST secure funds to deliver the scope, or part of it. |  | ​Scope is transferred to Poland/WUST and taken off FDC. |  | 1 (VL) | 2 (M) | 0 (N) | 1 (Low) | 1425.3333 | 2 | 14.3 | 0.02 | 2023-12-20 08:41 | David Montanari | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-116 | LBNF / DUNE | Machine shop not available underground for required field modifications | If amachine shop with the basic machinery and general construction tools are not availbale at 4850L, the schedule of the cryogenics construction/installation will be impacted. | Threat | Technical Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 100 | 1-point - single value |  | 0 |  | 131123.02.04.70MS - T4 MS - Cryo Equipment Common Area Start Construction​​​ | We expect the contractor that installs the LN2 system to provide the equipment needed for the installation and field adjustments. The duration of the installation of the internal cryogenics is 1.5 mo (for cryostats #1 and #2). The contractor will bring their own equipment for the installation of the internal cryogenics. | 2 - Reasonable estimate | ​if Fermilab labor is involved in this work, then equipment will need to be added by Fermilab. This is not presently a trigger. | ​Install a machine shop at the 4850L with the basic machinery in the CUC or the mucking drift. Contractor brings their own equipment. |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 50 | 0 | 5 | 0 | 2023-12-12 07:47 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-CR-138 | LBNF / DUNE | [CRYO] Potential partner to fund LAr Piping and LAr valves | ​​If the LAr Piping system (connecting CUC and Detector Caverns #1) is funded by a non-DOE partner, then DOE will not have the procure these items, decreasing the overall TPC for LBNF/DUNE. | Opportunity | External Risk | NO | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-04-01 | 2024-12-31 | ​Written agreement with international partner to supply LAr interconnecting piping and valves for Detectors #1. Potential point at which no agreement would close this opportunity is 2024 | 1% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | -2636 | -10543 | 1-point - single value |  | 0 |  | Risk hook: 13122.OBMS92560 --> RO-131-FDC-CR-138 --> 131123.02.03.29 | ​​Estimate taken from current plan: min is 0, most likely is 25% of value, Max is full value (100%). Schedule impact is negligible. Discussed probability with Hema R on Mar 4, 2021. Agreed that 50% is good. As of Jan 2023, revised P estimate to 10% | 2 - Reasonable estimate | ​​Partners to fund this work​are identified. Agreement secured to supply this equipment. | ​Develop Engineering Specifications and Interface Control Documents to support this effort either by a partner of by Fermilab/FRA.​Work with directorate and potential international partners to leverage interest​​. |  |  | 1 (VL) | 3 (H) | 0 (N) | 2 (Medium) | -4393 | 0 | -43.9 | 0 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-110 | LBNF / DUNE | [PM] DOE funded equipment damaged during delivery | ​If DOE funded equipment is damaged during delivery, storage, and transport, assembly could be delayed affecting critical path schedule affecting cost as well. | Threat | Management Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2026-07-01 | 2028-12-31 | Itemsdelivered to SURF and inspected prior to acceptance.Items delivered to place of installation. | 14% | 1 (L) - somewhat substandard | 3-point - triangular | 0 | 200 | 500 | 3-point - triangular | 0 | 2 | 4 | Risk hook: 13141.04.02.36MS --> RT-131-FDC-PM-110 --> 131123.02.04.70MS ​ | If a damage occurs, the equipment will need to be repaired and it may take a few months. The vendor will likely have to be contacted to establish a suitable course of action. The equipment may need to be shipped back to the nanufacturer for rework. If during transportation underground, it may need to be repaired on site. The probability is estimated using the statistics on accidents involving large trucks and resulting in property damage (https://www.fmcsa.dot.gov/safety/data-and-statistics/trends-table-10-large-truck-property-damage-only-pdo-crash-statistics-6, this is 1.38e-6/mile) multiplied by an estimate of the miles traveled by the trucks transporting DOE funded cryogenics equipment. We expect at least 100 deliveries, traveling an average of 1,000 m. That comes down to 14%.​ | 2 - Reasonable estimate | ​Logistics issue during handling and/or transport. | A full time Quality representitive will coordinate efforts by systems engineering to document a Quality plan/procedure to help guide the procurement process. Follow instructions from Logistics Manager to ensure adequate care of handling and shipping. Properly pack the items inside suitable crates. Verify credentials of shipping agent/broker. Verify acceptable QA plan for handling and shipping. |  |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 233.3333 | 2 | 32.7 | 0.28 | 2023-12-12 07:47 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FD-150 | LBNF / DUNE | [FD1] CERN contributes additional resources to HVS I&I effort at SURF | ​If CERN contributes additional resources to the HVS I&I effort at SURF, then an insufficient resource​​ threat is reduced, and installation may proceed more efficiently. | Opportunity | External Risk | NO | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open - Realized | 4 - approved | 2026-07-01 | 2027-10-31 | ​This opportunity can be closed once installation and integration are completed or a formal agreement has been signed. | 50% | 0 (N) - negligible technical impact | 2-point - flat range | -100 |  | -200 | 1-point - single value |  | 0 |  | Risk hook: 13122.A13334 --> RO-131-FDC-FD-150 --> 13122.A13315 ​ | ​The cost impact is based on the assumption that CERN will contribute a second FTE for the HV system installation | 1 - Rough guess |  | ​Secure a formal agreement with CERN. |  |  | 4 (H) | 0 (N) | 0 (N) | 0 (Negligible) | -150 | 0 | -75 | 0 | 2023-12-12 07:59 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-111 | LBNF / DUNE | [CRYO] LAr cryo pump lifetime requires frequent pump overhauls | ​If there are frequent failures to the LAr pumps then frequent pump overhauls will be needed and LAr fill will be affected. | Threat | Technical Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​Verification of performance of LAr pumps in LAr (main LAr circulation pumps and pumps under condensers). Perform regular maintenance at frequency specified by manufacturer. Monitor LAr purity and ensure it remains acceptable within LAr pumps maintenance schedule. | 30% | 0 (N) - negligible technical impact | 3-point - triangular | 237 | 602 | 910 | 3-point - triangular | 1.5 | 1.6 | 1.8 | 131123.03.191 Fill Cryostat #1 with LAr. 131123.03.40 LAr Delivery - Cryostat #2 - Part 1. | ​​Limited data is available on lifetime of pumps in LAr. These pumps typically run in LNG or LN2, which provide more lubrication to the moving parts of the pumps than LAr, increasing the life of the pumps. If maintenance is needed more frequently than regularly scheduled, downtime is needed to repair the damage to the pumps, affecting cost and schedule. Cost Impact. Cost of 4 new main LAr circulation pumps is $861,524 (manufacturing) + $322,792 (Installation) = $1,184,317. Cost of 6 new condenser pumps is $477,152 (manufacturing) + $246,516 (Installation) = $723,668. Min Cost Impact -->15% cost of replacement for maintenance kit + 30 hr/pump for maintenance (=$237,102). Most likely --> 1 spare pump of each type (installed) + 15% cost of replacement for maintenance kit + 30 hr/pump for maintenance(= $602,297). Max Cost Impact -->1 spare pump of main LAr circulation and 4 condenser pumps (installed) + 15% cost of replacement for maintenance kit + 30 hr/pump for maintenance(= $910,194). Having 6 full condenser pumps allow the fill to continue almost uninterrupted. These pumps are long lead items, they all have 8-10 mo lead time. If the condenser pumps are out of service the fill will have to stop. If the main LAr circulation pumps are out of service, it will take longer to achieve purity. Schedule Impact. 4 day/pump for installation of a new pump. 3 day/pump for repair. Min --> Maintenance on all pumps (3 day/pump * 10 pumps = 30 days). Most likely --> Replacement of 1 pump each type and maintenance on remaining (4 day/pump * 2 + 3 day/pump * 8 = 32 days). Max -->Replacement of 1 main circulation pump and 4 condenser pumps + maintenance on remaining pumps (4 day/pump * 5 + 3 day/pump * 5 = 35 days). | 2 - Reasonable estimate | ​Excessive wear of pumps in LAr service. | ​Each Cryostat will have four pumps to move the liquid. Cryostat 1 will need all four pumps until purity is reached. When the second cryostat is ready to fill the possibility exists to use two pumps from the first cryostat as a possible mitigation plan. Then the repaired pumps would be placed into the previous cryostat that had the working pump removed. Purchase spare parts to ensure continuous fill of LAr cryostat #1 if longer than recommneded maintenance interval. |  | Cost estimate | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 583 | 1.63 | 174.9 | 0.489 | 2023-12-12 07:47 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-118 | LBNF / DUNE | Not being able to hire a company to do the Final Design of the cryogenic system | ​If we are not able to hire a company to perform the Final Design of the cryogenic system (because companies are not interested to do just the design but they want to do design+fabrication), then we will need to finish with internal resources or hire a contractor to do final design+fabrication, if available. | Threat | External Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 90% | 1 (L) - somewhat substandard | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 6 | A1400 - 1st 10kt Facility Cryogenics Equipment and Piping |  | 0 - Wild guess | ​If we cannot award the contract for the Final Design only (no fabrication) to a company. | ​Investigate whether it is possible to find companies that do design only or if they do design + fabrication. If it is not, change the design strategy to a design/fabricate/install model or just design/fabricate. Do design in-house |  |  | 5 (VH) | 0 (N) | 1 (L) | 2 (Medium) | 0 | 3 | 0 | 2.7 | 2023-12-12 07:47 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-119 | LBNF / DUNE | Cryostat Design delays due to lack of requirements input | ​If the FD is not able to provide design input to the cryostat design team on schedule, then the cryostat design will be delayed and the schedule extended. | Threat | Technical Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 50% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 3-point - triangular | 1 | 6 | 12 | A1410 | ProtoDUNE is likely to tie up the FD team in 2017, hampering their engineers' abiltiy to provide design input. This could go on until late 2017 when protoDUNE design is complete, or about 6 months past when input is needed. | 1 - Rough guess | ​The cryostat has a long lead time before construction can begin. The sequence to get to that involves complex delivery, procurement, financial approvals, and iterations on design. The inputs from the FD are at the beginning of this process. ProtoDUNE is taking a lot of FD engineering time in 2017. | Plan for the inputs specifically in the schedule and develop opportunities for meetings between FD and cryostat to discuss. Try to develop means for standard top plate openings that need less specialized input. |  |  | 4 (H) | 0 (N) | 2 (M) | 3 (High) | 0 | 6.33 | 0 | 3.165 | 2023-12-12 07:47 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-121 | LBNF / DUNE | Indirect Cost Impact from Issuing new POs | ​If a new PO is required when executing an Option for the current design/build strategy then an overhead/indirect cost impact will be incurred | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 1 - draft |  |  |  | 50% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 500 | 1-point - single value |  |  |  |  | ​Indirect charges to issue a PO over $500k are ~$120k. We may need to issue 3-4 POs based on Options, which would equal roughly $500k. | 1 - Rough guess |  |  |  |  | 4 (H) | 1 (L) | 0 (N) | 2 (Medium) | 250 | 0 | 125 | 0 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-120 | LBNF / DUNE | Cryo: Need to remove LAr during cryostat filling process when it is >25% full | ​If there is a need to empty Cryostat #1 during the filling process at >25% full, and there is no buffer tank or extra cryostat available to transfer the liquid argon immediately, then the project will have to wait for a cryostat to be constructed. | Threat | Technical Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 1% | 0 (N) - negligible technical impact | 1-point - single value |  | 625 |  | 1-point - single value |  | 12.5 |  | 131123.03.191 - Fill Cryostat #1 with LAr​​​ | ​estimate is detailed in risk supplement form in docdb 1308, scenario B: wait for cryostat #2 to be ready without a detector completely installed. schedule delay = 12.5 months, operational cost to keep cryostat #1 cold = 625k probability: per discussion in JMT, 10% chance of something wrong with cryostat at this stage (fuller) and 5% with detector (would have known something earlier). Use 10% for thsi risk. | 2 - Reasonable estimate | ​problem with the cryostat or FD | ​prototype the cryostat & FD as much as possible. | ​keep cryostat #1 cold while waiting for cryostat #2 to be completed | docdb#1308 | 1 (VL) | 1 (L) | 3 (H) | 2 (Medium) | 625 | 12.5 | 6.3 | 0.125 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-122 | LBNF / DUNE | Delays during LAr Supply in Winter Months due to weather related issues | ​If adverse weather conditions delay LAr deliveries during the winter months due to concerns of supply, then the commissioning complete date of the project will be delayed. This is mainly concerned with access within the city limits. | Threat | External Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  | ​Completion of filling. Finishing filling after end of winter. | 90% | 0 (?) - Not yet defined | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 0.5 | 131123.03.191 - Fill Cryostat #1 with LAr​​​ | Based on discussions during LAr industry day, concerns were alleviated and possible delays reduced with a higher probabilty of occurence. | 2 - Reasonable estimate | ​Vendors being concerned with filling during winter | Determine if there are activities which have free float which can move to better accomodate filling during the summer months |  |  | 5 (VH) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0.25 | 0 | 0.225 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-123 | LBNF / DUNE | Nitrogen System Procurement process is delayed | ​If the DOE procurement review process takes longer than expected then the Nitrogen System procurement will be delayed. It the proposals from the potential vendors are too high as Firm Fixed Price or if the vendors take a lot of exceptions to the Terms and Conditions, the Nitrogen System procurement will be delayed. | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 3 - pending approval |  |  | retire this risk when the Nitrogen System procurement is awarded | 50% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | 23226 | 44096 | 2-point - flat range | 3 |  | 6 | 131123.02.01.469MS - T4 MS - Nitrogen System Subcontract in Place - PO Award​ | If DOE does not allow alternative to the Firm Fixed Price method for a contract with an expected duration of 7-8 years from start to finish with gaps in between due to the programmatic needs of the project, the price will considerably increase (x2-x2.5).​ The industry could complete the work in 24-30 months from award of contrat to completion of commissioning. If the alternate methods are significantly different, while acceptable from an economic point of view, they may still require significant negotiations with DOE, delaying the award of the subcontract. The current anticipated cost of the fabrication and installation of the Nitrogen System and LN2/GN2 pipes is $41.7M (with contingency $60.3M). If the bids come in at x2 the expected price, the delta cost to be covered (once the contingency has been used) is $23.2M, which we assume as the most likely cost impact. If the bids come in at x2.5 the expected price, the delta cost to be covered (once the contingency has been used) is $44.1M, which we assume as the max cost impact. If the vendors request a lot of deviations from the standard T&C, discussion will need to be held with DOE, potentially delaying the award of the subcontract. Nitrogen System procurement has started advancing with new procurement resources. The schedule impact is 3-6 months based on past experience with the DOE review & approval process. | 2 - Reasonable estimate | Complicated procurement processes. Receive proposals higher than estimated amount. Receive proposals with substantial deviations from standard T&C. Receive alternate proposals with more favorable price, but different contracting methodology than FFP. | Follow up with DOE/FSO to review and approve submittals. Engage with DOE/FSO to present alternative to Firm Fixed Price, like fixed price with economic price adjustments. Notified the potential vendors that taking a lot of exceptions to the Terms and Conditions might result in delays in contract award. |  |  | 4 (H) | 3 (H) | 1 (L) | 3 (High) | 22440.6667 | 4.5 | 11220.3 | 2.25 | 2022-08-10 08:26 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-124 | LBNF / DUNE | Construction delays and cost increase due to inadequate infrastructure provided by host | If the infrastructure (cranes, machine shops, shafts, etc.) & support teams provided by the host laboratory is inadequate then installation of the Cryostat will be delayed. | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | Finalization of far sit​e integration cost and schedule (DOE Review Fall 2019) | 10% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 3-point - triangular | 2 | 4 | 6 | 131123.01.01.568 - Steel Frame Build #1​​​ | Schedule impact - time to get resources required. | 2 - Reasonable estimate | ​Insufficient planning for international contribution installation | Project funding for host lab activities is being developed and will be reviewed by HEP in fall 2019. |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 4 | 0 | 0.4 | 2022-08-10 08:26 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-125 | LBNF / DUNE | DOE Cryo resources needed to advance Non-DOE Cryo Scope | ​If Non-DOE cryo scope design needs to advance in parallel with DOE scope then more engineering resources through Fermilab will be required. | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  |  | 90% | 2 (M) - significantly substandard | 2-point - flat range | 400 |  | 1200 | 1-point - single value |  |  |  | 131123.02.01.31MS - T5 MS - Cryogenic Equipment Preliminary Design Complete​ | 1-3 FTEs during design period of 2 years. | 2 - Reasonable estimate | ​Lack of non-DOE partner for non-DOE cryo scope. | Acquire resources |  |  | 5 (VH) | 2 (M) | 0 (N) | 3 (High) | 800 | 0 | 720 | 0 | 2023-01-23 16:43 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FD2-058 | LBNF / DUNE | [FD2-CRP] identify additional anode PCB vendor(s) | ​If additional anode PCB vendors can be identified, particularly ones capable of printing larger PCB than 1/6 of a CRU, then anode PCB costs can be reduced. | Opportunity | External Risk | NO | Matthew P. Worcester | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2021-10-01 | 2024-09-30 | This risk will be closed once the market survey of the companies that can build the PCBs has been completed and the relevant prototyping activities are done. This should be completed at the latest by the time of the production readiness review. | 50% | 0 (N) - negligible technical impact | 2-point - flat range | -110 |  | -225 | 1-point - single value |  | 0 |  | Risk hook: 13124.A369846 --> RO-131-FDC-FD2-058 --> 13124.A321​ | ​(1) Several potential additional vendors are already being considered in the US, EU, and China, so some additional vendors seem likely. (2) Assume that a 10-20% reduction in cost is achievable (3) no impact in schedule. | 1 - Rough guess |  | ​Investigating different vendors | ​ |  | 4 (H) | 1 (L) | 0 (N) | 2 (Medium) | -167.5 | 0 | -83.8 | 0 | 2023-12-12 07:57 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-127 | LBNF / DUNE | Scope gaps are discovered during the installation of the LAr components | ​If scope is missing between multiple parties, new equipment or components will need to be procured which will cause delays and potential cost increases | Threat | Technical Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 90% | 1 (L) - somewhat substandard | 3-point - triangular | 0 | 100 | 250 | 3-point - triangular | 0 | 1 | 3 | 131123.02.04.70MS - T4 MS - Cryo Equipment Common Area Start Construction​​​ | ​Risk probability is based on having multiple parties. To reduce the probability all LAr equipment would need to be provided by 1 party, which is not a possibility as this point. | 1 - Rough guess | ​Insufficient interface definition and scope identification between systems | ​Develop detailed interface documents and drawings between systems. Integration manager in the plan. Attempt to have fewer partners |  |  | 5 (VH) | 1 (L) | 1 (L) | 2 (Medium) | 116.6667 | 1.33 | 105 | 1.197 | 2022-08-10 08:27 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-128 | LBNF / DUNE | Mistakes during the installation of the non-DOE cryogenics result in rework of some parts | ​If mistakes are made during installation of the non-DOE cryogenics then rework will be required which will have cost and schedule impacts. | Threat |  |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2023-03-01 | 2028-04-30 | ​Completion of installation of non-DOE cryogenics. | 80% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | 100 | 250 | 3-point - triangular | 0 | 1 | 3 | 131123.02.04.70MS - T4 MS - Cryo Equipment Common Area Start Construction​ | ​Even with careful planning, mistakes can be made during the installation that might result in rework of certain parts or the need to purchase replacement parts for some components that have been damaged. We intend to purchase and have available a reasonable number of spares for critical (and long lead) components, but it is impossible to foresee everything that can go wrong and have 100% spares available. Some items will take days/weeks to procure, others may take longer. This risk item is related to the non-DOE cryogenics, where the Institution/entity responsible for delivering the components might no be in a position to quickly intervene should a situation like this arise. For the DOE responsibility the vendor responsible for the installation will be responsible for fixing the eventual mistakes (if any) and recuperate the time wasted, if any. Some examples: flanges with wrong features welded/machined on them. Mixed size flanges and bolts (Imperial versus Metric), a piece is dropped during the installation and becomes too damaged for use, the wrong piece is welded in the wrong position, etc. Experience during the installation of ProtoDUNE suggests that this will happen and that there would need to be a mechanism to address these situatoins in a fast and efficient way. | 1 - Rough guess | ​Mistakes during the installation of the non-DOE cryogenics. | ​QC plan and detailed work packages (of the DOE and non-DOE cryogenics). Contractor oversight. |  |  | 5 (VH) | 1 (L) | 1 (L) | 2 (Medium) | 116.6667 | 1.33 | 93.3 | 1.064 | 2022-08-10 08:27 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FD-354 | LBNF / DUNE | [FD1-PD] International partners found to cover warm electronics costs | ​International partners found to cover all or part of warm electronics base costs​. Several Latin American institutions have expressed interest in participating in warm electronics fabrication. One or more of them may be able to cover the associated core costs. | Opportunity | External Risk | NO | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-04-01 | 2024-03-31 | ​End of fabrication of PD warm electronics | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | -450 | 1-point - single value |  | 0 |  | Risk hook: 13122.OBMS92170 --> RO-131-FDC-FD-354 --> 13122.A12740 | ​International partners are involved in the engineering and design of the PD warm electronics. One or more of them may be able to cover some or all of the associated core costs, including component purchase and PCB fabrication/component positioning soldering. This assumes a flat probability of 0 to 100% international coverage of this expense. | 2 - Reasonable estimate | ​Additional international resources become available. | ​Consortia leadership & DUNE Collaboration proactively reaching out to attain resources |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | -225 | 0 | -22.5 | 0 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-105 | LBNF / DUNE | [CRYO] Heat load to cryo plant exceeds estimated load | IF the heat load from the cryostat is underestimated THEN the Nitrogen Refrigerator margin will be reduced and may not be sufficient for steady operations. | Threat | Technical Risk | NO | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2027-10-01 | 2029-03-12 | Verification that the fill rate of the cryostat is according to specifications. | 10% | 1 (L) - somewhat substandard | 1-point - single value |  | 26620 |  | 1-point - single value |  | 5 |  | Risk hook: 131123.04.04.46 -> RT-131-FDC-CR-105 --> 131123.04.04.04.47 The lag is needed to align properly with the activities | If the heat load to the nitrogen refrigeration exceeds the estimate, the refrigeration system might need to be supplemented with additional capacity to support the need of the experiment. The cost of an additional refrigeration unit is$26,620k (Manufacturing + Installation + Commissioning) from current estimate. Additional refrigeration capacity is needed. A new full unit is needed. Exercising Option 2 for 4th unit (= $26,620k). The delay is about 5 months, corresponding to the increased time needed to fill the cryostat. The manufacturing happens in the background. | 2 - Reasonable estimate | Cannot keep stable operations once full. | ​Engineers developed simulations and analysis of the system with sufficient margin built in. Various Design reviews will be put in place to confirm the necessary parameters of the cryo plant heat load specifications. The DOE cryogenics team is built from a highly knowledgable pool of talent at Fermilab that has extensive expertise on cryogenics engineering. Engineer in a sufficient Refrigerator margin. Cryostat performance from ProtoDUNE already incorporated in analysis. Verification of cryostat performance at SBDN (improved cryostat design based on ProtoDUNE results). Design Nitrogen System with margin (e.g. nominal cooling power not max cooling power). |  |  | 2 (L) | 3 (H) | 1 (L) | 2 (Medium) | 26620 | 5 | 2662 | 0.5 | 2023-12-12 07:47 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-135 | LBNF / DUNE | [CRYO] Nitrogen System Procurement DEAR Clause | ​If the current plan to design/fabricate/install/commission is determined by DOE to be a design/build/architect/engineer construction contract, then you have to seek a waiver of the DOE DEAR clause and the award of the Nitrogen system will be delayed | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​Award of the Nitrogen system Subcontract. | 10% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 2-point - flat range | 12 |  | 15 | 131123.02.01.631 FSO Review | We have been advised by the Legal Department that requesting a waiver to a DEAR clause requires Secretariat level approval and can take a miminum of 1 year. Acquisition plan approved by DOE in Sep-2020. RFP package approved by FSO, under IRB review. | 2 - Reasonable estimate | ​Cannot develop agreeable set of T&Cs between FRA and industry. | ​Engage with potential vendors to explain the clause and the implications of taking exception to it. Work with the Legal Department & DOE on proposed strategy and the potential vendors to identify alternative paths. Revised aquisition plan accepted by DOE or construction waiver of DEAR clause from DOE. |  |  | 2 (L) | 0 (N) | 3 (H) | 2 (Medium) | 0 | 13.5 | 0 | 1.35 | 2023-01-30 13:22 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-134 | LBNF / DUNE | Nitrogen System Procurement proposals higher than estimate | If the proposals from the potential vendors are higher than estimated (budget), then the Nitrogen System Subcontract (Engineering, Manufacturing, Installation and Commissioning) will cost more. ​​ | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​Retire this risk when the Nitrogen System procurement is awarded (FFP with EPA). | 85% | 0 (N) - negligible technical impact | 2-point - flat range | 15400 |  | 23700 | 1-point - single value |  | 0 |  | ​131123.02.01.469MS - T4 MS - Nitrogen System Subcontract in Place - PO Award | The current P6 schedule budget for the Nitrogen System comes from and Independent Cost Estimate (ICE) performed in late 2019-early 2020. Comparing these values with historic data from 2019, the maximum expected cost for the DOE part of this acquisition is $105.9M and the minimum is $97.5M. This risk item covers the delta between the current budget and the range from 2019 for this acquisition. Current budget for this acquisition (DOE part including contingency and escalation) is $82.1M. Min impact = 97.5 - 82.1 = $15.4M. Max impact = 105.9 - 82.1 = $23.7M. The cost range is related to the uncertainty of engineering a system that could be installed underground, breaking it down, shipping it and putting it back together at 4850L at SURF. It is possible and we have confirmation from the industry, but this industry is used to work in an open field environment where they have almost unlimited access to utilities and space. The historic data from 2019 relates to a much more stretched scheduled (long time between phases and uncertainty in time of award) and FFP (without EPA). The current budget is for a much more optimized schedule (almost zero float) and Fixed Price with Economic Price Adjustments. These should mitigate the risk. | 2 - Reasonable estimate | Receive proposals higher than estimated amount. | ​Understand industry approach to index pricing for outyear work. (done in Feb 2019). Work with DOE to obtain approval to use Fixed Price with Economic Price Adjustments for this contract. (Done in 2019 and 2020). Strategy implemented in AP, which has been reviewed by Board of Experts prior to submission to FSO. AP appproved by DOE (HCA/MA) in Sep-2020. RFP Package submitted to DOE in Nov-2020 (approved by FSO and submitted to IRB in Jan-2021). |  |  | 5 (VH) | 3 (H) | 0 (N) | 3 (High) | 19550 | 0 | 16617.5 | 0 | 2023-01-23 16:18 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-133 | LBNF / DUNE | Nitrogen System Procurement TC Exceptions | If the vendors take significant exceptions to the Terms and Conditions, the Nitrogen System procurement will be delayed. Note: Delay from this risk is correlated to other Nitrogen System award risks | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​retire this risk when the Nitrogen System procurement is awarded. to be closed when procurement timeframe is updated in the schedule​ | 99% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 2-point - flat range | 3 |  | 9 | ​131123.02.01.469MS - T4 MS - Nitrogen System Subcontract in Place - PO Award​ | ​If the vendors request a lot of deviations from the standard T&Cs, discussion will need to be held with DOE, potentially delaying the award of the subcontract. This may be due to the question of limitation of liability which the turnkey contract does not recognize With exceptions to the T&Cs, any significant exception is likely to result in delay, and some significant exceptions may result in increased cost. For example, if the exception is not accepting unlimited liability, then the alternatives of separating installation from the scope or pricing an insurance policy covering unlimited liability would require more time and increased cost. A significant exception to the T&C that would result in delay but not necessarily increased cost would be taking exception to the schedule constraints, warranty, or price adjustment mechanisms | 2 - Reasonable estimate | Complicated procurement processes. Receive proposals with substantial deviations from standard T&C | Notified the potential vendors that taking a lot of exceptions to the Terms and Conditions might result in delays in contract award. (done) Evaluate options for risk responses related to limitations of liability with legal and procurement team. Action: SEB met Feb 2019 to discuss options, including breaking up scope to be design/fab separate from install. Requesting waiver from DOE to allow limitation of liability not seen as possible option. Regarding breaking up into 2 contracts alternative:This is not per regular industry practice, thought to be viewed as unfavorable from industry for their proprietary systems, and may result in no bidders (a new risk).Increased risk to FRA/DOE, since responsibility to make system work is now between 2 entities instead of all with one entityUntil proposals are received for current solicitation, it is believed we cannot predict possible objections vendors will take, and thus must continue with this approach until we see proposals. Keep FSO informed of status of solicitation and issues raised during solicitation process including issues with limitations of liability. Action: as of Mar 2019, Procurement has been meeting with FSO to keep them informed, but not on limitation of liability concern. Follow up with DOE/FSO as they review and approve submittals. | ​If the exception is for not accepting unlimited liability: Create 2 contracts for design/fab and installation, then recompete. Delay likely 9 months A significant exception to the T&C that would result in delay but not necessarily increased cost would be taking exception to the schedule constraints, warranty, or price adjustment mechanisms. Response would be to negotiate with the vendor, which would take time and delay award |  | 5 (VH) | 0 (N) | 2 (M) | 3 (High) | 0 | 6 | 0 | 5.94 | 2022-08-10 08:27 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-175 | LBNF / DUNE | [CRYO] South Dakota Taxes for In-Kind Contributions to Cryogenics | ​IF LBNF/DUNE-US project needs to pay SD sales & use tax for In-Kind Contributions to FDC cryogenics, THEN the project budget will be impacted. | Threat | External Risk | YES | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-03-01 | 2028-08-31 | Resolution of SD tax applicability; all FDC Cryo installation work completed. | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 2605 |  | 1-point - single value |  | 0 |  | Risk hook: 131123.02.03.4655 --> RT-131-FDC-CR-175 --> 131123.02.03.4225​ | ​The current total value of In-Kind Contributions to LBNF Cryogenics is $40,069,780. SD sales & use tax is 6.5%, which corresponds to $2,604,536. | 2 - Reasonable estimate | determination regiarding applicability of taxes to LBND/DUNE FDC activities. | Fermilab General Counsel has engaged SD-based tax legal experts​ to advise and resolve applicability. | Ttax to be paid. Risk to be realized. |  | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 2605 | 0 | 1302.5 | 0 | 2024-01-13 12:51 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-132 | LBNF / DUNE | [CRYO] Nitrogen System review & approval takes longer than planned | IF the DOE procurement review process takes longer than expected AND/OR the selected subcontractor internal review process takes longer than expected THEN the Nitrogen System award will be delayed. | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2022-10-01 | 2023-03-31 | ​Retire this risk when the Nitrogen System procurement is awarded (Phase 2 base award). | 45% | 0 (N) - negligible technical impact | 1-point - single value |  | 1457 |  | 3-point - triangular | 2 | 4 | 6 | ​131123.02.01.4690MS - T6 MS - Full Subcontract Award | DOE has approved the award of the subcontract and it is being sent to the vendor for review and approval. The schedule impact is 2-4-6 months based on the internal review process at the selected vendor. The internal review process of the selected vendor does not go all the way up to the CEO level until they receive a signed subcontract. The COO has reviewed the package, but not the CEO. This step may increase the award time if things need to be addressed. Vendor requires 15 work days for internal Exectuive review.Any proposed change will require DOE review and approval as well. Vendor is aware that any proposed change will require DOE review and approval. CEO ultimately decides what is best for the company and has not reviewed the package yet due to their internal review process. It is likely that he will have changes. The cost impact has been calculated as 1 year of escalation for the Base subcontract award (at 5%, which is the yearly escalation used in the ICE). Base award: $29,140,380. 5% of base = $1,457,019. Manufacturing and Installation may need to be revised as well, but we will try to negotiate a better schedule with the selected vendor (e.g., by shortenening the duration of the final engineering). OLD TEXT for reference. The schedule impact is 4-6-8 months based on past experience with the DOE review & approval process. This procurement has been selected for HCA/MA review. Review and approval of Phase 1 award took twice the expected duration (based on DOE guidelines). While T&Cs for Phase 2 have been negotiated already for the most part, additional discussions and negotiations are still expected, especially on liabilitry, insurance and warranty. Schedule to remain according to DOE guidelines to ensure procurement is completed on time. Based on the above, it is likely that the DOE review and approval of the Phase 2 consent package will took longer as well. | 2 - Reasonable estimate | ​Complicated procurement processes​. Contract requires approval of the highest levels of DOE (HCA/MA), which adds levels of approval authority and complications. | ​Keep FSO informed as to status of solicitation and issues that may have arisen during proposal period. Follow up with DOE/FSO to review and approve submittals​. |  |  | 4 (H) | 2 (M) | 1 (L) | 3 (High) | 1457 | 4 | 655.7 | 1.8 | 2023-04-04 12:13 | David Montanari | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-014 | LBNF / DUNE | [I&I] Unavailability of FS Integration Labor | ​If FDC is unable to attract and retain sufficient labor in South Dakota to accomplish installation, logistics and other technical tasks, then the work may be delayed as new employees are onboarded and smaller crews continue working at a slower pace; additional staffing contracts may need to be placed at additional cost and procurement time; additional incentives may be needed to attract staff. | Threat | Management Risk | YES | Michael D Pfaff | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2027-05-01 | 2028-06-30 | ​FD #2 installation complete | 50% | 0 (N) - negligible technical impact | 2-point - flat range | 5000 |  | 10700 | 2-point - flat range | 2 |  | 6 | Risk hook: 13141.A2580MS --> RT-131-FDC-FI-014 --> 13141.A3340 | Max impact cost includes: -add per diem for 50% of craft staff ($125/day * 4 years * 40 persons) = 1 year * $125/day = $45,625 * 4 years =$182,500 * 40 persons = $7.3M (NOTE: this is consistent with TMI rate of per diem rate of $125/day = ~ 70% of GSA rate) -include a 20% premium for a portion of the staff (10 FTE/year) = 10 * 20% premium * $200k/year * 4 years = $1,600,000 -attract additional Fermilab Batavia staff for 1-year roles; add supplemental DEA for 6 persons per year = (6 persons * 4 years) * $12-mon DEA ($53k) = $1,300,000 -add training and recruitment allowance = $500k Total cost impact = $10.7M Min impact cost includes a subset of these mitigations | 2 - Reasonable estimate |  | Multiple outreach efforts will occur in parallel. Outreach to tech schools for possible implemention of apprenticeship programs. Leverage a SD-focused 4-person HR team to recuit personnel. Outreach to FNAL labor market regarding available jobs. Investigating subcontracting options with local unions Collaborate with SDSTA to provide supplemental labor which will have similar costs to subcontracted labor | ​leverage all options; decide to proceed on additional subcontracting. Prepare ICE analysis. |  | 4 (H) | 3 (H) | 1 (L) | 3 (High) | 7850 | 4 | 3925 | 2 | 2024-01-13 12:30 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-024 | LBNF / DUNE | [IPM] South Dakota Taxes for cryostat#1 cold M&S/labor & cryostat#2 warm/cold M&S/labor | ​If it is determined that South Dakota state sales and use tax (6.5%) and contractors excise tax (2%) must be paid for the cryostat #1 cold materials and labor and cryostat #2 warm and cold materials and labor, then the Project will need to pay the taxes for this in-kind contribution from CERN. | Threat | External Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-10-01 | 2026-10-01 | Guidance from the SD Department of Revenue on how SD will treat this from a tax perspective.​ | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 3206 |  | 1-point - single value |  | 0 |  | Risk hook: 13141.A82030 --> RT-131-FDC-FI-024 --> 13141.A82050 | South Dakota material taxes are estimated at 8.5%, which includes 6.5% for sales and use tax and 2% for contractor's excise tax. Labor is estimated at only 2%. The values below are for warm/cold materials/installation of two cryostats. ​$21M in materials for warm structure​ - $1.793M $8M in labor for warm structure - $0.16M $22.5M in materials for the cold cryostat - $1.913M $16M in labor for the cold cryostat - $0.32M Total: $4.186M This risk is for the cold materials /installation for cryostat #1 and warm/cold materials/installation for cryostat #2. For this risk: $1.793M + $0.16M = $1.953M/2 warm cryostats = $0.9765M = materials & labor for a single warm structure $1.91M + $0.32M = $2.23M = materials & labor for two cold cryostats $3.2065 = total for this risk | 2 - Reasonable estimate |  | Fermilab counsel is working with SD tax counsel to engage with the SD Department of Revenue to ask for clarification and make arguments on why this should not be taxed. ​ | ​None |  | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 3206 | 0 | 1603 | 0 | 2024-01-13 12:38 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-CR-149 | LBNF / DUNE | Cryo: All LAr supplied as in-kind contribution | ​If LAr is supplied as in-kind contribution by an international partner, then the LAr procurement (part or all) can be taken off project. | Opportunity | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 4 - approved |  |  | ​Identification of in-kind contributor for the LAR commodity and possibly transportation to Lead, SD. | 1% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 31743 | 1-point - single value |  |  |  | ​13123.04.04.04.49,​13123.03.40,​13123.03.215. | ​If the LAr could be supplied as in-kind contribution by an International partner and delivered to Lead, SD, the cost of the LAr supply would be taken off project. If the LAr could be supplied at a production facility or a port of entry to the US and transporation (all or part of it) is needed, there could be a (smaller) cost saving. Italy is looking into this, as they have the potential of supplying it. The cost of transporation (freight + tanks, either rented or purchased) is prohibitive so far and does not make it a viable solution. A possibility to reduce the transportation cost is to increase the duration of the fill of the first cryostat (to that of the second one) to require fewer tanks. Max cost impact based on current value of LAr (Base + escalation). Discussed probability with Hema R on Mar 4, 2021. Agreed that 1% is good at this stage. | 2 - Reasonable estimate | Agreement with international partner for the supply of part or all the LAr to Lead, SD, or a port of entry in the US, or at the production site. | ​Engage with international partners and logistics experts (via LBNF Logistics Manager) to understand the cost/duration of the transport. Work with directorate and potential international partners to leverage interest​​. |  |  | 1 (VL) | 3 (H) | 0 (N) | 2 (Medium) | 15871.5 | 0 | 158.7 | 0 | 2023-01-23 16:35 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-150 | LBNF / DUNE | Cryo: Partners require engineering assistance to design & deliver IKC #1, #2 (Up to 2 partners) | ​If (up 2 partners) partners require engineering assistance to design and deliver in-kind contributions​, then additional DOE funded engineering resources will be required. | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | Equipment delivered to SURF. | 40% | 1 (L) - somewhat substandard | 2-point - flat range | 114 | 1239 | 2364 | 3-point - triangular | 2 | 3 | 6 | 131123.02.03.2355,131123.02.03.15,131123.02.03.2695,131123.02.03.3945.​ | ​1 FTE for 6 years, 250k/year. This will be applied to these systems: - LAr items on mezzanine ($1.5M) 0.5 FTE for 6 years, $250k/year. This will be applied to this system: - LAr circulation and LAr Pumps ($0.75M). Travel: - LAr Items on mezzanine ($83k). - Internal Cryogenics ($31k). The minimum cost impact is just the travel. The most likely cost impact is half the resources needed + travel. The maximum cost impact is labor + travel. Assumed realistic schedule impact to identify suitable resources and secure them: - Min --> 2 mo. - Most likely --> 3 mo. - Max --> 6 mo. No cost associated with this, just the time needed to secure additional resources. Assume low Technical Impact as we would not let the partners continue the work without proper oversight. Goal is to preserve quality of work. | 3 - Solid estimate | Agreement with partners for delivery of in-kind contributions and their level of committment. | ​Engage with potential partners and understand their committment and approach to deliverying these systems. |  | Travel Estimate | 4 (H) | 2 (M) | 1 (L) | 3 (High) | 1239 | 3.67 | 495.6 | 1.468 | 2023-01-23 16:35 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-001 | LBNF / DUNE | Need to support costed scientific effort | ​If research funding is insufficient then project may need to support some studies. | Threat | Technical Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  | ​Realized for ProtoDUNE, therefore obsolete | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 500 |  | 3-point - triangular |  |  |  | ​CD-2 for the detectors is successor A1480 - Detector Procurment and Assembly. |  | 1 - Rough guess | ​insufficient base research funding | ​Possibly hire applications physicist | ​pay for scientists |  | 4 (H) | 1 (L) | 0 (N) | 2 (Medium) | 500 | 0 | 250 | 0 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-020 | LBNF / DUNE | The cost of underground detector installation is higher than anticipated | ​If ___ then ___ impacted. Process of installation is not fully understood at conceptual design. Lack of necessary equipment and facilities hinders rate of construction. Inadequate modeling of travel times and confined construction areas. Inability to identify underground working personnel. If additional labor is required the cost will be higher but the impact on the schedule may be low. Current plan is based on two shifts for 4 days each week (plus one shift of CE testing). Additional work could be scheduled on the fifth day, at night, or over the weekend, to recuperate for delays. | Threat | Management Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 4 - approved |  |  |  | 15% | 1 (L) - somewhat substandard | 2-point - flat range | 0 |  | 1000 | 2-point - flat range | 0 |  | 2 | 13122.04.03.195 - Install TPC, Detector #1​ |  | 1 - Rough guess |  | ​Significant work is going in defining exactly the sequence of operations that take place in the area outside the cryostat (assembly of CPA, installation and testing of CE cables on the APAs), inside the cryostat (wire inspection on the APAs), and on top of the cryostat, in order to arrive at a better estimate of the resources and the time needed for installation. Estimates of the installation schedule are already being made using a total of 9 shifts per week, with the 9th shift (Friday morning) used only for tests of the cold electronics. For all other activities this leaves 2 full shifts of contingency to address problems that have taken place during the week. Tests are being planned at Ash River to validate the design and estimates being done. These activities should significantly reduce the risk probability. |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 500 | 1 | 75 | 0.15 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-129 | LBNF / DUNE | [CRYO] LAr fluids procurement process is delayed | If the project does not come to an agreement with DOE on a LAr procurement strategy then the procurement will be considerably delayed. | Threat | Management Risk | NO | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2025-03-31 | 2028-06-01 | ​Retire this risk when the LAr Fluids procurement is awarded and the LAr fill starts. | 40% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 4 | 8 | 12 | Risk hook: 131123.03.725 --> RT-131-FDC-CR-129 --> 131123.01.01.585MS4​ | LAr Fluids PO award may be delayed due to procurement process issues between DOE and LBNF. The schedule impact is based on uncertainty in the current understanding of the LAr fluids procurement process: assumes delay in subcontract award and consequential completion of fill. The cost impact of this risk is set to zero brecause otherwise it would be double counted when taking into account the escalation component associated to an overall schedule delay. The procurement of the LAr for filling the two cryostats needs to be handled separately in that calculation since the escalation rate for that procurement, based in market studies is 3.5% instead of the standard 3%. ​ | 2 - Reasonable estimate | Difficulties with defining procurement process with DOE for LAr fluids | Have assigned procurement resources early in the process. Have engaged with potential LAr vendors. Planned updates at annual intervals. Prepared Acquisition Plan (to be submitted to DOE by Jan 31, 2023). It includes the feedback from the 2022 RFI and independent consultant investigation. ​Follow up with DOE/FSO to review and approve submittals. Issue another RFI to industry in 2023-2024 to fine tune details prior to release of RFP in 2025. |  |  | 4 (H) | 0 (N) | 2 (M) | 3 (High) | 0 | 8 | 0 | 3.2 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-021 | LBNF / DUNE | The availability of resources for work at the Far Site is less than planned | ​The far site is remote. The far detector construction cost estimate assumes that qualified local labor can be identified for certain activities. The cost will increase if external labor is required. Labor costs might need to increase to attract qualified candidates. Labor resources from laboratories may need to be housed and used. | Threat | Management Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 25% | 1 (L) - somewhat substandard | 2-point - flat range | 0 |  | 1000 | 2-point - flat range | 2 |  | 6 | 13122.04.03.195 - Install TPC, Detector #1​ | In the process of developing a labor model for installation and integration acitivities in South Dakota. That model may change and require additional resources from the project. | 1 - Rough guess |  | ​Discussions are ongoing to have an exact plan for the activities both at the Integration and Test Facility and inside the cavern, taking into account also the lessons learnt from protoDUNE. This will help establishing the exact level of staffing for both sites, including technical and scientific personnel from the consortia, and local personnel to be recruited by Technical Coordination or by SDSMT. Once these plans are finalized discussions can be held in the Collaboration / Consortia to ensure that sufficient personpower can be identified to provide adequate staffing levels, and to estimate the costs of relocating personnel to Rapid City, pay for travel of personnel that will commute for 2-3 weeks time, and for hiring local labour. Once the plans for the work at the ITF and at SURFare firmed up and a funding model for technical coordination is in place, the probability of this risk should be revisited. |  | 4949 | 3 (M) | 1 (L) | 1 (L) | 1 (Low) | 500 | 4 | 125 | 1 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-009 | LBNF / DUNE | FD event reconstruction software has insufficient energy for neutrino scatters | ​Ambiguities and inefficiencies in hit finding, pattern recognition mistakes, and incorrect interpretation may cause misreconstruction of electron shower and track energies. Mis-ID will result in energy mismeasurement. Reconstruction of beam in wide-band beam is critical to etract oscillation parameters. If required resolution is not obtained, more data will need to be collected for final precision. Delayed achievement of target physics sensitivity. | Threat | Technical Risk |  | Thomas R Junk | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 25% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 0 |  | ​n/a |  | 1 - Rough guess |  | ​TBD |  |  | 3 (M) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-008 | LBNF / DUNE | Access to detector cryostat is difficult in the event of needed repairs | ​The whole detector would not become operational until after the lengthy fill process and possibly purification steps are completed. If a repair cycle is necessary, the schedule to get to CD-4 will be delayed by at least 4 months. | Threat | Technical Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 15% | 1 (L) - somewhat substandard | 2-point - flat range | 500 |  | 1000 | 2-point - flat range | 0 |  | 4 | 131123.03.191 - Fill Cryostat #1 with LAr​​​​​ |  | 1 - Rough guess |  | ​Detailed plans for testing at the integration and test facility first and later during the installation of the APAs and CPS in the cryostat are being put in place. These tests should reduce the probability of major failures in the detector components prior to the filling of the cryostat with liquid argon. Reviews should be put in place by technical coordination prior to the closure of the TCO and prior to start filling the cryostat, with the goal of making sure that all detector components are functioning. Lessons learnt from the filling and the commissioning of the protoDUNE detector will be incorporated in this plan, again with the goal of minimizing the risks. Proposed Actions: ​Failures detected during the installation of APAs and CPAs can be fixed, eventually at the cost of taking one of these detector components out of the cryostat upon failing some initial testing. If possible the APA or the CPA can be repaired in the mine, otherwise it would have to be shipped back to the surface. Ideally each row of APAs and CPAs is tested in the cryostat prior to the beginning of the installation of the next row of detector components. One the installation of all the APAs and CPAs is completed and prior to the closure of the TCO the replacement of an entire APA/CPA is still possible, although the cost and the logistic can become complicated. Access to the FEMBs inside the cryostat is also possible prior the filling with liquid argon, using the manholes. Failures detected up to this stage are believed to be repairable. Problems that occur after the filling with liquid argon would be more complicated to fix, and would entail larger costs / delays. |  |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 750 | 2 | 112.5 | 0.3 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-007 | LBNF / DUNE | Detector performance is impaired by electrical noise | ​This experiment will have channels of electronics with intrinsic noise levels. The detector utilizes low-noise electronics. Noise from external sources can introduce interference. The TPC has a requirement to distinguish a minimum ionizing particle from noise with a signal to noise ration of 9:1. If external noise affects the TPC readout it will be more difficult to discern the event signals. Grounding, shielding and power distribution are critical to the success of the experiment. | Threat | Technical Risk |  | Theresa M Shaw | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 15% | 0 (N) - negligible technical impact | 2-point - flat range | 75 |  | 125 | 2-point - flat range | 0 |  | 2 | 13122.04.04.115 - Detector #1 commissioning​​​ 13122.04.07.230 - Detector #2 commissioning-phase II​ |  | 1 - Rough guess |  | Having a well-defined and isolated detector ground, the use of double shielded transformers for detector power, using proper shielding techniques on all conductive cables, validation of the noise performance of all equipment (e.g., variable frequency drives) and careful review and oversight of the installation process. |  | 4397 | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 100 | 1 | 15 | 0.15 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-015 | LBNF / DUNE | ODH risk for underground installation may require additional measures for safety | ​ODH threat in underground installation is greater than same installation located in building on the surface. It is possible that there are unique initiating events (rock falling hitting cryostat that have not been considered in the analysis. Could delay approval. Could cause additional costs for systems like fans, monitoring, etc. | Threat | Technical Risk |  | Russell A Rucinski | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 15% | 1 (L) - somewhat substandard | 2-point - flat range | 100 |  | 300 | 2-point - flat range | 0 |  | 2 | ​A1490 - 1st 10 kt Detector Installation |  | 1 - Rough guess |  | ​The ODH analysis can be reviewed with underground mining SURF folks prior to CD-2 and again prior to CD-3 to be sure that nothing regarding the site is missed. The ODH analysis can be submitted to the JHA prior to CD-3 for acceptance so that all features (air flow patterns, fans, demarcations) are agreed upon before outfitting. |  | dune-doc-169 | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 200 | 1 | 30 | 0.15 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-024 | LBNF / DUNE | Required FD off-project R&D is not completed on time | ​If R&D is required and is not being performed by other groups or collaborations then DUNE may need to perform this work. This can produce cost or schedule impacts. Depending on detector validation studies and physics analysis work further test beam measurements may be needed. | Threat | Management Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 50% | 1 (L) - somewhat substandard | 3-point - triangular | 200 | 500 | 1000 | 3-point - triangular | 0 | 2 | 6 | A1480 - 1st 10 kt Detector Procurement & Assembly | ​5M is rough estimate of possibly having to re-run ProtoDUNE | 1 - Rough guess |  | Work toward increasing international contributions Provide short term US project support​ |  |  | 4 (H) | 1 (L) | 1 (L) | 2 (Medium) | 566.6667 | 2.67 | 283.3 | 1.335 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-011 | LBNF / DUNE | Mechanical difficulties with wire plane design during APA construction | ​New wire wrapping technice may have significant mechanical issues and difficulties. The time to produce the number of anode plane assemblies will take longer than expected. As this is not on the critical path, it should not impact the schedule. | Threat | Technical Risk |  | Alberto Marchionni | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  | ​superceded by new risks regarding APA, Jan 2018 | 25% | 0 (N) - negligible technical impact | 2-point - flat range | 50 |  | 500 | 2-point - flat range | 0 |  | 2 | A1490 - 1st 10 kt Detector Installation​ |  | 1 - Rough guess |  | ​TBD |  |  | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 275 | 1 | 68.8 | 0.25 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-044 | LBNF / DUNE | Efficiency for K+ neutrino proton decay may be lower than expected | ​Hits could be indentified incorrectly, or placed on the wrong ambiguity choices. Selection requirements may have to be raised in order to reduce backgrounds. Impact of nuclear excitations in Ar not evaluated for proton decay. LBNE may be less competetive in proton decay searches. | Threat | Technical Risk |  | Thomas R Junk | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 0 |  | n/a​ |  | 1 - Rough guess |  | TBD |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-010 | LBNF / DUNE | Detector startup may have unknown unknowns | ​Failures in cryogenics, HV, and seals can degrade detector performance and lead to down time. Unforseen operational problems may result in low efficiency. Any downtime will need to be added on to the run increasing operating costs for the duration of the experiment. | Threat | Technical Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 15% | 0 (N) - negligible technical impact | 2-point - flat range | 50 |  | 500 | 2-point - flat range | 0 |  | 2 | 13122.04.04.115 - Detector #1 commissioning​​​ 13122.04.07.230 - Detector #2 commissioning-phase II​ |  | 1 - Rough guess |  | ​TBD |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 275 | 1 | 41.3 | 0.15 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-005 | LBNF / DUNE | The background for proton decay is higher than expected | ​Higher production rates of kaons from atmospheric neutrino collisions with Argon or other material causes 10x difference in the background rates as estimated, most likely due to a lack of relevant data. May affect LBNE's comptetiveness in nucleon decay sensitivity. | Threat | Technical Risk |  | Thomas R Junk | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 1 - draft |  |  |  | 20% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 0 |  | ​n/a |  | 1 - Rough guess |  | ​​Need requirements first before we can know if this is a risk. Could use collaboration help in understanding this. |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-019 | LBNF / DUNE | Difficulties in detector commissioning after start of LAr filling | Problems found after the start of filling then remove LAr. | Threat | Technical Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 2 - see Comments |  |  | ​This risk is a duplicate | 15% | 0 (N) - negligible technical impact | 3-point - triangular | 500 | 2500 | 5000 | 3-point - triangular | 6 | 9 | 24 | ​13005.06.09.02.30 end of det #1 commisioning |  | 1 - Rough guess |  |  |  | 4376 | 2 (L) | 2 (M) | 3 (H) | 2 (Medium) | 2666.6667 | 13 | 400 | 1.95 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-026 | LBNF / DUNE | Movement of long unconstrained wires causes noise in the detector | If we observe higher than expected vibrational noise from the TPC during protoDUNE running then additional engineering would be required to fix the issue regarding DUNE | Threat | Technical Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  |  | 10% | 2 (M) - significantly substandard | 3-point - triangular | 200 | 400 | 1000 | 3-point - triangular | 4 | 6 | 12 | 13122.04.04.115 - Detector #1 commissioning​​​ 13122.04.07.230 - Detector #2 commissioning-phase II​ | ​2.0 FTE needed for 6 months most likely scenario. | 1 - Rough guess |  | Additional engineering based on what we learn from ProtoDUNE and this influences DUNE's design. The new winder design should allow for more control and more uniformity in the wire tension (and possibly also for a larger wire tension), reducing the probability that this risk is realized. |  |  | 2 (L) | 1 (L) | 2 (M) | 2 (Medium) | 533.3333 | 7.33 | 53.3 | 0.733 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-049 | LBNF / DUNE | Free hanging frames can swing in the fluid flow | ​The detector is a long and light structure that must be held rigidly in position and that shrinks from room temperature to cryogenic operating temperature. The design calls for freely hanging wire planes. Issues of deformation and stability could arise. | Threat | Technical Risk |  | Alberto Marchionni | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 0 - obsolete |  |  | ​APA frames are affixed to each other and the field cage. Cannot swing freely. Risk obsolete. | 15% | 1 (L) - somewhat substandard | 2-point - flat range | 50 |  | 500 | 2-point - flat range | 0 |  | 2 | A1500 - 1st 10 kt Detector Filing |  | 1 - Rough guess |  | ​A full scale installation mock up is planned. This will help us re-evaluate this risk. |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 275 | 1 | 41.3 | 0.15 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-028 | LBNF / DUNE | Detector components are damaged during shipment to the far site | ​Poor shipping techniques and electrostatice discharge could cause damage. Delicate and expensive components can be damaged if adequate provisions are not made. Repairs to detector components would need to take place at SURF or South Dakota School of Mines. | Threat | External Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 15% | 0 (N) - negligible technical impact | 2-point - flat range | 50 |  | 500 | 2-point - flat range | 2 |  | 6 | 13122.04.03.195 - Install TPC, Detector #1​ |  | 1 - Rough guess |  | Need to build spares. Need documented QA program for shipment packing and method. Review shipping procedures, shipping containers, test in crate after arrival. |  |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 275 | 4 | 41.3 | 0.6 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-050 | LBNF / DUNE | Zero-suppression algorithm parameters may be set incorrectly | ​Noise could be high enough to keep the trigger rates and data volumes down. Zero-suppression threshold has to be raised, reducing shower energy resolution. Measurements are lost when applying zero suppression. Set zero threshold high as to reduce energy resolution and keep data volume under control. Worsened energy resolution requires more data to be taken to achieve the same physics goals. | Threat | Technical Risk |  | Thomas R Junk | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 0 |  | n/a​ |  | 1 - Rough guess |  | ​Requires simulation, physics tools group. Preliminary study is given in DocDB 8270. |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-035 | LBNF / DUNE | Average component lifetime is less than expected | ​The design is greatly different than existing devices built by the present engineers. The mean time between failure for the detector components may be shorter than expected. Adds mitigation costs to the project. | Threat | Technical Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 15% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 500 | 2-point - flat range | 0 |  | 6 | 13122.04.04.115 - Detector #1 commissioning​​​ 13122.04.07.230 - Detector #2 commissioning-phase II​​ |  | 1 - Rough guess |  | In addition to designing ASICs taking into account the "hot carrier effect", that is the main source of reliability issues for ASICs operated at LAr temperature, plans are being put in place to perform lifetime reliability tests for all new ASIC and for all discrete components that will be operated in LAr. One example of these tests is the lifetime estimate that has been just obtained by the SBND Collaboration for commercial ADCs. Similar tests will be performed in 2019/2020 on all the ASICs that will be used for the DUNE Cold Electronics, as well as for all the discrete components that will be installed on the Front End Motherboards (FEMBs). Similar tests should be performed by the Photon Detector System consortium on SiPMs and on other electronics components that could be installed in LAr.​ |  | 8909 | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 250 | 3 | 37.5 | 0.45 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-043 | LBNF / DUNE | Detector trigger efficiency is lower than expected for low-energy physics | ​Software and hardware trigger thresholds may have to be set high in oder to redue the rates from electronics noise and radiological backgrounds. Trigger thresholds may be too high to detect 10 MeV electrons among the ambient noise sources and for achieved electron lifetimes. Reduced efficiency for detection of neutrino events. | Threat | Technical Risk |  | Thomas R Junk | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 0 |  | n/a​ |  | 1 - Rough guess |  | ​ A software or FPGA-based stub-finder may be needed to trigger SNB events. |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-060 | LBNF / DUNE | Critical components have limited suppliers | ​Limited suppliers for certain equipment. Specific components are evaluated and qualified for operation in liquid argon locking us into purchasing from a single supplier or doing additional qualification. May need to place large order early to ensure you get the parts. May have to go back into design. | Threat | External Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 20% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 1000 | 2-point - flat range | 2 |  | 6 | 13122.04.03.195 - Install TPC, Detector #1​ |  | 1 - Rough guess |  | ​TBD |  |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 500 | 4 | 100 | 0.8 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-065 | LBNF / DUNE | Radioactive contamination/ dust cause background signals in the TPC or PD system | ​High level contamination controls would be expensive to apply to detector installation and are currently not in the plan. Radioactive contamination could impact threshold for low-energy analyses of data. The availability to study low-energy events could be reduced. | Threat | Technical Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 0 |  | n/a​ |  | 1 - Rough guess |  | TBD​ |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-068 | LBNF / DUNE | Electrostatic discharge causes damage | ​People and objects near sensitive electronics can accumulate charge which can cause discharge and damage electronics. Discharge protection needs to be provided during all steps. Electronics can be damaged to the point where they do not work. Increased cost and schedule will result if ESD mitigation plans are not followed. | Threat | External Risk |  | Theresa M Shaw | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  |  | 25% | 1 (L) - somewhat substandard | 2-point - flat range | 50 |  | 500 | 2-point - flat range | 0 |  | 2 | 13122.04.03.195 - Install TPC, Detector #1​ |  | 1 - Rough guess |  | ​Written procedures should be written for the handling of devices during fabrication, assembly, shipping, unpacking and installation. Workers may need to wear/use protective ESD equipment and follow ESD preventitive handling procedures. ESD protection is being added in some of the ASIC design |  |  | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 275 | 1 | 68.8 | 0.25 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-067 | LBNF / DUNE | Impact gaps between frames is not understood | ​The electic field and therefore the electron trajectory can not be precisely modelled near the gaps of the APAs. Charge collection is not present in gaps. | Threat | Technical Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 0 |  | n/a​ |  | 1 - Rough guess |  | TBD​ |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-072 | LBNF / DUNE | Installation process prototype is required | ​The process of hanging TPC elements will require unique techniques due to the large size and limited handling points on the APA frame. Wires have limited attachment points. An engineering risk assessment of the process of installation indicated high risk across all categories. The project needs to perform a full size installation dry run to work out installation techniques, interfaces, and work estimates. | Threat | Technical Risk |  | Joseph W Howell | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 45% | 2 (M) - significantly substandard | 2-point - flat range | 0 |  | 1000 | 2-point - flat range | 2 |  | 6 | A1480 - 1st 10 kt Detector Procurement & Assembly |  | 1 - Rough guess |  | ​The project is planning on building a full size TPC drift cell and testing the key equipment and installation operations. |  |  | 4 (H) | 1 (L) | 1 (L) | 3 (High) | 500 | 4 | 225 | 1.8 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-070 | LBNF / DUNE | Anode plane assembly is more complex than foreseen | Prior to CD-2 we will have tested full sized APAs in ProtoDUNE. If the changes required to go between ProtoDUNE and DUNE prove more challenging than anticipated then additional engineering effort beyond CD-2 will be required. | Threat | Technical Risk |  | Alberto Marchionni | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  |  | 20% | 1 (L) - somewhat substandard | 3-point - triangular | 200 | 400 | 1000 | 3-point - triangular | 4 | 6 | 12 | A1480 - 1st 10 kt Detector Procurement & Assembly | ​Based on 2.0 FTEs for 6 months | 1 - Rough guess |  | Additional engineering effort planned in FY18/19 and perform trial assembly with 2 APAs. |  |  | 2 (L) | 1 (L) | 2 (M) | 2 (Medium) | 533.3333 | 7.33 | 106.7 | 1.466 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-074 | LBNF / DUNE | Wire pitch may not be adequate | ​May need to reduce the wire pitch from 5 mm to 3 mm. | Threat | Technical Risk |  | Thomas R Junk | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 0 |  | n/a​ |  | 1 - Rough guess |  | TBD​ |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-076 | LBNF / DUNE | More dead channels than expected | ​Detector will degrade over time and channels may die or become noisy to the extent that it is best to ignore them. Loss of channels impacts the ability to identify, reconstruct, and measured neutrino scatters and other events on physics interest. Missing channels will correspond to dead argon volume. Events that originate or pass through the volume that is viewed by these channels may have to be removed from physics analyses. | Threat | Technical Risk |  | Thomas R Junk | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 25% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 0 |  | n/a​ |  | 1 - Rough guess |  | ​ |  |  | 3 (M) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-078 | LBNF / DUNE | Electric field uniformity is not adequate for muon momentum reconstruction | ​Cathode plan and space charge can distort the electric field. Momentum of non-contained muons i measured by estimating the multiple scattering rate for the observed track segments. Degraded resolution for non-contained muon momentum measurements. Affects numu disappearance analyses and the three-flavor fits. Can cause feed-down of high-energy neutrino backgrounds to low-energy reconstructed categories. | Threat | Technical Risk |  | Thomas R Junk | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 0 |  | n/a​ |  | 1 - Rough guess |  |  |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-079 | LBNF / DUNE | Field Cage design using printed circuit boards on a large scale not demonstrated | ​Thin edges of copper traces on the boards have very high electric fields. The electric field along the strip edges are much higher than the rest of the system. A higher risk of HV breakdown at the edges of the field cage strips. | Threat | Technical Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 15% | 0 (N) - negligible technical impact | 2-point - flat range | 50 |  | 500 | 2-point - flat range | 0 |  | 2 | A2630 - 1st 10 kt Detector Testing and Commissioning​ |  | 1 - Rough guess |  | ​35t TPC test will demonstrate the safety of the field cage up to 150kV. Further tests are needed for FD voltage |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 275 | 1 | 41.3 | 0.15 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-064 | LBNF / DUNE | Handling techniques not sufficient to protect from exposure to UV or humidity | ​UV radiation, sunlight, and humidity can affect performance of wavelength shifter and cause reduction in detector effeciency. Wavelength shifting plastics will need to be shielded from UV light and excessive moisture during handling. | Threat | Technical Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 15% | 1 (L) - somewhat substandard | 2-point - flat range | 50 |  | 500 | 2-point - flat range | 0 |  | 2 | 13122.04.04.115 - Detector #1 commissioning​​​ 13122.04.07.230 - Detector #2 commissioning-phase II​ |  | 1 - Rough guess |  | ​TBD |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 275 | 1 | 41.3 | 0.15 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-066 | LBNF / DUNE | Detector does not achieve the measured active/fiducial volume requirement | ​Thermal contraction causes cryostat walls to contract. TPC will move vertically different amounts due to roof pressure deflections. Predicted TPC volume when cold is not correctly predicted from warm installed condition. Signal normalization requirement of level will not be achieved. | Threat | Technical Risk |  | Jack Fowler | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 45% | 1 (L) - somewhat substandard | 1-point - single value |  | 0 |  | 1-point - single value |  | 0 |  | A2630 - 1st 10 kt Detector Testing and Commissioning A1840 - 2nd 10 kt Detector Testing and Commissioning |  | 1 - Rough guess |  | TBD​ |  |  | 4 (H) | 0 (N) | 0 (N) | 2 (Medium) | 0 | 0 | 0 | 0 | 2023-12-12 07:53 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-083 | LBNF / DUNE | Event reconstruction software has insufficient track or shower identification | ​Events that fail quality requirements may need to be removed from analyses if they are not measured well enough to contribute. Results in misreconstructed event topologies, degraded energy resolutions, and possibly loss of the events due to analysis cuts. The particle detection efficincies will be functions of particle energies and event content, so some physics topics may be affected more than others. | Threat | Technical Risk |  | Thomas R Junk | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 0 |  | n/a​ |  | 1 - Rough guess |  |  |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:53 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-084 | LBNF / DUNE | Event reconstruction software cannot perform particle ID sufficiently well | ​Ambiguities and inefficiencies of the hits in the event can result in one species of particle being misidentified as another. Of particular concern is the separation of photon backgrounds from electron signals, thus polluting the nue appearance signal with neutral current backgrounds. Higher background rates and uncertainties on backgrounds will degrade the sensitivity of LBNE to the beam and atmospheric oscillation physics, delaying the publication of relevant results until sufficient data samples are collected. | Threat | Technical Risk |  | Thomas R Junk | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 0 |  | n/a​ |  | 1 - Rough guess |  |  |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:53 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-082 | LBNF / DUNE | Test Beam measurements may be required to achieve scale and accuracy | ​The energy scale may require a calibration measurement with the test beam. The efficiency for neutron detection is not yet well known and may need to be measured. The impact of non-visible energy on reconstruction will need to be determined and may require a calibration measurement with test beam. | Threat | Technical Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 15% | 1 (L) - somewhat substandard | 2-point - flat range | 0 |  | 1000 | 2-point - flat range | 0 |  | 2 | 13122.04.04.115 - Detector #1 commissioning​​​ 13122.04.07.230 - Detector #2 commissioning-phase II​​ |  | 1 - Rough guess |  | ​TBD |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 500 | 1 | 75 | 0.15 | 2023-12-12 07:53 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-073 | LBNF / DUNE | Photon Detector Design has insufficient light yield | If ​PD light yield limit of chosen technology is determined to be insufficient with default number of detector elements then additional PD modules are required which necessitate changes to APA frame design & flange design. | Threat | Technical Risk |  | Alberto Marchionni | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  |  | 10% | 2 (M) - significantly substandard | 3-point - triangular | 200 | 400 | 1000 | 3-point - triangular | 4 | 6 | 12 | A1490 - 1st 10 kt Detector Installation A1800 - 2nd 10 kt Detector Procurement and Assembly | ​Based on 2.0 FTEs for 6 months | 1 - Rough guess |  | ​Strong R&D pre-CD2 |  | 9156 | 2 (L) | 1 (L) | 2 (M) | 2 (Medium) | 533.3333 | 7.33 | 53.3 | 0.733 | 2023-12-12 07:53 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-086 | LBNF / DUNE | Assumed funding sources do not deliver as expected | If assumed funding does not pan out then DOE might need to absorb additional cost. | Threat | Technical Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 50000 |  | 3-point - triangular | 3 | 6 | 9 | ​CD-2 |  | 1 - Rough guess |  |  |  |  | 2 (L) | 3 (H) | 2 (M) | 2 (Medium) | 50000 | 6 | 5000 | 0.6 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-087 | LBNF / DUNE | FD Prototyping indicates need for scope increase | IF FD prototype performance or other experimental work indicates scope increase is necessary for the detector to meet scientific requirements, THEN cost and schedule will increase. | Threat | Technical Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  | ​Duplicated risk | 20% | 2 (M) - significantly substandard | 2-point - flat range | 0 |  | 2000 | 3-point - triangular | 3 | 6 | 9 | A1480 - 1st 10 kt detector procurement and assmbly |  | 1 - Rough guess |  |  |  |  | 2 (L) | 2 (M) | 2 (M) | 2 (Medium) | 1000 | 6 | 200 | 1.2 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-088 | LBNF / DUNE | Cold ASIC chip set is unavailable | IF the cold ASIC chip set is unavailable for installation THEN installation will be delayed. | Threat | Technical Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 5% | 1 (L) - somewhat substandard | 1-point - single value |  | 4000 |  | 3-point - triangular | 6 | 12 | 18 | 13122.06.01.11.200MS - T6 MS - Cold Electronics Installation begins​​ |  | 1 - Rough guess | The custom ADC chips do not meet the DUNE specifications | ​The demonstration by the SBND Collaboration that a commercial ADC can be operated in LAr and that it has a lifetime exceeding the requirements of DUNE already provides the backup plan. |  |  | 1 (VL) | 2 (M) | 3 (H) | 2 (Medium) | 4000 | 12 | 200 | 0.6 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-092 | LBNF / DUNE | Late delivery of technical components for CERN prototype | If ProtoDUNE components are late being delivered to CERN then the integration engineering test may be delayed which could delay CD2/3b because TDR inputs would not be available. | Threat | Management Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  |  | 25% | 0 (N) - negligible technical impact | 3-point - triangular | 250 | 500 | 750 | 3-point - triangular | 1 | 6 | 12 | CD-2 | ​Cost is derived from continued prototyping past expected time frame | 1 - Rough guess | ​Insufficient resources, technical and/or production complications that arise, fabrication slower than anticipated, design completion delay, failed testing of components | This risk has been partially realized for protoDUNE-SP, hopefully with no impact on the actual data taking. In some sense one could close this risk. On the other hand it is very likely that a 2nd run of protoDUNE will take place in 2021/2022, allowing for a repetition of the risks contained in this entry. For the 2nd run of protoDUNE, the risk should be smaller, first because of the longer amouint of time available to prepare, and second because other test stands are being arranged (including the use of the protoDUNE cold box), to test various solutions prior to the shipment of the detector components to CERN. |  |  | 3 (M) | 1 (L) | 2 (M) | 2 (Medium) | 500 | 6.33 | 125 | 1.5825 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-089 | LBNF / DUNE | FD1 PD SiPMs are not qualified for cryogenic use | If the PD SiPMs are found to have quality problems at cryogenic temperatures such as cracking or failure of devices, then other solutions will have to be developed such as replacing sensor with alternate design. | Threat | Technical Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  | ​After cold testing representative samples of production SiPMs | 5% | 0 (N) - negligible technical impact | 2-point - flat range | 15 |  | 60 | 2-point - flat range | 4 |  | 6 | 13122.A12424 (PRR for remaining PD system) | Extra testing at NIU may be required. Experience from ProtoDUNE I, started fab and packaging design changed, discovered problems, faces started cracking and problems with devices. | 2 - Reasonable estimate |  | ​Risk and mitigation were realized for ProtoDUNE, currently testing commercial solution from Hamamatsu & FBK that may eliminate this risk. |  |  | 1 (VL) | 0 (N) | 1 (L) | 1 (Low) | 37.5 | 5 | 1.9 | 0.25 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-094 | LBNF / DUNE | Far Detector Engineering resources are inadequate | ​If engineering resources needed for CD2 are unavailable or targeted towards ProtoDUNE then needed work on Far Detector Technical design will not be accomplished on time. | Threat | Management Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  |  | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - | ​Competing priorities - ie. SBN, redirecting resources to ProtoDUNE, inadequate planning of technical resources | ​Hire additional technical resources, refine estimates |  |  | 1 (VL) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-093 | LBNF / DUNE | Far Detector Technical interfaces not adequately defined or identified | If during Far Detector installation an incompatibality between subsystems is identified then additional rework is required to solve the problem | Threat | Technical Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 15% | 1 (L) - somewhat substandard | 3-point - triangular | 0 | 500 | 2000 | 3-point - triangular | 0 | 3 | 12 | 13122.04.03.195 - Install TPC, Detector #1​​​ | ​Some level of rework requiring engineering and technical resources | 1 - Rough guess | ​discovery of incompatible interface during installation/integration | ​Implement lessons learned from ProtoDUNE, execute integrated test stands and trial installations, perform production readiness reviews, preparation and review of interface control documentation | ​ |  | 2 (L) | 2 (M) | 2 (M) | 2 (Medium) | 833.3333 | 5 | 125 | 0.75 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-095 | LBNF / DUNE | Insufficient performance of Single Phase ProtoDUNE Detector | ​If ProtoDUNE detector is installed and operating in 2018 but unsuccessful, then another prototyping round may have to be considered prior to CD2 | Threat | Technical Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 10% | 2 (M) - significantly substandard | 3-point - triangular | 200 | 500 | 750 | 3-point - triangular | 12 | 15 | 24 | 13122.02.01.04.160 - Fabricate/Assemble APAs at Assembly Area - DOE​​ | ​Rough estimate for rework of components Schedule based on emptying, access, rebuild, and refill cryostat | 1 - Rough guess | ​ProtoDUNE operations | Integration testing, cold testing of components​, concurrent prototyping test of alternate technical (DP) | ​Revise strategy for technology choice |  | 2 (L) | 1 (L) | 3 (H) | 2 (Medium) | 483.3333 | 17 | 48.3 | 1.7 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-096 | LBNF / DUNE | Scientific support is inadequate to progress technical designs | ​If we dont get enough scientific resources can not do systematic studies then CD-2 will be delayed | Threat | Management Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 15% | 2 (M) - significantly substandard | 1-point - single value |  | 0 |  | 3-point - triangular | 0 | 3 | 12 | 13122.02.01.04.160 - Fabricate/Assemble APAs at Assembly Area - DOE​ | ​Based on needing data from ProtoDUNE | 1 - Rough guess | Competing scientific interest | ​Collaboration engagement of task forces and working groups, irresistable scientific opportunity |  |  | 2 (L) | 0 (N) | 2 (M) | 2 (Medium) | 0 | 5 | 0 | 0.75 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-097 | LBNF / DUNE | ProtoDUNE-SP: Broken wires on APA |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​execute installation trial assembly to practice handling techniques & process |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-099 | LBNF / DUNE | ProtoDUNE-SP: Installation complications (equipment / tooling) |  | Threat |  |  | Jack Fowler | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​execute trial assembly |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-100 | LBNF / DUNE | ProtoDUNE-SP: Components arrive late to CERN, with implications for cold testing |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 50% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​Include adequate lead times for procurement and shipping in schedule |  |  | 4 (H) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-101 | LBNF / DUNE | ProtoDUNE-SP: Detector components not tested prior to installation |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​Nothing to be installed that is not tested. First test at production site, then integration & cold testing at CERN |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-102 | LBNF / DUNE | ProtoDUNE-SP: Cable lengths complicate installation / operation |  | Threat |  |  | Matthew P. Worcester | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​use right-sized cable lengths; perform trial runs of the cable routing & assembly prior to final design |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-103 | LBNF / DUNE | ProtoDUNE-SP: Unknown conditions in cryostat during operations |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​install cameras in cryostat |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-104 | LBNF / DUNE | ProtoDUNE-SP: Loss of key staff prior to project completion |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 50% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  |  |  | 4 (H) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-105 | LBNF / DUNE | ProtoDUNE-SP: Grounding issues at EHN-1 |  | Threat |  |  | Theresa M Shaw | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​Develop grounding & shielding plan in cooperation with CERN safety personnel |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-106 | LBNF / DUNE | ProtoDUNE-SP: Kapton tape dissolves in LAr |  | Threat |  |  | Jack Fowler | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 5% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​identify a LAr compatible wrap or jacket for cable bundles; Tefzel cable ties used in 35t |  |  | 1 (VL) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-098 | LBNF / DUNE | ProtoDUNE-SP: Degraded Photon Detectors |  | Threat |  |  | Leon M. Mualem | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 5% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​install PD as late as possible into APAs |  |  | 1 (VL) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-107 | LBNF / DUNE | ProtoDUNE-SP: Detector damage caused by loose hardware |  | Threat |  |  | Jack Fowler | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 5% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​all hardware should be captive to the connector |  |  | 1 (VL) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-108 | LBNF / DUNE | ProtoDUNE-SP: Confusion due to inconsistent numbering schemes of components |  | Threat |  |  | Jack Fowler | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 5% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​Employ consistent number of components; overseen by protoDUNE-SP configuration manager at CERN |  |  | 1 (VL) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-110 | LBNF / DUNE | ProtoDUNE-SP: Inadequate operational control due to poor cyrogenic control interface |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-109 | LBNF / DUNE | ProtoDUNE-SP: Commissioning delayed due to failed equipment |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 5% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​test all equipment prior to delivery at CERN; test again prior to installation |  |  | 1 (VL) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-111 | LBNF / DUNE | ProtoDUNE-SP: Components fail integration testing |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-112 | LBNF / DUNE | ProtoDUNE-SP: Components fail cold testing |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-113 | LBNF / DUNE | ProtoDUNE-SP: Checkout procedures for components are unavailable |  | Threat |  |  | Matthew P. Worcester | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-114 | LBNF / DUNE | ProtoDUNE-SP: Hardware requirements not communicated to subsystem; 35t problem perpetuate | ​Hardware requirements not communicated to subsystems; 35t problems perpetuated at protoDUNE-SP | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​Requirements communication; relevant 35t lessons learned reviewed with each L3 manager |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-115 | LBNF / DUNE | ProtoDUNE-SP: Electronics noise levels impair run results |  | Threat |  |  | Matthew P. Worcester | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-118 | LBNF / DUNE | ProtoDUNE-SP: Delay in testing, installation, commission, due to component failure |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​have spares available; allows for concurrent testing, prompt replacement in case of failure |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-117 | LBNF / DUNE | ProtoDUNE-SP: Photon Detector monitoring software is unavailable for commissioning |  | Threat |  |  | Leon M. Mualem | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-122 | LBNF / DUNE | ProtoDUNE-SP: Computing support from FNAL/CERN is inadequate |  | Threat |  |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​Joint team working to quantify and establish institutional support |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-120 | LBNF / DUNE | ProtoDUNE-SP: Resource competition with other experiments (e.g., SBN) |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 50% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  |  |  | 4 (H) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-121 | LBNF / DUNE | ProtoDUNE-SP: Resource competition with CD2 effort |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​Each L3 manager to prioritize production, testing, delivery & installation activities and promptly redirect effort to CD2 as each phase of work is completed |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-119 | LBNF / DUNE | ProtoDUNE-SP: Equipment failure due to failed ventilation / cooling |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​install temperature interlocks on DAQ racks |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-123 | LBNF / DUNE | ProtoDUNE-SP: Inefficiences due to lack of clarity regarding lines of responsibility |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​Frequent communication; establish clarity on interfaces |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-126 | LBNF / DUNE | ProtoDUNE-SP: Grounding plan is not implemented correctly |  | Threat |  |  | Theresa M Shaw | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  | ​do not run protoDUNE-SP |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-125 | LBNF / DUNE | ProtoDUNE-SP: Communication problems due to geographic dispersal |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​Designate key personnel for each WBS, each phase of work |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-124 | LBNF / DUNE | ProtoDUNE-SP: Inefficiency due to lack of clarity regarding incremental goals & milestones |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-127 | LBNF / DUNE | ProtoDUNE-SP: Catastrophic contamination of LAr in the cryostat |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​utilize monitoring mechanisms |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-129 | LBNF / DUNE | ProtoDUNE-SP: Insufficient project management resources |  | Threat |  |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-130 | LBNF / DUNE | ProtoDUNE-SP: APA wiring more complex than anticipated |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-131 | LBNF / DUNE | ProtoDUNE-SP: Unable to maintain HV at 180kV |  | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​develop testing plan and operate at lower voltage |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-132 | LBNF / DUNE | ProtoDUNE-SP: Engineering staff resources insufficient |  | Threat |  |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​continue EOI outreach with collaborating institutes |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-134 | LBNF / DUNE | Redesign flanges on the chimneys to allow additional connections | ​The flanges on the chimneys have to be redesigned to allow for additional connections, without changing the design of the feedthroughs | Threat | Technical Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​Risk should be closed once the detector integration has been completed | 5% | 0 (N) - negligible technical impact | 2-point - flat range | 200 |  | 400 | 2-point - flat range | 3 |  | 6 | 13122.04.03.195 - Install TPC, Detector #1​​ | ​Engineering time for redesigning the flanges and fabricating new ones | 0 - Wild guess | ​Realize that a new design of the flanges is required to accomodate additional connections (increase in the number of voltages for the field cage termination electrodes and/or the electron diverters, additional wires for RTDs or detector status monitoring, additional connections for detector commissioning) | Early design and thorough estimate of the required number of connections prior to design completion. Allow for a few spare connectors on the flanges.​ |  |  | 1 (VL) | 1 (L) | 1 (L) | 1 (Low) | 300 | 4.5 | 15 | 0.225 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-133 | LBNF / DUNE | Redesign of electronic components would be necessary if technology becomes unavailable. | If a certain technology becomes unavailable between the engineering phase and the start of production, a new design to adapt to a new technology may be necessary​. Examples include: changes in ASIC foundry process availability, availability of optical transmitters / receivers.​ | Threat | External Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  | ​Risk should be closed (for the first far detector) when all the orders for the various electronics components have been received. A similar risk should be added to the following far detectors, even in the assumption that these are built exactly like the first one | 5% | 0 (N) - negligible technical impact | 3-point - triangular | 400 | 500 | 1000 | 2-point - flat range | 3 |  | 9 | 13122.04.07.175 - Install TPC, Detector #2​ | ​The estimate is based on the need of redesigning electronic boards or ASICs, transferring from one technology to another. This is based on the assumption that certain technlogies (like 130nm or 65nm) do not become completely unavailable, and that one has to adapt simply to using a different foundry and possibly different design rules. Redesigning entirely the ASICs in a new technology (for example porting the FE ASIC from 130nm to 65nm could be more costly and time consuming - should we add a 2nd risk with lower probability and larger impact ?) | 1 - Rough guess | ​Vendor informs us that certain technologies are no longer available | ​Keep informed of technology trends, and plan for redesign if we feel that certain technologies are going to become unavailable in the short term. Ensure that we use widely adopted technologies that are unlikely to become unavailable on a timescale of 10 years. To reduce the possible impact on a 2nd Singe Phase TPC detector, we should consider the purchase of all the ASICs as soon as the production of ASICs for the 1st detector. |  |  | 1 (VL) | 1 (L) | 2 (M) | 1 (Low) | 633.3333 | 6 | 31.7 | 0.3 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-135 | LBNF / DUNE | Cold electronics cables cannot be routed through APA frames | If the cold electronics cables cannot be routed through the APA frames, because all the space is taken by other cables or because the openings are not sufficient, then additional design is needed. | Threat | Technical Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  | ​Demonstrate with prototypes / mockups that the cable routing is feasible in a system of two stacked APAs | 10% | 0 (?) - Not yet defined | 2-point - flat range | 1500 |  | 2000 | 2-point - flat range | 3 |  | 6 | 13122.02.01.04.160 - Fabricate/Assemble APAs at Assembly Area - DOE​​​​ | ​Design a system for allowing the routing of cables outside the anode planes | 0 - Wild guess | ​Changes in the design of the APA frame or requirement for additional space for the photon detectors | The size of the APA frame has been increased from 4"x3" to 4"x4" and trials are being made at PSL to demonstrate that the cables can be routed through the APA frames. The photon detector cables have been already routed differently inside the APA volume. After the initial tests at PSL further tests will be made at Ash River, first with APA tubes, and then in 2019 with two APA mechanicel frames. In the meantime studies are ongoing to reduce the number of cables that have to be routed through the APA frame. A preliminary solution appears to be available (end June 2018).​ |  |  | 2 (L) | 2 (M) | 1 (L) | 2 (Medium) | 1750 | 4.5 | 175 | 0.45 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-116 | LBNF / DUNE | ProtoDUNE-SP: Scientific resources unavailable for testing, commissioning, diagnostics | ​Scientific resources unavailable for testing, commissioning, diagnostics, running; ProtoDUNE-SP is unable to attract scientific talent based on the limited physics opportunities (career implications) | Threat |  |  | Steve Kettell | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 50% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  | ​Seek DOE operations fund support to enable travel, stipends |  |  | 4 (H) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-138 | LBNF / DUNE | Winder modifications do not provide enough reduction in time for APA construction. | ​If it is not possible to reduce the manufacturing time of an APA from the present 80 shifts to 60 by middle of 2019 because of complexity of the winding procedure and tight manufacturing tolerances, then the APA construction schedule will be impacted. | Threat | Technical Risk |  | Alberto Marchionni | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  | Closed based on production optimization from ProtoDUNE - able to fabricate an APA in 40 shifts. | 15% | 1 (L) - somewhat substandard | 1-point - single value |  | 1400 |  | 1-point - single value |  |  |  | ​A1480 - 1st 10 kt Detector Procurement & Assembly | ​Out of the 4 production lines foreseen in the US, to compensate a 30% increase in production time, 1 additional production line is needed. Additional winder cost 400k$ + 5 FTE to cover operation for 2.5 years.. | 1 - Rough guess |  | ​Additional engineering effort planned in FY18/19. | ​Increase the number of assembly lines to produce the total number of APAs within the required time. |  | 2 (L) | 2 (M) | 0 (N) | 2 (Medium) | 1400 | 0 | 210 | 0 | 2022-08-10 08:31 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-136 | LBNF / DUNE | Excess noise observed during commissioning due to non-respect of grounding rules | During commissioning of the detector prior to LAr filling we discover that there is excessive noise due to some detector components having violated the grounding rules​ | Threat | Technical Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 10% | 1 (L) - somewhat substandard | 2-point - flat range | 200 |  | 500 | 2-point - flat range | 3 |  | 6 | 13122.04.04.115 - Detector #1 commissioning​​​ 13122.04.07.230 - Detector #2 commissioning-phase II​​​​ | ​Assume that noise studies have to be performed and then interventions made to alleviate the noise sources | 0 - Wild guess | ​Somebody decides to implement some feature in the detector and violate or ignores the grounding rules (just happened for APA #2 of protoDUNE, when RTDs were added without proper filtering at the flange) | ​Ensure that grounding rules are enforced, review any proposed modification of the detector design. |  |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 350 | 4.5 | 35 | 0.45 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-137 | LBNF / DUNE | Low yield of components | ​If the ASICs or printed circuit boards have low yield during detector fabrication, production would be delayed. | Threat | Technical Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 400 |  | 800 | 1-point - single value |  | 2 |  | 13122.04.03.195 - Install TPC, Detector #1​​ | ​Time for fabricating and testing new ASICs / printed circuit boards. Assume that if the risk is realized, corrective actions (fabrication of additional components) are taken as soon as possible to minimize the time impact (the fabrication of the detector is a serial process, if this risk is observed early enough there should be a very small time impact) | 0 - Wild guess | ​Low yield observed during the production. In case the yield affects late batches of ASICs/printed circuit boards, the impact could be larger (add 2nd risk with low probability and large time impact ?) | ​Planning for spares or system test stands should be a priority. Conservative planning of yields, monitoring of the production |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 600 | 2 | 60 | 0.2 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-139 | LBNF / DUNE | Large number of unusable/dead channels in ProtoDUNE due to mechanical problems. | ​We are planning for less than 1% channel failure. If ProtoDUNE results point to a larger failure rate due to wire breakage, loose wires, warping of the frame, then it could delay the start of APA construction or even of CD2. | Threat | Technical Risk |  | Alberto Marchionni | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  |  | 10% | 1 (L) - somewhat substandard | 1-point - single value |  | 250 |  | 2-point - flat range | 3 |  | 6 | ​A1480 - 1st 10 kt Detector Procurement & Assembly | ​2.5 FTE for 6 months | 1 - Rough guess |  | Cold box test at CERN. | ​Allocate enough engineering/scientific resources to understand the cause of the problem. Improve the design and QA/QC procedures. |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 250 | 4.5 | 25 | 0.45 | 2022-08-10 08:31 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-130 | LBNF / DUNE | [CRYO] Cryogenic safety review process takes longer than planned for Detectors #1 and #2 | ​If the expedited crygenic safety review process presently planned takes longer, then the detector operations will be delayed. | Threat | Technical Risk | NO | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2027-09-01 | 2029-06-30 | ​Completion of cryogenic safety review process for Detector #1. ​Completion of cryogenic safety review process for Detector #2. #2 will be informed by #1, so risk will likely be updated after that. | 40% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | 126 | 376 | 3-point - triangular | 0 | 1 | 3 | Risk hooks: ​1) 131123.01.01.586MS --> RT-131-FDC-CR-130-A --> 131123.04.04.03.17 2) 131123.01.01.587MS --> RT-131-FDC-CR-130-B --> 131123.04.04.04.47 Risks CR-130-A and CR-130-B are uncorrelated | ​The cost impact for one instance (FD1 or FD2) of the risk event is: 2 FTEs for 1 months @ $375k/yr per FTE = $62.5k cost impact. 2 FTEs for 3 months @ $375k/yr per FTE = $187.5k cost impact. The total risk impact shown above is summed over FD1 and FD2. The schedule risk is related to the complexity and uniqueness of the LBNF cryostat/cryogenics installation with respect to all other installations done so far on the Fermilab premises. Schedule impact is for one or other of the FD1 or FD2 risk events. | 2 - Reasonable estimate | ​Currently planned duration for cryo safety review assumes expedited process through early engagement of cryo safety panel. This may not have been enough to offset this risk. The timescale of this project is also a potential factor as subcommittee membership and chairmanship change over time. While the work with the subcommittee advances and decisions are recorded, there is a learning curve and new members seem interested to at least review what was done in the past. | Early engagement of cryo safety panel. Production, collection, and provision of documentation as early as possible​. Working through unique codes and standards and testing proccesses. Gathering consensus on procedures, codes and regulations. Sharing knowledge with non-DOE parties. Bridging cultural differences. When approaching the time of construction, if possible, update the composition of the LBNF cryo safety subcommittee to provide stability and a consistent approach going forward, according to mutualluy agreed processes and timelines. |  |  | 4 (H) | 1 (L) | 1 (L) | 2 (Medium) | 167.3333 | 1.33 | 66.9 | 0.532 | 2023-12-12 07:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-141 | LBNF / DUNE | Production problems during APA fabrication result in rework | If more wire planes are outside the required tolerances than estimated, then the APA production schedule will be affected. | Threat | Technical Risk |  | Alberto Marchionni | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  |  | 20% | 1 (L) - somewhat substandard | 2-point - flat range | 0 |  | 1000 | 2-point - flat range | 0 |  | 12 | 13122.02.01.04.160 - Fabricate/Assemble APAs at Assembly Area - DOE​​​​​​ | ​Assumed about 10% cost and schedule impact for APA production | 2 - Reasonable estimate | ​Personnel turnover, insufficient QA implementation, difference in various construction sites, winder issues | ​Strict requirements for QA need to be set at the start of the project, together with formal training of every technician/operator of the winding machine. |  |  | 2 (L) | 1 (L) | 2 (M) | 2 (Medium) | 500 | 6 | 100 | 1.2 | 2022-08-10 08:31 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-142 | LBNF / DUNE | Personnel with poor qualification at the integration site damages detector | ​This risk should be seen as a complement to RT-131-FD-121. It assumed that personnel from institutions will contribute to work done at the integration facility. This personnel (in particular undergraduate students) may not be as qualified or committed to the project as personnel (including scientist, postdocs, and students) from other DUNE institutions, or may not be able to identify problems as they occur, resulting in delays or extra expenditures for repairs or modifications to detector components | Threat | Technical Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 25% | 1 (L) - somewhat substandard | 2-point - flat range | 0 |  | 1000 | 2-point - flat range | 2 |  | 6 | ​A1490 - 1st 10 kt Detector Installation |  | 1 - Rough guess | ​Decision of DUNE management to have the integration facility in a remote location, and possibly use personnel from local institutions (in particular undergraduate students) that may not be as experienced or committed as staff scientists, engineers, technicians, postdocs and graduate students that are member of the DUNE collaboration. Experience from other experiments indicate that the quality of work performed by undergraduate students not really interested in the project may be substantially lower, depending on the training and the level of supervision by more experienced personnel. | ​Ensure that during the integration at the remote facility the fraction of experienced personnel that is made of engineers and technicians as well as scientific personnel (including postdocs and graduate students) from DUNE collaborating institutions with the sufficient expertise to deal with the detector components being assembled and tested is at least 50% of the total number of people working at the integration site in every job category. ​Ensure that sufficient funding for travel / temporary relocation, and appropriate accomodations (in terms of office space and meeting rooms) are made in the planning of the remote facility. | ​If an insufficient yield is observed during integration and testing, increase the fraction of experienced personnel compared to the original plans and/or increase the training and supervision of undergraduate students from local institutions. |  | 3 (M) | 1 (L) | 1 (L) | 1 (Low) | 500 | 4 | 125 | 1 | 2022-08-10 08:31 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-143 | LBNF / DUNE | Additional storage space required at the Integration and Test Facility | ​Accumulation of detector components at the Integration and Test Facility (either before or after integration and testing have taken place) saturates the available storage space, requiring the rental of an additional warehouse | Threat | Management Risk |  | Eric B James | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​The risk can be retired or closed only if a detailed plan exists for the construction of all the DUNE detector modules showing that the available storage space at the Integration and Test Facility will be sufficient at all times during the detector construction, or only after the detector construction has been completed. | 20% | 0 (N) - negligible technical impact | 2-point - flat range | 300 |  | 1500 | 2-point - flat range | 2 |  | 6 |  | ​I have assumed (google) that warehouse space in Rapid City could be rented at a cost of 1$/square foot/month, assumed an area of 50,000 square feet, and assumed that this space would be needed for somewhere between 0.5 and 2.5 years. The lower boundary is an estimate of the maximum delay between the availability of the APAs and that of the Cold Electronics, the upper boundary is obtained assuming that the APAs for two single phase detectors are built at full speed but then installed in cryostats 1 and 3, meaning that the full contingent of APAs for detector 2 need to be stored somewhere. The delay of 2-6 months is taken assuming that the search for the warehouse space will cause a stoppage of the production. | 2 - Reasonable estimate | ​There are various scenarios in which this risk can be realized:. The single phase detector is used as an example, but a similar risk (probably with a lower probability since the total number of detector components is smaller) could also take place for the dual phase detector. 1) the production of the APAs starts earlier than that of the cold electronics and/or of the photon detector, and APAs accumulate at the integration facility because they cannot be populated and tested, requiring extra warehouse space 2) the integration of APAs proceeds as planned but they cannot be transported to SURF due to a delay in the availability of the cryostat. The case in which the production of the APAs for two single phase detectors proceeds at full speed but then cryostats 1 and 3 are filled with single phase detectors is a particular realization of this scenario. | ​This risk can be mitigated by accurate production and logistic plans, including building an integration facility with sufficient storage space. ​If the likelihood of this risk being realized increases (due to delay in the availability of some detector components, or due to the decision to build / integrate single phase detectors to be installed in cryostats 1 &3 as if they were going to be installed in cryostats 1 &2 ) detailed estimations of the space needs as a function of time should be made in advance such that the extra warehouse space can be found in time without incurring any delays due to construction stoppages. | ​If the risk is realized the only possible responses are either a production stoppage (which will entail extra labor costs and additional risks in restarting a production) or the rental of additional warehouse space. |  | 2 (L) | 2 (M) | 1 (L) | 2 (Medium) | 900 | 4 | 180 | 0.8 | 2022-08-10 08:31 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-144 | LBNF / DUNE | Insufficient number of spares during installation | If the failures are larger than expected then we may not have a sufficient number of components to complete the detector​. For the installation/integration of the TPC components that are installed inside the cryostat we will assume that a certain number of spares will be necessary for replacing parts that are detected to be non-fully functional during testing, prior to the closure of the cryostat. | Threat | Technical Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  | ​This risk can be closed once the cryostat is filled with LAr | 15% | 0 (N) - negligible technical impact | 2-point - flat range | 1200 |  | 3000 | 2-point - flat range | 2 |  | 6 | 13122.04.03.195 - Install TPC, Detector #1​​​ | The cost estimate assumes 10% for CE and 2 APAs for APAs. To revisit spare plan. Revise this estimate after project cost estimate is complete | 1 - Rough guess |  | ​Monitor the usage of spares of any components that are going to be installed inside the cryostat and eventually produce more components of the kind for which the inventory becomes critical. Choose appropriately the fraction of spares such that the inventory is largest for those components (most probably the ASICs) have the longest lead time. | ​​If the risk is realized a delay may arise because the need for launching new production and or repairs of hese components. If the risk is realized the inventory of all spares should be reassessed.​ |  | 2 (L) | 2 (M) | 1 (L) | 2 (Medium) | 2100 | 4 | 315 | 0.6 | 2022-08-10 08:31 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-128 | LBNF / DUNE | ProtoDUNE-SP: Fall 2016 FNAL HV integration test fails |  | Threat |  |  | Victor J. Guarino | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  | ​run without the beam plug |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-145 | LBNF / DUNE | Scientific support is inadequate during construction / commissioning | ​If the scientific resources are insufficient during the construction phase the quality control process may lag behind the construction and eventual installation, resulting in components of insufficient quality being installed. If they are detected at a later stage, this may require reworking components, or delay in installation because higher quality components are required. | Threat | Management Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 1 - draft |  |  | ​This risk can be closed only once the detector fully commissioned | 5% | 1 (L) - somewhat substandard | 2-point - flat range | 500 |  | 1500 | 2-point - flat range | 6 |  | 12 |  | ​Wild guess | 0 - Wild guess | ​If the scientific resources are insufficient during the construction phase the quality control process may lag behind the construction and eventual installation, resulting in components of insufficient quality being installed. If they are detected at a later stage, this may require reworking components, or delay in installation because higher quality components are required. | ​​Collaboration engagement of task forces and working groups. Constant review of the testing procedures, analysis results, and review of the quality control process during production. | ​If this risk is realized (i.e. low quality components are identified only at later stages of testing, possibly after integration with the APAs or even worse after installation in the cryostat) a delay may arise because components may have to be reworked, or because one may have to wait for parts with better quality, or because fully integrated APAs have to be extracted from the cryostat. Once the risk is realized, the delay will have to be taken into account, and the whole quality control process may have to be revisited and improved. Depending on the possible yield issues we may have to use a significant fraction or all of the planned spares, resulting also in possible cost increases, because additional parts may have to be fabricated.​ |  | 1 (VL) | 2 (M) | 2 (M) | 1 (Low) | 1000 | 9 | 50 | 0.45 | 2022-08-10 08:31 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-150 | LBNF / DUNE | APA assembly takes longer time than planned | ​The estimated uncertainty on the labor for APA assembly is 30%. This may lengthen the time required to produce 75 APAs by 30%. | Threat |  |  | Alberto Marchionni | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 15% | 1 (L) - somewhat substandard | 1-point - single value |  |  |  | 2-point - flat range | 0 |  | 9 | ​SP-APA #1 131.02.02.20.02.03.06.02 SP-APA #2 131.02.02.20.02.04.06.02​ | ​This is a risk on the schedule delay, additional labor resources have been already taken into account as part of the estimated uncertainty on cost. We assume a 15% probability for this risk with a maximum impact of 30% on the schedule (the production of 75 APAs takes about 30 months). | - Not yet defined - |  | ​Formal training of every technician/operator of the winding machine in order to maintain a high production efficiency. |  |  | 2 (L) | 0 (N) | 2 (M) | 2 (Medium) | 0 | 4.5 | 0 | 0.675 | 2022-08-10 08:31 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-010 | LBNF / DUNE | [PM] Unavailability of SURF-/FRA-supplied systems at SURF - High P / Low impact | ​IF systems at SURF don't work as required THEN schedule delays may occur.​ (ventilation or shaft systems). High probability, low impact version. See RT-131-FDC-PM-012 for the low probability, high impact version. This risk covers the FDC period after the completion of the BSI suproject (September 2025 to December 2028). Between the start of FDC work at SURF (October 2024 and August 2025) this risk is covered by risk RT-131-FSCF-BSI-012​. | Threat | External Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-08-01 | 2028-06-30 | ​​Completion of FS work | 50% | 0 (N) - negligible technical impact | 3-point - triangular | 375 | 750 | 1500 | 3-point - triangular | 0.5 | 1 | 2 | Risk hook: 13141.04.02.275MS --> RT-131-FDC-PM-010 --> 13141.01.01.576 | ​​​Potential system failures that would affect the entire project include ventilation fan failure or failure to shaft ​systems​ (shaft, hoists, conveyances). Highest impact would be a fan failure, which could take 2 months for an electrical component, 6 months for a new fan wheel. 12 months to replace the cage. Cost impact is based on $750k per month (see RT-131-FDC-PM-012). | 1 - Rough guess | ​​Shutdown of some part of ventilation system or hoisting system | ​Implement planned SURF Reliability​ Projects to increase uptime. Regular maintenance is necessary to be sure equipment is available. Several reliability projects associated with hoists have been added to the project scope to reduce this risk, but until completed these project themselves may increase the risk of a delayed start. Ensure spares are available on-site for repairs | ​​If risk occurs, mobilize temporary equipment such as generators, fans, utilize yates shaft for access​. |  | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 875 | 1.17 | 437.5 | 0.585 | 2024-01-13 12:43 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-148 | LBNF / DUNE | Delay in the availability of components at the Integration and Test Facility | If some of the components (APAs, FEMBs from the CE consortium, photon detectors from the PDS consortium) are not available, then the integration schedule gets delayed, which could result in an overall delay of the integration and then installation schedule, possibly affecting the LBNF/DUNE KPP​ | Threat | Management Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  | This risk can be closed when the integration of all the APAs for the SP detector(s) is completed including a sufficient number of spares.​ | 25% | 0 (?) - Not yet defined | 1-point - single value | 300 |  | 800 | 2-point - flat range | 2 |  | 6 | 13122.04.03.195 - Install TPC, Detector #1​​​ | ​The cost / schedule impact are for the moment a rough guess. They should be replaced by a better estimate which includes a) standing army costs at the ITF (both in terms of local personnel and personnel coming from DUNE institutions and resident at the ITF), b) extra costs for additional shifts at the ITF to recuperate part of the delays. | 1 - Rough guess | ​This risk would be realized if any of the components (some of them US responsibility, some from international partners) are delivered late at the integration and test facility. This would cause a delay in the integration and test activities, and depending on whether this delay can be reabsorbed, this would also cause a delay in the installation. | ​In addition to monitoring the production of all components, spare capacity should be available (in terms of working areas for the integration, test benches) at the ITF to allow for a more compressed schedule for the integration of APA, CE, and PDS detector components. This would allow to recuperate part of the delays and avoid further delays in installation. | ​​If the risk is realized provide additional personpower at the ITF to ensure that the delay can be compensated by a compressed integration schedule. Estimated cost $400k |  | 3 (M) | 1 (L) | 1 (L) | 1 (Low) | 0 | 4 | 0 | 1 | 2022-08-10 08:31 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-157 | LBNF / DUNE | [CRYO] Partners require engineering assistance to design and deliver IKC | ​If partners require engineering assistance to design and deliver in-kind contributions​, then additional DOE funded engineering resources will be required. | Threat | External Risk | NO | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-03-01 | 2024-05-31 | ​Partner commitments to perform engineering & design. | 50% | 1 (L) - somewhat substandard | 3-point - triangular | 264 | 1501 | 2739 | 3-point - triangular | 1 | 2 | 4 | Risk hook: 131123.02.02.2631 --> RT-131-FDC-CR-157 --> 131123.02.02.441MS | 1.0​ FTE for 4.5 years, 275k/year. This will be applied to these systems: - LAr items on mezzanine ($1.5M) 0.5 FTE for 4.5 years, $275k/year. This will be applied to this system: - LAr circulation and LAr Pumps ($0.75M). 0.5 FTE for 4.5 years, $275k/year. This will be applied to this system: - Ar distribution piping ($0.4M). - GAr/LAr Filtration and Regeneration + Copper/Mol Sieve ($0.4M) Travel: - LAr Items on mezzanine ($83k). -GAr/LAr Filtration and Regeneration + Copper/Mol Sieve ($81k). -LAr circulation and LAr Pumps ($69k). - Internal Cryogenics ($31k). The minimum cost impact is just the travel. The most likely cost impact is half the resources needed + travel. The maximum cost impact is labor + travel. Assumed realistic schedule impact to identify suitable resources and secure them: - Min --> 1 mo. - Most likely --> 2 mo. - Max --> 4 mo. No additional cost associated with this, just the time needed to secure additional resources Assume low Technical Impact as we would not let the partners continue the work without proper oversight. Goal is to preserve quality of work. | 3 - Solid estimate | ​Agreement with partners for delivery of in-kind contributions and their level of committment. | ​​Engage with potential partners and understand their committment and approach to deliverying these systems. |  | https://docs.dunescience.org/cgi-bin/sso/RetrieveFile?docid=10836&filename=Travel%20estimate%20FY20%20Rev%204.xlsx&version=5 | 4 (H) | 2 (M) | 1 (L) | 3 (High) | 1501.3333 | 2.33 | 750.7 | 1.165 | 2023-12-21 09:19 | David Montanari | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-152 | LBNF / DUNE | Insufficient scientific manpower at APA assembly factories | ​1.5 FTE at each production line are assumed to be uncosted scientific manpower. If it is not possible to recruit scientific resources, costed professional manpower is needed and costs will increase. | Threat | Management Risk |  | Alberto Marchionni | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  | Risk will remain until all fabrication is complete | 50% | 0 (N) - negligible technical impact | 3-point - triangular | 1000 | 3500 | 7000 | 1-point - single value |  | 0 |  | ​Apply 16.4% to 131.02.02.02.09.4.1.3 Apply 16.4% to 131.02.02.02.09.4.1.4 Apply 16.4% to 131.02.02.02.09.4.2.3 Apply 16.4% to 131.02.02.02.09.4.2.4 Apply 17.2% to131.02.02.02.09.4.3.3 Apply 17.2% to131.02.02.02.09.4.3.4 | ​The total number of uncosted hours necessary to assemble 152 APAs is 74,160 K hours. We assume that a maximum of 100% of the needed resources may be missing, and a most likely of 50%. Needed professional manpower is assumed to cost $95/hour. | 2 - Reasonable estimate | ​Institutions do not get base grants - cannot supply labor | ​Proactively contact US institutions and get their commitments. | ​Hire technicians & engineers to perform the work in place of the uncosted scientific resources |  | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 3833.3333 | 0 | 1916.7 | 0 | 2023-01-23 16:16 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-153 | LBNF / DUNE | [FD1-APA] winder construction takes longer than planned | If winder construction takes longer than planned, the schedule for APA production will be delayed, and additional labor for winder production will be needed. | Threat | Technical Risk |  | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  | ​End of winder fabrication or if additional winder is fabricated. | 50% | 0 (N) - negligible technical impact | 3-point - triangular | 50 | 150 | 300 | 3-point - triangular | 0.5 | 1.5 | 3 | 13122.02.A139432,434,436,438,440,442,444​ | ​The estimated time for the production of the additional winder is 10 months. We assume a maximum delay of 3 months and a most likely delay of 1.5 months, with a probability of 50%. There is an associated cost increase due to additional labor for winder production ( labor costs amount to about $0.3M for the production of 1 winder, including effort at Chicago and support from PSL). | 2 - Reasonable estimate | ​problems during set up of winders: delay in procuring parts needed to fabricate winder; insufficient manpower | ​Get commitments from the relevant institutions for the necessary resources for winder production, both for space and skilled manpower availability. Develop and execute a detailed plan to set up new winding machines at each production site. This plan will include contingencies in the event that technical problems cause schedule delays. | ​possibly find another vendor if parts are delayed; find labor resources |  | 4 (H) | 1 (L) | 1 (L) | 2 (Medium) | 166.6667 | 1.67 | 83.3 | 0.835 | 2023-01-31 10:09 | Mohammed Elrafih | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-154 | LBNF / DUNE | FD1 APA Loss of APAs due to an assembly-related accident | ​If a catatrophic accident happens during APA assembly, then an APA may be ruined. An example of an accident could be wire breakage or damage to geometry boards. The specifications allow for a few broken wires at the conclusion of each APA assembly. | Threat | Technical Risk |  | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​Once all APAs are installed | 30% | 0 (N) - negligible technical impact | 1-point - single value |  | 220 |  | 1-point - single value |  | 6 |  | 13122.02.A139258​ | The UK partners will build two spare APAs. There is both a cost impact (production of one additional APA) and a schedule delay (time needed to investigate the cause and fabricate the additional APA). | 3 - Solid estimate | Lack of attention during assembly/integration/installaion; procedures aren't followed | ​Define procedures to handle APAs at all stage of fabrication, integration and installation, together with associated engineering notes for all modes of handling. | ​Build additional APAs |  | 3 (M) | 1 (L) | 1 (L) | 1 (Low) | 220 | 6 | 66 | 1.8 | 2023-01-23 16:36 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-155 | LBNF / DUNE | One additional pre-production APA may be necessary | ​One pre-production APA from US will be necessary for the ProtoDUNE-II test. Several changes with respect to ProtoDUNE will need to be implemented. If the quality of the pre-production APA is not acceptable for the ProtoDUNE-II test, the production of one additional APA will be necessary. | Threat | Technical Risk |  | Alberto Marchionni | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | Fabrication & testing of pre-production APAs in coldbox at CERN | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 250 |  | 1-point - single value |  | 2 |  | ​13122.02.06.01.1421 | ​We assume a probability of 10%, impacting cost and schedule due the construction of one additional APA. | 3 - Solid estimate | ​Modification of winders does not work properly; problems with assembling new boards on new frame because dimensions are different | ​Provide enough time and manpower to implement winder modifications and update mechanical drawings for APA construction | ​​Fabricate additional pre-production APA |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 250 | 2 | 25 | 0.2 | 2022-08-10 08:31 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-201 | LBNF / DUNE | [FD-CE] FD1 and FD2 Cold Electronics ASIC(s) not meeting specifications | ​If the ASIC(s) do not meet the specifications another iteration of design may be required, which could then delay the integration of the Front-End Motherboards on the Anode Plane Assemblies and therefore the installation of FD1 and FD2. | Threat | Technical Risk |  | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2021-01-27 | 2023-04-19 | This risk will be closed after the final lifetime tests on all the ASICs have been performed, prior to the production readiness reviews for DUNE FD1 and FD2. This risk has already been partially realized when we found out that one more iteration of LArASIC (p5) and COLDATA (p4) was needed to fix minor design issues. After testing LArASIC p5 and ColdADC p2 meet all the requirements. The design differences between COLDATA p3 and p4 ​are so small that this risk is almost non-existant at this point. The only remaining uncertainty is related to the ongoing lifetime tests. These tests will be completed by the time of the production readiness review, and at that time the risk can be closed.​ | 5% | 1 (L) - somewhat substandard | 3-point - triangular | 450 | 600 | 800 | 3-point - triangular | 8 | 12 | 16 | Risk hook: 13122.2004.214.420 --> RT-131-FDC-FD-201 --> 13122.OBMS91710 | We assume that another cycle of design is required for one or more of the ASICs, with fabrication costs for the ASIC(s) prototypes of about $400k (redo ColdADC, and COLDATA)​. We then consider $250k of engineering for the ASIC redesign, $50k for making new FEMB prototypes, and $100k for repeating all the qualification tests. We assume a most likely delay of 1 year in the Production Readiness Review that serves to launch the preproduction of the ASICs and the FEMBs, with a minimum delay of 8 months and a maximum delay of 16 months. The low range corresponds to minimal design changes, the mid-range corresponds to significant COLDATA re-design, and the upper range corresponds to both ColdADC and COLDATA need to be re-designed. | 2 - Reasonable estimate | ​LArASIC, ColdADC, and COLDATA have essentially met the DUNE physics requirements. The final validation is the onging lifetime measurements. This risk can be realized only if issues are found during the measurement of the expected lifetime in liquid Argon of the three ASICs. These measurements will be completed prior to the production readiness review for the ASICs. No problems are expected in the lifetime measurements because the three ASICs have been designed taking into account the requirements of DUNE (very small number of ASIC failure in liquid Argon over the 20-30 years lifetime of the experiment). If problems are observed new submissions and new engineering runs will be required. This would require another iteration in the design. This risk covers also the possibility that a fabrication process becomes unavailable at a foundry. | ​The only remaining ASIC requirement that needs to be verified is that the chips meet the DUNE lifetime requirements. Here the risk mitigation is based on the use of appropriate design rules that were developed at the transistor level. The real remaining risk is that the design rules have not been followed correctly during the ASIC development, and this risk is significantly reduced by the use of appropriate libraries during the design.​ | ​If the risk is realized we can increase the float in the schedule by compressing the schedule for testing the ASICs and the FEMBs which would allow us to recuperate some schedule delays.. This may require increasing the testing throughput by operating more shifts per day, which would require additional personpower. |  | 1 (VL) | 1 (L) | 3 (H) | 2 (Medium) | 616.6667 | 12 | 30.8 | 0.6 | 2023-12-12 07:51 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-024 | LBNF / DUNE | [PM] FS long-term housing unavailable | If LBNF/DUNE-US cannot secure economical long-term housing for the installation team, then more expensive hotels will need to be used for extended periods.​ | Threat | External Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-04-01 | 2028-07-01 | economical ​long-term housing secured. | 50% | 0 (N) - negligible technical impact | 2-point - flat range | 2200 |  | 5000 | 1-point - single value |  | 0 |  | Risk hook: 13141.A2580MS --> RT-131-FDC-PM-024 --> 13141.A3340​ | ​​Cost estimate is based on the differential between estimates for shared housing ($600/mo per person) versus hotel ($3000/mo per person; average $100/day GSA per diem). FD1 and FD2 CAM has prepared travel estimates to support installation teams based on the shared housing costs. Note this is not applicable to all of FDC as I&I and Cryogenics estimates are based on hotel stays. | 1 - Rough guess |  | ​Engage with Fermilab Travel Office on long-term housing options. Engage with Fermilab Procurement to explore lease options for long-term housing. | Revert to using hotels for long-term stays​ |  | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 3600 | 0 | 1800 | 0 | 2024-01-13 12:41 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-204 | LBNF / DUNE | Cables for the cold electronics cannot be routed through the APA frames | ​If the cables used to provide power, control, and clock and to readout the FEMBs mounted on the lower APA cannot be routed through the APA frames, then a different solution involving routing the cables outside the field cage needs to be implemented, which could result in a delay of the beginning of the construction and possibly a reduction of the sensitive volume of the detector. | Threat | Technical Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2018-07-01 | 2020-06-30 | ​This risk can be closed once we have demonstrated that we have a design for the cable plant that is compatible with routing the cables for the CE boxes of the lower APA through the frames of the APAs, and this design is tested with actual prototypes of the cables. | 5% | 1 (L) - somewhat substandard | 1-point - single value |  | 1850 |  | 1-point - single value |  | 8 |  | ​13122.2004.114.240 (Engineering design review for the cable routing inside the cryostat, that triggers the purchase of the cold cables) | ​The cost impact is estimated as follows: if the cables need to be longer (up to 35m) we may need one more iteration in the design of COLDATA, to reoptimize the line drivers, which we estimate at $350k. We also need longer cables (i.e. replace the 22m length cables with 35 long cables), and based on the quotes we estimate the cost at $1,100k. Finally the field cage and the cable supports will need to be redesigned, for which we estimate 2 FTE years of engineering at at cost of $400k. The time delay is caused on one hand by the amount of time required to design a new routing solution and study all its impact on the various detector system and on one hand by the need of redesigning COLDATA. | - Not yet defined - | ​This risk is realized if the integration tests at Ash River fail to demonstrate that we can route all the cables for the lower APA through the APA frames. | ​Several risk mitigations have already been put in place. The size of the tubes used for the construction of the APA frames has been increased to 4"x4" to ensure that cable bundles with the appropriate number of conductors can be routed through the frames. Simple insertion tests have already been performed and more complicated ones are being prepared. The size of the cable plant required for DUNE has already been reduced compared to that used in ProtoDUNE. Additional tests of the cable properties in cold are planned, and the design of ASICs is being changed to increase the number of ways in which the size of the cable plant can be reduced. | ​Depending on when the risk is realized we may decide to reschedule the ASIC submissions to avoid the need for an additional iteration of ASIC design. The only way to reduce the delay in the beginning of the construction is to provide additional engineering resources to speed up the redesign of the detector.​ |  | 1 (VL) | 2 (M) | 2 (M) | 1 (Low) | 1850 | 8 | 92.5 | 0.4 | 2022-08-10 08:32 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-205 | LBNF / DUNE | [FD-CE] Delay or damage to TPC electronics components on top of FD1 and FD2 cryostats | ​If the TPC electronics components to be installed on top of the cryostat (cryostat penetrations with their spool pieces, warm interface electronics crates with their board, power and bias voltage supplies with the warm cables, and other ancillary services) are delayed or are damaged after installation, then the entire installation schedule may be delayed, with a consequent delay in the start of the detector commissioning and physics operations. | Threat | Technical Risk |  | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2024-04-01 | 2029-11-30 | ​This risk will be closed once the installation of the second far detector module has been completed and the FD1 and FD2 cryostats have been sealed. At that time part of the risk will become an operation risk. | 5% | 0 (N) - negligible technical impact | 2-point - flat range | 180 |  | 530 | 2-point - flat range | 0.5 |  | 2 | Risk hook: 13141.A1280 --> RT-131-FDC-FD-205 --> 13141.A1290 ​ ​ | ​There are multiple ways this risk can be realized. If for example the cryostat penetrations are late, then the cryostat cannot be sealed (or a different way of sealing needs to be devised) and the whole installation is delayed. If one cryostat penetration is damaged after installation, it has to be replaced. Similarly if any other components is late or damaged, the installation process will be extended. We estimate the cost impact under the assumption that extra parts for one row of APAs have to be purchased ($150k) and that extra labor will be necessary for the amount of time corresponding to the delay in the installation ($200k). We then assume +/-50% for the cost/time range and a delay of 2 months. We assume the cost estimate applies to both FD1 and FD2. | 1 - Rough guess | ​This risk is realized if the number of spares of cryostat penetrations, WIECs, WIBs, PTCs, power and bias voltage supplies are insufficient to address problems during the installation, or if there are delays in the availabily of components. There can be multiple reasons for this, including low yield during fabrication and testing, losses during shiments to the far site, problems with handling of detector parts during integration and installation. | ​The schedule is the main mitigating action against delays. The components on the top of the cryostat can and should be procured as early as possible and stocked at the South Dakota Warehouse Facility. Sufficient testing should demonstrate that they meet the specifications. Early installation of the cryostat penetrations and of the WIECs, and early connection of the WIECs to the DAQ, followed by testing, will help ensuring that there are no problems. Careful planning of spares and monitoring of their usage will also help reducing the probability that we realize late in the game that there are problems. ESD protection will help against damage of the WIECs, and supplies. | ​If the cryostat penetrations are installed late, we could close the cryostat with temporary and standard flanges and proceed with the installation, but after a few months we would need the cryostat penetrations. If the WIECs/WIBs/PTCs are late we can proceed with the installation, but we would be slowed down by the need of moving the crates around as we progress testing. Similarly for power supplies. |  | 1 (VL) | 1 (L) | 0 (N) | 1 (Low) | 355 | 1.25 | 17.8 | 0.0625 | 2023-12-12 07:51 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-202 | LBNF / DUNE | [FD1-CE] Delay in the availability of ASICs and FEMBs | ​If the ASICs or the FEMBs production and testing are delayed for reasons other than design issues then the FEMBs may not be available in time for integration with the APAs possibly delaying the installation of the detector and the beginning of physics operations. | Threat | Management Risk |  | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2023-04-12 | 2025-12-26 | ​This risk can be closed when all the FEMBs have been integrated on the APAs for the first Single Phase Far Detector Module. | 10% | 0 (N) - negligible technical impact | 3-point - triangular | 700 | 750 | 800 | 2-point - flat range | 2 |  | 6 | ​13122.2004.132.420 (FEMB production, second 20%) | ​The estimate is obtained assuming that an extra batch of ASIC wafers are needed ($300k in the case of the 3 ASIC solution, $200k in the case of the CRYO solution), that a significant number of FEMBs needs to be fabricated/populated (20% of the FEMB production, equivalent to $400k), and then adding an estimate of the costed labor for testing, $100k. | 2 - Reasonable estimate | ​There can be multiple triggers for this risk: delays in the fabrication caused by the problems with the ASIC industry, a lower fabrication yield than expected for ASICs and FEMBs, significant downtimes at one of the quality control sites, losses during handling and transportation, custom issues. This risk assumes that all the spares planned for production have been used and extra spares are needed. | We already have multiple risk mitigation actions in place. For items with long lead-times (the ASICs, discrete components on the FEMBs that are hard to procure) we are assuming that the number of spares has to be larger than what is actually planned from the installation point of view (we are planning for example for 10% spare FEMBs for the first detector, and 5% spare FEMBs for the second detector, and we are assuming 85% yield for the ASICs, but given how ASIC purchases are done we are could also live with a 70% yield on the ASICs). We are planning to request CD-3a authorization for the purchase of the ASICs and of the FEMB components. We are splitting the quality control process between various sites, such that a failure in one of them does not entail a complete stop to the production. We are implementing training and strict procedures to avoid ESD damage. We will be monitoring the use of spare components and if needed fabricate additional parts. We are also assuming that we are building two Single Phase Far Detector modules for DUNE, and we can use the ASICs and the FEMBs planned for the first detector to ensure that the first one is completed in time (for this reason this risk really affects the second detector more than the first one).​ We have very little protection against the problems that are affecting the ASIC industry and that started toward the end of 2020 (lack of production capacity). The only defense against this is to try to start the production as early as possible. | ​Corrective actions can be taken early in the process already at the stage of testing ASICs or FEMBs if we notice that there are yield issues. If the problems are caused by poor handling during testing or by shipping problems additional corrective actions can be put in place. Another (automatic) corrective action is to use for the first Single Phase Far Detector module the ASICs and FEMBs that are originally targeted for the second module, and increase the number of ASICs and FEMBs that are built for that. |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 750 | 4 | 75 | 0.4 | 2023-01-31 11:15 | Mohammed Elrafih | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-206 | LBNF / DUNE | [FD1-CE] Incompatibilities with detector components provided by other consortia | ​If there are incompatibilities of the TPC electronics with other detector components that are discovered after first prototypes are fabricated, or later during integration at SURF, installation and commissioning, then some redesign or rework of components may be required, which will may cause a delay in the installation of the detector and the beginning of physics operations. | Threat | Technical Risk |  | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2019-07-01 | 2026-11-25 | ​This risk will be closed once a significant fraction of the first Single Phase Far Detector module has been installed and tested. | 5% | 0 (N) - negligible technical impact | 3-point - triangular | 50 | 200 | 1000 | 3-point - triangular | 1 | 2 | 6 | Risk hook: FD1: 13141.A1230 --> RT-131-FDC-FD-206 --> 13141.A.1240​ | ​We estimate that both the cost and schedule impacts will have a triangular probability distribution, with a peak fairly close to the minimum, and a relatively large tail. The actual values are engineering expert estimates. This risk covers a lot of possible incompatibility failures, and some of them have a minimal impact. In the long term the only major risk is that either software or firmware need to be adapted. The upper limit corresponds to two/three FTEs working full time for a long period of time. | 1 - Rough guess | This risk is realized if at any point during the prototyping, the integration, or the installation an incompatibility is observed between the TPC electronics components and the components provided by other consortia. This can be caused by not adequately defined or identified interfaces between the detector components provided by the TPC electronics consortium and other consortia.The probability of the risk decreases with time (which can be accomplished by re-evaluating the probability as time evolves), and should become zero after 20% of the detector has been integrated, installed and tested. The cost and schedule impact will increase with time even if the probability decreases. | There are several levels of risk mitigation. The first line of defense is the proper design of interfaces and extensive prototyping. During this phase it is almost inevitable that this risk will be realized, but the impact will be minimal. After the first round of prototyping it should be expected that the probability of this risk will be minimized. Further prototyping and integration tests will help reducing the probability of this risk taking place. Integration tests include mockups of the APA head tubes, of cable routing, of cable insertion through the cryostat, the 2nd run of ProtoDUNE, system tests with the photon detector and with the DAQ. ​ | ​If this risk takes place during the prototyping phase (where we actually expect it to happen as part of the design process), the risk response is to modify the design and refabricate the prototype. If the risk takes place very late during integration and installation of the detector, hopefully we are at the stage where minimal rework of components is required, instead of design and refabrication. |  | 1 (VL) | 1 (L) | 1 (L) | 1 (Low) | 416.6667 | 3 | 20.8 | 0.15 | 2023-12-12 07:51 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-026 | LBNF / DUNE | [PM] US reinstates duties on steel imports from Europe | ​If the duties on imported steel is reinstated, then the Project will have to pay duties to the US Department of Commerce for the cryostat steel & fasteners, in-kind contributions from CERN​. | Threat | External Risk | YES | Michael D Pfaff | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-10-01 | 2026-10-01 | ​​all cryostat steel is delivered to the Far Site laydown yard | 50% | 0 (N) - negligible technical impact | 2-point - flat range | 1747 |  | 3494 | 1-point - single value |  | 0 |  | Risk hook: 13141.A80070 --> RT-131-FDC-PM-026 --> 13141.A80080 | ​Estimates are detailed in dunedocdb1339 based on material lists from LBNF/DUNE project team. Cryostat import estimate market value is $14m, including high-strength steel, carbon steel & steel fasteners (bolts, etc). 25% duty = $3,493,666. HTS Codes = 7203 - 7229 and 7218-7222. Duty rates can change at any time, based on US policy, by country and import item. When these dutieswere active, these costs were included in the FDC direct costs. These steel duties were removed in 2022, due to the removal of these duties. | 2 - Reasonable estimate | ​Change in ​​policy regarding steel imports/tariffs​ | The Project is supporting DOE OHEP and OMB to obtain a HTS code for LBNF/DUNE. The Project and Fermilab are also following the example of SBN to use ITA-338P (Request for Duty-free entry of scientific instruments or apparatus) documentation for all IKC. Use HTS: 8543.90.8845 Parts of Particle Accelerators Guidance provided by FNAL import/export control manager | ​ |  | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 2620.5 | 0 | 1310.3 | 0 | 2024-01-13 12:31 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-162 | LBNF / DUNE -- Operations | Argon filter media different than Cu-0226S less performant | ​​If an alternative media is selected for the Argon purification then that media might be less performant in removing contaminants and the detector may be affected. | Threat | Technical Risk | NO | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Proposed | 1 - draft |  |  | ​Satisfactory verification of performance of alternative media being considered and verification in actual experiment (ProtoDUNE?) whose performance is known with current media (Cu-0226S). Use current media (Cu-0226S and mol sieve), whose performance is known and proven. | 10% | 2 (M) - significantly substandard | 2-point - flat range |  | 0 |  | 2-point - flat range | 12 |  | 15 |  | If the verification of performance is completed after the completion of installation and before the equipment is shipped, there is only a potential schedule delay associated with replacing the media with the right one, assuming that the partner bears the cost of purchasing new media. Current manufaturing times for the current media (Cu-0226S) from industrial supplier (BASF). | 2 - Reasonable estimate | ​Unicamp is testing alternate media that they can manufacture in Brazil and may potentially have higher absorption capacity, therefore reducing amount needed. | ​Measure the performance of the media being considered to ensure it is satisfactory. If so, then test the media in a larger facility (ProtoDUNE) to verify no effect on performance of actual Detector. QA documentation of batches being delivered, if not an industrial supplier or known supplier (E.g. BASF). Verification of performance at vendor's site (industry or University). Use the current media (Cu-0226S), whose performance is confirmed and verified. |  |  | 2 (L) | 0 (N) | 3 (H) | 2 (Medium) | 0 | 13.5 | 0 | 1.35 | 2021-11-19 13:44 | Marco Verzocchi | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-208 | LBNF / DUNE | [PM] Insufficient personnel for QC activities during the detector construction | ​If any of the FD1 or FD2 cannot identify all the resources required to perform the quality control tasks during the detector construction, there could be a delay in the delivery of the components to SURF, and as a consequence, in the integration, installation and commissioning of the detector. | Threat | Management Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2019-07-01 | 2026-09-30 | ​This risk can be closed only after all the detector components for the first Single Phase Far Detector module have gone through the entire quality control process. | 30% | 0 (N) - negligible technical impact | 2-point - flat range | 75 |  | 150 | 1-point - single value |  | 0 |  | Risk hook: 13141.A8360 --> RT-131-FDC-PM-208 --> 13141.A1210 and 13141.A8390 (need two successors) ​ | The assumption is made that one of the institutions responsible for the QC activities in the US on APAs, TPC Electronics, HV, photon detectors cannot continue its work due to the lack of support from the research program. Some expenses are assumed to be necessary to transfer the responsibility for the QC process to another institution, but it is also assumed that there is no schedule delay, as usually there is sufficient warning prior the termination of a research grant. | 2 - Reasonable estimate | ​During the construction the problem could be caused by the non-availability of personnel to perform QC tasks, slowing them down. This can happen either because the research grant of one group is not renewed, or because that group fails to identify the personnel required to carry out the QC tasks. | ​The plans of some of the consortiua already include risk mitigations for this specific risk. The distributed nature of the testing activities automatically protects us against some of the triggers, since the testing can be moved from one site to another. Careful planning is the other handle against this risk, and plans are being put in place in the long term, including memoranda of understanding with the groups that intend to participate in the consortium activities. | ​Depending on how the risk is realized, the testing activities will be moved to a different instituion or delayed. |  | 3 (M) | 0 (N) | 0 (N) | 0 (Negligible) | 112.5 | 0 | 33.8 | 0 | 2023-12-12 07:51 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-167 | LBNF / DUNE | [CRYO] CD-3 approval delayed | ​If CD-3 approval is delayed beyond current start of manufacturing (Jan-2024), THEN the installation and commissioning of the Nitrogen System will be delayed. | Threat | Management Risk | NO | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-01-01 |  | ​CD-3 approval for Far Site Cryogenics. | 25% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | 2067 | 4241 | 3-point - triangular | 0 | 3 | 6 | Risk hook: 131123.02.03.1663MS --> RT-131-FDC-CR-167 --> 131123.02.03.28 | ​A delay in CD-3 approval beyond current start of manufacturing (Jan-2024) will delay the Notice To Proceed for manufacturing of the Nitrogen System. There currently are only 3 months of float in the Nitrogen System subcontract. Anything beyond that will impact the project critical path. A 3 mo delay could potentially increase the cost of manufacturing by ~2.32% (= $2,066,973). A 6 mo delay could potentially increase the cost of manufacturing by ~4.76% (= $4,240,858). Values are calculated assuming the agreed upon indices to escalate the cost of manufacturing, with respect to the base year. Maximum values based on caps to indices. Actual values will be calculated based on corresponding indices at the time the delay is realized. | 3 - Solid estimate | ​CD-3 approval takes longer than anticipated and goes byone current start of manufacturing (Jan-2024). Policital appointees and/or people with proper authorization not in place in the new Administration. Project delays in readiness for FDC CD-2/3 Review. | ​Monitor performance of the subcontractor to identify possible schedule saving opportunities in the activities following CD-3 approval (manufacturing, installation and commissioning). Negotiate lower values for escalation indeces based on situation at the time of delay. |  | Cost Impact | 3 (M) | 2 (M) | 1 (L) | 2 (Medium) | 2102.6667 | 3 | 525.7 | 0.75 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-213 | LBNF / DUNE | [FD1-CE] Loss of key personnel for the TPC electronics consortium during the design phase | If ​some critical member of the TPC electronics consortium suddenly leaves the project, there could be a schedule delay while their replacement is identified / trained, which would cause a delay in the activities of the consortium. | Threat | Management Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved | 2019-09-01 | 2021-09-30 | This risk can be closed only when the design of the detector is completed. | 5% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 300 | 2-point - flat range | 2 |  | 4 | ​13122.2004.114.160 (production readiness review) | We assume that the most critical losses of personnel will take place during the R&D and prototyping phase, were the loss of one or more engineers / technicians with significant expertise from the construction and commissioning of ProtoDUNE will have the largest impact. We also assume that at later stages the loss of engineers / technicians will have a negligible impact because the knowledge of the detector design and construction will be spread among a larger team. We assume a cost impact that is distributed flat between 0 and $300k (which is close to 1 FTE-year of engineering or 2 FTE-years of technicians) and a delay that has a flat distribution between 2 and 4 months. These are rough guesses based on the need for the new personnel to get on board with their respective part of the project. These numbers are not large, and this is based in part on the fact that the knowledge of the detector construction has been significantly spread around compared to ProtoDUNE. This risk covers only the loss of personnel in the TPC electronics management team and some critical engineer/technicians. Loss of scientific personnel is covered in RT-131-FD-208 (for testing activities) and in RT-131-FD-214 (for integration and installation activities).​ | 1 - Rough guess | This risk will be realized if a critical engineer and technician with exclusive knowledge from ProtoDUNE stops working on the design of the DUNE detector and has to be replaced. For ASICs this is not a risk, because the knowledge has already been shared between multiple design groups. This remains a risk for the design of FEMBs, WIBs, PTCs and for the mechanical components, although for the latter we note that the sharing of design and the involvement of Kyle Zeug at PSL has already reduced significantly the probability of the risk. | ​The main way to mitigate the risk is to share the designs and train new personnel, and where necessary put in place succession plans. For the ASIC we can almost claim that the risk no longer exists (since we have multiple designs available). For FEMBs this is till a risk, although we do not think that this is a major one. The risk continues to be sizeable in the area of WIBs and PTCs where plans are being put in place to get more groups involved in the board design and in the firmware development. For the mechanical components that are a responsibility of the TPC electronics consortium the design is being done almost exclusively by one engineer at BNL, but the designs are now shared regularly with Technical Coordination and are well known by at least another engineer at BNL and another one at PSL. A deputy L2 manager has been identified and will be trained to possibly succeed the current L2 manager if needed. | If the risk is realized the relevant engineer(s) and technician(s) need to be replaced as quickly as possible. It would be preferable to do this with personnel from the same institutions such that (if needed) information can be transferred easily. |  | 1 (VL) | 1 (L) | 1 (L) | 1 (Low) | 150 | 3 | 7.5 | 0.15 | 2023-08-16 01:36 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-214 | LBNF / DUNE | [FD1-CE] Insufficient personnel for the TPC electronics installation activities at SURF | If some of the scientific personnel for the TPC electronics integration and installation work at SURF is not available, it will have to be replaced by additional personnel (technicians) supported by the project, thereby increasing the total cost of the integration and installation activities, that would otherwise be significantly delayed. A delay of the installation is also possible, which would affect the completion date for the project. | Threat | External Risk |  | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2014-08-01 | 2027-12-31 | ​This risk can be closed only upon completion of the installation of the first Single Phase Far Detector module. | 30% | 0 (N) - negligible technical impact | 2-point - flat range | 450 |  | 1050 | 2-point - flat range | 0 |  | 2 | Risk hook: 13141.A1210 --> RT-131-FDC-FD-214 --> 13141.A1220​​ | ​The integration and installation activities of the TPC electronics consortium at SURF require 9 FTE of engineers and technicians that are supported by the project, plus 21 FTE of scientific personnel that is supported by the research grants of their institution (universities and national laboratories) for each detector module.​ The estimate for the risk cost is obtained assuming that between 10% and 30% of the 21 FTE of scientific personnel required to integrate and install each Single Phase Far Detector module need to be replaced by paid technicians, assuming a rate of $150k / FTE-year. We also assume that there will be a small delay for the first detector module, corresponding to the time required to hire and train the new technicians (ideally this could be zero, as long as the risk is realized at least 6 months ahead of the beginning of the integration and installation activities at SURF). This risk covers also the possibility that additional personnel may be required for the ~3 month period where the installation activities of FD1 and FD2 overlap. For this reason we add the 4 FTEs for 3 months (ie. another $150k of cost impact). It should be noted that this risk does not cover similar problems that may take place during the design and construction phases. Those are covered by risks RT-131-FD-208 (insufficient personnel during QC testing) and RT-131-FD-213 (loss of key personnel during R&D and prototyping). | 2 - Reasonable estimate | ​This risk will be realized if some the TPC electronics consortium institutions that have promised to participate in the integration and installation activities cannot send their personnel to SURF, either because their research grant has not been renewed or because they could not identify the personnel that would move to South Dakota. | Some risk mitigations have already been put in place by increasing the amount of technicians participating in the integration and installation activities after a first round of discussion with the institutions participating in the TPC electronics consortium. We will continue to try to enlarge the TPC electronics consortium to ensure that there will be sufficient scientific personnel for all the activities planned for SURF.​ | If the risk is realized we will first try to identify additional scientific personnel within the DUNE Collaboration that may be interested in participating in the integration and installation activities. If that fails we will then proceed to hire and train technicians that will be doing the work originally planned for scientific personnel​ |  | 3 (M) | 2 (M) | 0 (N) | 2 (Medium) | 750 | 1 | 225 | 0.3 | 2023-12-12 07:51 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-216 | LBNF / DUNE | [FD1] FD2 Non-US Workers Work Permit Delays - Detector | If workers from outside the U.S. are not able to get and maintain work permits, then progress on non-DOE partner contributions such as the Far Detector could be delayed. | Threat | External Risk |  | Janet E. Bishop | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved | 2022-06-30 | 2030-12-31 | ​end of project | 25% | 0 (N) - negligible technical impact | 2-point - flat range | 50 |  | 250 | 1-point - single value |  |  |  | 13141.A2580MS (T5 MS - Cryostat #1 Ready for FD1 Installation) (50% of the risk) 13143.A2580MS10 (T5 MS - Cryostat #2 Ready for FD2 Installation) (other 50%)​​​ | 1 Technician = 50k for 6 months. Cost impact is based on 1-5 Techs needed if non-US workers cannot work on US soil. Foreign nationals entering the US can stay for 90 days without a visa if they are fromspecific countries identified by the U.S. Dept of Stateand meet specific requirements. Fermilab works with a J-1 visa type. Workers may not be able to be brought in by partners in a timely manner. Also, if the work takes longer than expected, the visa may not be able to be extended. Estimate there's ~ 50% chance something will go wrong with a visa that will most likely take a month to straighten out. (This occurred on the 35t prototype during IHI construction with Japanese workers.) | 1 - Rough guess | ​Foreign nationals are not able to get visas to work in the US or be part of the visa waiver program in the timeframe necessary to meet the project schedule. | Fermilab is hiring legal support to better understand and plan for non-US workers. DUNE-US PM is working with the HLWG subgroup on Export/Import/Tarrifs thinking about this issue related to number of workers and timing. providing more specific info sooner will be more helpful to resolve the issue. Project management will work with nonDOE partners to assist with any visa issues and verify planning as early as possible. | ​Wait for workers to arrive. |  | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 150 | 0 | 37.5 | 0 | 2023-12-12 07:51 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-171 | LBNF / DUNE | [CRYO] No chiller redundancy during Far Detector #2 filling | ​If the chiller is unavailable during FD#2 filling then the filling will have to stop until the chiller is brought back online | Threat | External Risk | NO | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2029-06-01 |  | ​Completion of the fill of cryostat #2. | 30% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 0.1 | 0.25 | 0.5 | Risk hook: 131123.04.02.75MS --> RT-131-FDC-CR-171 --> 131123.03.40 ​ | No cost impact to the project (covered by operations). Schedule impact is the time taken to bring the chiller back on line. See email from Josh Willhite for details. | 2 - Reasonable estimate | ​If one of the chillers fails, we don't have enough capacity to operate the first cryostat and fill the second one at the same time. The filling will stop and resume once the chiller has been repaired. | ​Regular maintenance of the chillers. Minimize the cooling to other part of the facility. | ​Place a contract for the repair of the chiller | https://edms.cern.ch/document/2822921 | 3 (M) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0.28 | 0 | 0.084 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RU-131-FDC-PM-005 | LBNF / DUNE | [PM] Changes to the Estimate of Duties for Imports | ​If the Project has made an error in its estimate of duties for FS imported deliverables (DOE purchases or IKC), then the Project will have to pay less/additional tariffs to the US Department of Commerce​ | Uncertainty | External Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2025-06-01 | 2027-09-30 | ​​All FS shipments complete for LBNF/DUNE | 100% | 0 (N) - negligible technical impact | 3-point - triangular | -200 | 500 | 1500 | 1-point - single value |  | 0 |  | Risk hook: 13141.04.02.36MS --> RU-131-FDC-PM-005 --> 131123.02.04.70MS | ​Estimates are detailed in dunedocdb1339 based on April 2021 material lists from LBNF/DUNE project team. FS estimates (cryo & detector total ~$1.5m) Duties can be up to 25% of the market value. For the Far Site, this would impact detector components and cryogenic purchases and IKC, with a range of 4% to 25% for various commodities and countries. Duty rates can change at any time, based on US policy, by country and import item. | 1 - Rough guess |  | ​​The Project is supporting DOE OHEP and OMB to obtain a HTS code for LBNF/DUNE. The Project and Fermilab are also following the example of SBN to use ITA-338P (Request for Duty-free entry of scientific instruments or apparatus) documentation for all IKC. Leveraging FNAL's import/export control manager​​​​ |  |  | 5 (VH) | 2 (M) | 0 (N) | 3 (High) | 600 | 0 | 600 | 0 | 2024-01-13 12:40 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RU-131-FDC-PM-103 | LBNF / DUNE | [PM] Partner Insurance at SURF | ​If there is not a wrap-up or other comprehensive solution to insurance for LBNF/DUNE partners working at SURF, then LBNF/DUNE partners working at SURF will have to obtain and provide evidence of insurance coverage meeting the SDSTA Risk Transfer Protocols, and FRA will have to administer evidence of insurance coverage to ensure compliance. ​ BCR FDC_1016 added $4.6M into the plan for insurance costs. This uncertainty covers the range of costs this insurance may incur. | Uncertainty | External Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-07-01 | 2027-12-31 | Placing insurance. | 100% | 0 (N) - negligible technical impact | 3-point - triangular | -200 | 1500 | 3000 | 3-point - triangular | 0 | 0.25 | 1 | Risk hook: 13122.OBMS92750 --> RU-131-FDC-PM-103 --> 13141.A450001 | $4.6M is included in the plan based on a budgetary quote received in August 2022. This uncertainty estimate is based off of that considering uncertainty in the market, with costs anticipated to be higher. $4.6M quote is based on optimized schedule. Longer work requires additional insurance. | 2 - Reasonable estimate | ​ | We have asked Aon for an updated estimate from Aon and will be able to tighten this uncertainty in that event. After the policy is in place, we will be able to retire this uncertainty. | ​Pay the insurance as needed. | BCR FDC_1016 | 5 (VH) | 2 (M) | 0 (N) | 3 (High) | 1433.3333 | 0.42 | 1433.3 | 0.42 | 2024-01-13 12:45 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-154 | LBNF / DUNE | [CRYO] Nitrogen System completion is delayed | If the delivery of the Nitrogen System by the selected vendor is delayed and/or the installation/commissioning takes longer than planned, then the installation of the detector will be delayed. Since the installation of the detector is on the critical path, the start of the filling of detector #1 will be delayed as well. | Threat | External Risk | YES | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-03-01 |  | Completion of commissioning of equipment for Detectors #1 and #2 at SURF. | 40% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 0 | 1 | 4 | Risk hook: 13122.OBMS92440 --> RT-131-FDC-CR-154 --> 131123.04.04.02.95​ | ​Refrigeration systems for SNS, SLAC and FRIB were delayed upon delivery and caused significant challenges to the projects. The schedule include industry feedback for the duration of manufacturing and installation. However the installation underground at SURF poses unique challenges and may cause delays for sub-optimal conditions. The equipment is required to be delivered to SURF 3 mo in advance of the beginning of the installation to absorb potential delays in the manufacturing. A delay greater than 4 mo seems highly unlikely at this time with 4 weeks the most likely expected delay. No direct cost impact. | 2 - Reasonable estimate | ​Delivery in supply of materials to vendor. Competing projects for vendor. Unforeseen circumstances. Non-optimal site conditions for installation work. | ​Closely monitor the performance of the contract. Look for opportunities to shorten the delivery schedule. Production review meetings. Payment based on completion of milestones. Look for oppoprtunities to shorten the installation and commissioning schedule. Require that the equipment be delivered to SURF 3 mo in advance of the beginning of installation. Subcontract includes Liquidated Damages clause. From section H.13 of the Subcontract: "...The provision establishes liquidated damages at a rate of 0.5% of the contract value, per week of delay. Cumulative liquidated damages are capped at 10% of the contract value. …". |  |  | 4 (H) | 0 (N) | 1 (L) | 2 (Medium) | 0 | 1.67 | 0 | 0.668 | 2024-01-13 12:50 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-177 | LBNF / DUNE | [CRYO] PLC equipment procurement is delayed | ​If supply chain issues continue through the next year, Siemens PLC equipment delivery will be delayed. | Threat | External Risk | NO | Ian L. Young | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-02-01 | 2024-06-24 | ​Delivery of PLC equipment to FNAL | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 1 | 2 | 3 | Risk hook: 131123.02.03.6939 --> RT-131-FDC-CR-177 --> 131123.02.03.6801 | PLC manufacturers have been dealing with supply chain issues since COVID-19, but the delays have been steadily declining since 2020. Estimate is based on previous quotations and delivery times between 2020 and present, where 6 months was the longest seen delay in a PO placed with Siemens, implying an impact of 2 months (above the 4 months already in the plan). Error bar on top of this is +/- 1 month. | 2 - Reasonable estimate | Manufacturer supply chain delays​ | ​​Have engaged with Siemens frequently to assess their delivery schedule. |  |  | 4 (H) | 0 (N) | 1 (L) | 2 (Medium) | 0 | 2 | 0 | 1 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-140 | LBNF / DUNE | [FD1-APA] Poor quality of frames or inaccuracy in hole/slot machining | ​The APA frame is constructed from structural stainless steel. The quality of beams and tubings provided by the vendor may change with time and be outside the required tolerances. Problems with QA during machining of holes and slots may result in unusable products. If this happens, it may delay the supply of frames of sufficient quality and it would delay the APA construction schedule. | Threat | External Risk | NO | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-01-01 | 2027-06-30 | ​End of APA frame construction. | 10% | 1 (L) - somewhat substandard | 1-point - single value |  | 0 |  | 2-point - flat range | 2 |  | 4 | Risk hook: 13122.D2283 --> RT-131-FDC-FD-140 --> 13122.D2284 | Schedule delay is time it takes to identify a new vendor and be included in their production schedule. | 2 - Reasonable estimate | ​Problems with fabrication procedures (including the possibility that these are not followed by the vendor's personnel) | ​All requirements must be clearly specified in the purchase contracts. We will establish a well managed relationship with a vendor to provide the stainless steel tubing and the machining for the components of an APA frame. In addition, through our prototyping efforts we will seek out at least one solid backup vendor for material supply and machining. | ​When problematic frames are identified, these need to be either remachined or sent back to the vendor, and replaced which causes a delay |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 3 | 0 | 0.3 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-146 | LBNF / DUNE | [FD-CE] Cost increases in components originating from non-US vendors due to customs duties | If the "trade war(s)" between the US and other countries escalates, additional dutie could be applied to goods that are purchased in the US but are actually fabricated outside of the US and then imported, resulting in a cost increase. | Threat | Management Risk | NO | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2019-09-01 | 2025-12-31 | This risk can be closed only when all the detector parts that originate from other countries have been procured. Depending on the timeline this means the completion of the purchase of discrete components and printed circuit boards for the FEMBs, the WIBs, and the PTCs, of cold cables, and of power supplies. | 15% | 0 (N) - negligible technical impact | 3-point - triangular | 320 | 2000 | 2500 | 1-point - single value |  | 0 |  | Risk hook: 13122.2004.133.330 --> RT-131-FDC-FD-146 --> 13122.2004.133.390 | There are a lot of components (the cables and the power supplies being the most expensive, but this is a problem that affects also printed circuit boards and discrete components for the FEMBs, the WIBs, and the PTCs) that originate from other countries, despite the fact that they are being purchased from US vendors. If additional custom tariffs are applied on these products, it is assumed that the custom tariffs will be reflected in a cost increase for the parts that are required for the construction of the DUNE detector. About $12.5M of the total M&S expenses (FD1 $6.9M, FD2 $5.6M) are for parts that are likely to originate from countries to which the past administration was planning to apply significant custom tariffs. These parts are printed circuit boards and components for the FEMBs, the WIBs, and the PTCs (mostly China), cold cables, and power supplies (Germany). The cost estimate is done assuming that the entire amount of the tariffs (assumed to be 20%) is transferred from the vendor to the purchaser (i.e. the DUNE project). There is no schedule impact associated to this risk. The low end of the cost impact corresponds to power supply only, the upper range corresponds to all components, and the mid-range corresponds to all components minus the power supply. | 2 - Reasonable estimate | ​Completely outside our control. International politics. | We may try to find for some of the components (printed circuits are the most likely) a US vendor, but this is very unlikely, as these types of markets (printed circuit boards, components) rely mostly on non-US vendors. | ​​If the risk is realized we can increase the float in the schedule by compressing the schedule for testing the ASICs and the FEMBs which would allow us to recuperate some schedule delays.. This may require increasing the testing throughput by operating more shifts per day, which would require additional personpower.​ |  | 2 (L) | 2 (M) | 0 (N) | 2 (Medium) | 1606.6667 | 0 | 241 | 0 | 2023-12-12 07:52 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-151 | LBNF / DUNE | [FD1-APA] production quality does not meet requirements | If wire planes are outside the required tolerances, they will need to be reworked and the APA production schedule will be affected.​ A point of concern is to stay within limits for the tension of the wires. | Threat | Technical Risk | NO | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-06-01 | 2026-12-31 | ​Once all APAs are manufactured. Check qualities of first APAs produced in the US at each factory. | 20% | 0 (N) - negligible technical impact | 3-point - triangular | 30 | 50 | 110 | 3-point - triangular | 0.5 | 1 | 2 | Risk hook: ​ 13122.D2247 and 13122.02.A139259 --> RT-131-FDC-FD-151 --> 13122.02.A139260 (risk hook has two predecessors) ​ | ​Wires with tension outside the required limits may occur due to lack of attention/training of the winding personnel, or to problems with the winding machine. Cost/schedule impacts assume issues are 1-layer repairs, due to diligent QC during winding each layer. | 2 - Reasonable estimate | ​Techs are not careful winding; winder is not working properly | ​Strict requirements for QA need to be set at the start of the project, together with formal training of every technician/operator of the winding machine. The overall quality of each constructed APA will be ensured by following detailed procedures for every step of the assembly process (e.g. mesh installation, board placement and gluing, soldering, wire winding, etc.). These procedures already exist from our ProtoDUNE-SP work and are in the process of being modified to the final design of the DUNE FD APAs. For critical steps, an operator and quality control representative will record information in travelers for each APA. A new winding head with active tension control is being developed, which should improve wire tension uniformity. Procedures for regular maintenance of the winders will need to be implemented. | retension 1-layer of wires to proper tension; find root cause for error; possible retrain operators; fix winder; perform maintenance on winder |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 63.3333 | 1.17 | 12.7 | 0.234 | 2023-12-12 07:51 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-158 | LBNF / DUNE | [FD1-APA] Chicago factory takes too long to begin production | ​If the Chicago APA factory production start is delayed then the US APA production may become the critical path | Threat | Management Risk | NO | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-06-01 | 2024-07-31 | ​Chicago factory is producing APAs within the planned timeline | 20% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 72 | 2-point - flat range | 0 |  | 4 | Risk hook: 13122.02.A139260 --> RT-131-FDC-FD-158 --> 13122.02.A139258​ | Assume that for every possible month of delay there will be one extra trip from the UK to Chicago (estimated at $5k), plus additional support from the PSL engineers (estimated at $10k per month plus 3$k of travel). | 1 - Rough guess | This risk can be triggered by delays in the setup of the APA factory at U Chicago as well as by poor training of the technicians involved in the production. | ​Monitor the factory set up and commissioning, including training from experienced personnel from PSL and from Daresbury | ​If the risk is realized, the duration of the production would be extended, requiring extra funding. Additional funding will be provided for engineers from PSL to travel to Chicago and extend their support of the U Chicago team. Travel funding will also be provided to the Daresbury factory personnel to help with addressing the issues at U Chicago. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 36 | 2 | 7.2 | 0.4 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-217 | LBNF / DUNE | [FD1-APA] Insufficient scientific labor for installation | If it is not possible to recruit scientific labor, costed professional labor is needed and costs will increase. | Threat | Management Risk |  | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2027-01-01 | 2027-12-31 | ​Risk will remain until all installation is complete | 30% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 1500 | 1-point - single value |  | 0 |  | Risk hook: 13141.A1210 -->​RT-131-FDC-FD-217 --> 13141.A1220 ​ | ​The total number of uncosted hours necessary to install APAs for a 10 kt detector module is 35.2K hours. We assume that a maximum of 50% of the needed resources may be missing, and a most likely of 25%. We assume $86/hour for costed professional labor. ​APA installation will be performed by a team of 15 people/shift, with two 10 hour shifts/day, 4 days/week, for a period of 10 months. 12 of the 15 people are assumed to be scientists. Schedule impact is 0 to prevent double counting of schedule impact for similar risks in other subsystems. | 2 - Reasonable estimate | ​Institutions do not get base grants - cannot supply labor | ​Proactively contact US institutions and get their commitments. | ​Hire technicians & engineers to perform the work in place of the uncosted scientific resources |  | 3 (M) | 2 (M) | 0 (N) | 2 (Medium) | 750 | 0 | 225 | 0 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-218 | LBNF / DUNE | [FD1-APA] FD1 APAs damaged beyond repair during shipping from Daresbury to FNAL | ​If an accident happens during a shipment of an APA transport frame we may lose both APAs in the frame. | Threat | External Risk |  | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2024-01-01 | 2027-08-30 | ​End of APA shipments | 3% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 3 |  | 6 | Risk hook: 13122.D1422 --> RT-131-FDC-FD-218 --> 13122.D1396​ | ​The schedule delay is time needed to fabricate the four additional APAs. 3 month impact is if the delay happens in the mdidle of production, 6 months if the delay happens at the end of production The probability is for all APA shipments together. | 2 - Reasonable estimate | Handling during shipping | Consortia personnel will be present during loading/unloading of the shipments. Logging devices will track shocks and environmental conditions during transport. The transport will be done by airplane to minimize handling risks. | ​Fabricate additional APAs. |  | 1 (VL) | 0 (N) | 1 (L) | 1 (Low) | 0 | 4.5 | 0 | 0.135 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-219 | LBNF / DUNE | FD1 APA Delay in finalization of frame design | ​If problems are encountered ​​with the integration test of the pre-production APA at CERN, this will delay the finalization of the APA frame design. | Threat | Technical Risk |  | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | Integration test prior to protoDUNE-II installation | 5% | 0 (N) - negligible technical impact | 2-point - flat range | 45 |  | 135 | 2-point - flat range | 1 |  | 3 | ​13122.02.06.01.1421 | ​We estimate a delay from 1 to 3 months, with associated engineering costs of a team of 2 engineers. | 1 - Rough guess |  | ​Oversight of the APA Consortium on the procurement schedule of components for the Ash River tests and close coordination with the Ash River team. Close coordination with CE and PDS Consortia on all interface issues, to be formalized in the Interface documents. |  |  | 1 (VL) | 0 (N) | 1 (L) | 1 (Low) | 90 | 2 | 4.5 | 0.1 | 2023-01-23 16:36 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-010 | LBNF / DUNE | [FD2-PDS] Additional detection efficiency is required | ​If physics simulation results or detector characterization measurements indicate the need for increased detection efficiency to meet collaboration requirements, then additional funding will be required from the project to avoid the possibility that the physics requirements of the DUNE experiment may not be met | Threat | Technical Risk | NO | Peter Shanahan | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-07-06 | 2024-03-31 | This risk can be closed once simulations based on the actual detector response measured in the cold box tests and in the NP02 module show that the detector coverage is sufficient to meet the DUNE physics requirements​ | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 500 |  | 1000 | 1-point - single value |  | 0 |  | Risk hook: 13124.Z401352 --> RT-131-FDC-FD2-010 --> 13124.Z400560 | ​(1) Probability is engineering estimate based on recent fluctuations in simulation. (2) Cost impact was estimated by extrapolating labor and material cost to increasing detector coverage in the range of 5% to 12.5%​​. (3) Schedule impacts has been set to 0 delay because the detector construction timeline will be rearranged to ensure that there is not going to be any delay in the installation.​ | 2 - Reasonable estimate | ​This risk is triggered by measurements indicating the baseline detector does not meet physics requirements. The measurement needs to include a parameterization of the actual photon detector performance as measured in cold box or Module 0 tests. This risk is also triggered by realizing lower than expected detector efficiency before the conclusion of the ProtoDUNE2 module-0 demonstration.​ | Various risk mitigation strategies are already in progress: studies of different geometries, optimizations of the SiPMs and of the Arapuca systems. | If the risk is realized the main response will be to increase the overall surface of the photon detector and/or increase the number of SiPMs in each detector element. |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 750 | 0 | 75 | 0 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-012 | LBNF / DUNE | [FD2-CRP] bottom assembly too technical for undergraduate labor and requires more technicians | ​If the bottom CRP assembly is too technical for students then the US assembly factories will need to repurpose or hire new technicians for the production effort.​ | Threat | Technical Risk | NO | Matthew P. Worcester | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-06-01 | 2024-06-01 | ​The CRP factories begin production with the anticipated student labor. | 20% | 0 (N) - negligible technical impact | 1-point - single value |  | 400 |  | 1-point - single value |  | 0 |  | Risk hook: 13124.A588 --> RT-131-FDC-FD2-012 --> 13124.A369956​ | ​The CRP assembly sequence as currently designed includes significant technical labor. The US assembly factories plan to use uncosted student labor for many of the CRP assembly activities. An assembly plan needs to be developed and engineered to reduce the complexity with a 30% estimated chance that the CRP assembly will continue to require significant technician effort. In this case, the assembly factories will need to spend roughly $400k to add technician effort (assumes 1 FTE at each of the 2 sites for 1 year). This will be known during the prototype phases so the work can be adjusted ahead of the production. | 1 - Rough guess | ​Students not able to perform job on pre-production CRP (in advance of anticipated factory startup).​ | ​Several phases of CRP design, assembly, and prototyping are planned to refine the CRP design and assenbly sequence. | ​Addition of technician labor. |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 400 | 0 | 80 | 0 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-221 | LBNF / DUNE | APA not funded by NSF | ​If the NSF cannot fund the production of the APAs, then the DOE will have to fund the APA production, resulting in a cost increase to the project | Threat |  |  | Alberto Marchionni | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  | 50% | 0 (?) - Not yet defined | 1-point - single value |  | 40000 |  | 1-point - single value |  |  |  |  | Value based on implementation of BCR to remove the production of APAs from the DOE schedule | 3 - Solid estimate |  |  |  |  | 4 (H) | 3 (H) | 0 (N) | 3 (High) | 40000 | 0 | 20000 | 0 | 2021-10-15 09:13 | Mohammed Elrafih | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-014 | LBNF / DUNE | [FD2-PDS] Insufficient Power-over-Fiber efficiency | ​If PoF efficiency is insufficient, as compared to baseline expectations, then we will need more PoF transmitters, receivers, and fiber penetrations into the cryostat, or alternatively, a reduction in cold electronics power which could ultimately impact detector coverage and efficiency depending on preferred risk response. | Threat | Technical Risk | NO | Peter Shanahan | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2021-10-01 | 2023-12-22 | ​Realization of PoF baseline efficiency estimates demonstrated through R&D, prototype, and module-0 installation and module-1 run. | 10% | 1 (L) - somewhat substandard | 2-point - flat range | 200 |  | 1000 | 1-point - single value |  | 3 |  | Risk hook: 13124.Z401346 --> RT-131-FDC-FD2-014 --> 13124.Z401354​ | ​Probability is engineering estimate of design uncertainties. Cost impact is established by scaling baseline system, increasing the number of channels/fibers to effectively mitigate against 10-50% lower than expected efficiency. Schedule impact is engineering estimate assuming scaling PoF system acceptance testing, installation, and commissioning impact. | 2 - Reasonable estimate | ​This risk is realized if measurements performed in the cold box tests indicate that the overall efficiency of the power over fiber system is smaller than estimated, and that therefore either additional power fibers are needed or that the power consumption of the photon detector needs to be reduced. | We are exploring various PoF technologies from different vendors and building relationships with leaders in the field including the University of Illinois. | There are two options: (1) a​dd PoF transmitter-receiver pairs with corresponding feedthrus, (2) turn off or reduce features to save power. Additional feedthrus may be required which could have interface impacts on other detector subsystems, fieldcage and cryostat.​ |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 600 | 3 | 60 | 0.3 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-223 | LBNF / DUNE | Insufficient undergraduate manpower | DUNE-​NSF APA and DS projects utilize a large amount of undergraduate manpower. If it is not possible to recruite enough undergraduates, the projects will need to hire professional manpower at higher cost. | Threat | Management Risk |  | Alberto Marchionni | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  | ​Risk will remain until all fabrication is complete | 50% | 0 (N) - negligible technical impact | 2-point - flat range | 900 |  | 2700 | 1-point - single value |  | 0 |  | Apply 2.2% to 131.02.02.02.09.1 Apply 5.0% to131.02.02.02.09.2 Apply 55.0% to131.02.02.02.09.3 Apply 12.4% to131.02.02.02.09.4.1 Apply 12.4% to131.02.02.02.09.4.2 Apply 3.5% to131.02.02.02.09.4.4 | ​The total number of undergraduate hours necessary for the APA and DS projects is 120,332. We assume that a maximum of 30% of the needed resources may be missing, and a minimum of 10%. The additional cost for professional manpower is assumed to be $75/hour. | 2 - Reasonable estimate | ​Not enough undergraduate manpower is available. | ​Plan in advance for undergraduate labor, taking into account constraints in their schedule. | ​Hire technicians & engineers to perform the work in place of undergraduate manpower. |  | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 1800 | 0 | 900 | 0 | 2023-01-23 16:17 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FD-222 | LBNF / DUNE | [FD1-APA] Reduction of the APA assembly time | ​If the new winding head will provide a better uniformity in wire tension, it will reduce the number of wires outside tolerance, saving the time for retensioning. If the new electrical method for wire tension measurements will work as planned, it will reduce substantially the time required for wire tension measurements. | Opportunity | Technical Risk |  | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 0 - obsolete |  |  | ​End of completion of winding machine modifications and decision on wire tension measurement method | 15% | 0 (?) - Not yet defined | 2-point - flat range | 0 |  | -110 | 2-point - flat range | 0 |  | -5 | 13122.02.A139258,262,264,266,268,270,272,274,276,278,280,282,284,286,288,290​ | ​We estimate that out of 8 shifts needed for tension test and retension, we could save 4 of them, with a 10% saving in APA assembly time. Total APA assembly labor is $2.2M, and total assembly duration per APA is ~1200 hours combined engineering and technician time. | 1 - Rough guess |  |  |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | -55 | -2.5 | -8.3 | -0.375 | 2023-03-12 22:00 | Marco Verzocchi | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-022 | LBNF / DUNE | [FD2] ASICs storage surcharge | ​If the start of the ASIC production is longer than two years from the end of FD1 production, then we incur a storage fee to the foundry to maintain the production masks | Threat | External Risk | NO | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-10-01 | 2025-12-31 | ​The risk can be closed at the completion of all the ASIC productions. | 30% | 0 (N) - negligible technical impact | 1-point - single value |  | 70 |  | 1-point - single value |  | 0 |  | Risk hook: 13124.1.1.5 --> RT-131-FDC-FD2-022 --> 13124.2.2.1​ | ​Based on vendors' quotes. | 3 - Solid estimate | The risk will trigger when two years has elapsed since the end of FD1 ASIC production and FD2 ASIC production has not started, due to onset of storage fees. | ​Plan to start ASIC production for FD1 within two years from the end of FD1 production. | ​Risk impact can be minimized by start the ASIC production |  | 3 (M) | 0 (N) | 0 (N) | 0 (Negligible) | 70 | 0 | 21 | 0 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-226 | LBNF / DUNE | [FD1-HV] Sole source for Kapton resistive surface; and may go out of production | If the sole source of Kapton material for the cathode panels goes out of production then there will be a delay in the delivery of the cathode planes. | Threat | External Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2023-02-01 | 2024-02-09 | ​The risk can be closed once the resistive film is received | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 3 | 13122.A373208 (Ship resistive film to RP factory - CERN) 13122.A12977MS (T6 MS - CPA factory 1 production begins) 13122.A12978MS​ (T6 MS - CPA factory 2 production begins) | Zero cost impact because international partners have the responsibility for the cathode panels. The baseline schedule for the purchase and deliveryof the material is six months and the schedule impact allows for additional procurement time (depending on when we know about the cease of production). Another potential source for the material has been identified. | 2 - Reasonable estimate | ​The source of Kapton goes out of production. | An alternative source of the resistive FR4 panels has been identified. Prototype samples of the new material has been evaluated and found to meet requirements. Cost of the new material is similar to the current choice. ​​This item will be an early purchase if it remains a single source. | Switch to the​ alternative source​ |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 1.5 | 0 | 0.15 | 2023-02-01 15:32 | Jill Dornfeld | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-227 | LBNF / DUNE | FD1 HV Cathode plane assemblies are damaged during delivery to the far site | ​If the cathode plane assemblies are damaged during delivery to SURF then the cathode plane parts will need to be refabricated. | Threat | Technical Risk |  | Sarah Lockwitz | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​The risk can be closed after the cathode plane assemblies are delivered to the caverns. | 5% | 0 (N) - negligible technical impact | 1-point - single value |  | 50 |  | 2-point - flat range | 0 |  | 2 | ​CPA & Field cage installation | ​Risk is assumed beyond the mitigation listed in parentheses and that the walls/top/or bottom would have to be remade from spare parts. (Spare parts at LW. FC/CPA modules can be swapped and replaced from factories in a few days. We have multiple shipments.) There are a total of 50 shipments. The estimated cost is 1/50 of total. The schedule impact is only if an accident occurs to the last few shipments. Cost of $50k for rebuilding components. This was added back in as the CPAs were added to the US scope. | 1 - Rough guess | ​Shipping accidents, poor handling or equipment malfunctions | ​Shipping crate design. Split into more shipments, reduces amount of loss if shipment damage. | ​Refabricate the parts |  | 1 (VL) | 0 (N) | 0 (N) | 0 (Negligible) | 50 | 1 | 2.5 | 0.05 | 2023-01-23 16:37 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-228 | LBNF / DUNE | [FD1-HV] Components are damaged during delivery to the far site | If the FD1 HV components are damaged during delivery to SURF then they will need to be refabricated​ | Threat | Management Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2024-10-04 | 2027-05-18 | ​once the final components (end wall parts)​ are delivered to the caverns | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 50 |  | 70 | 2-point - flat range | 2 |  | 4 | Risk hook: 13122.A13204 --> RT-131-FDC-FD-228 --> 13122.A13212 ​ | ​​​There are 50 CPA crates, 2 EW, 8 TBFC crates. Probability: 1% per crate. For CPAs, 50% chance of one crate is damaged is high, but it is covered by the 4% spares. For FC, 1% x 10 crates = 10% probability of having one crate lost. Cost: replacement value of a EWFC (50% of EWFC frames, 68k) or TBFC crate (1/4 of T/B FC frames, 50k). Schedule: time needed to refabricate the damaged parts ​ | 1 - Rough guess | ​Shipping accidents, poor handling or equipment malfunctions, natural disaster | Shipping crate design. Pick a reliable shipping company. | ​Refabricate the parts |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 60 | 3 | 6 | 0.3 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-229 | LBNF / DUNE -- Operations | FD1 HV Bottom modules are damaged during delivery to the far site | If the bottom modules are damaged during delivery to SURF then the bottom module parts will have to be refabricated.​ | Threat | Technical Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​The risk can be retired once the bottom module parts are delivered to the caverns. | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 200 |  | 300 | 2-point - flat range | 2 |  | 4 | 13122.A13279​ | ​Probability: 5 shipments x 4 crates each x 1% chance of damage = 20% Cost: The range of cost for different crates. Schedule: time needed to refabricate the parts | 1 - Rough guess | ​Shipping accidents, poor handling or equipment malfunctions, acts of God | ​Shipping crate design | ​Refabricate the parts |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 250 | 3 | 25 | 0.3 | 2022-06-05 03:53 | Bo Yu | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-230 | LBNF / DUNE | FD1 HV Top modules are damaged during delivery to the far site | If the top modules are damaged during delivery to SURF, then the top modules will have to be refabricated. | Threat | Technical Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​The risk can be closed once the top module parts are delivered to the caverns. | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 200 |  | 300 | 2-point - flat range | 2 |  | 4 | 13122.A13266 ​ | ​Probability: ​5 shipments of 4 crates each, 1% chance of damage Cost is based on losing one crate. The time allocated is the time needed to refrabricate the parts. | 1 - Rough guess | ​Shipping accidents, poor handling or equipment malfunctions, acts of God. | ​Shipping crate design. | ​Refabricate the parts. |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 250 | 3 | 25 | 0.3 | 2023-01-23 16:37 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-231 | LBNF / DUNE | Underground installation is more labor intensive or slower than expected | If the underground installation is more labor intensive or slower than expected, then additional labor will be required to stay on schedule. | Threat | Management Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​The risk can be retired once the underground installation is complete. | 20% | 0 (N) - negligible technical impact | 1-point - single value |  | 60 |  | 1-point - single value |  | 2 |  | ​Installation of the HVS in the underground | Each single-phase far detector has about eight months of HVS work. The estimate assumes two months additional time needed for installation and a 20% increase in the amount of labor needed. Labor estimates assumed a $50/hour rate and 6k hours of US installation labor for the baseline schedule. | 1 - Rough guess | The underground installation takes longer than scheduled | Careful estimates of the time needed are made from previous installations of similar pieces at ProtoDUNE. Mechanical tests are being performed to understand the effort and challenges involved. |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 60 | 2 | 12 | 0.4 | 2022-08-10 08:33 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-232 | LBNF / DUNE | [FD1-HV] Research program cannot provide all uncosted labor needs for HV installation | ​If the research program cannot provide the full amount of uncosted labor needed for HV installation, then costed labor must be used. | Threat | Management Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2026-09-03 | 2027-06-01 | ​The risk can be closed once the HVS installation in complete. | 30% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | 145 | 581 | 1-point - single value |  | 0 |  | ​Risk hook: 13141.A2580MS --> RT-131-FDC-FD-232 --> 13141.A3340 ​ ​ | The total uncosted hours for underground work is 8,300 hours. This is multiplied against a generic technician rate of $70/hr, giving a max cost impact of $581k. The max cost impact assumes that the project is unable to use any uncosted labor. Middle point is set to 1/4 of the range. No schedule impact if paid replacement workers (generic mechanical techs) are identified​. | 2 - Reasonable estimate | ​A reduction in the amount of uncosted effort the project can supply.. Institutions do not get base grants - cannot supply uncosted labor | ​Proactively contact US institutions and get their commitments | ​project hire additional labor​ |  | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 242 | 0 | 72.6 | 0 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-028 | LBNF / DUNE -- Operations | FD2 elevated surface electric field on alternative FC configuration | ​if the alternative FC configuration is adapted, then there will be an overall higher surface E field and higher risk of HV instability | Threat | Technical Risk |  | Bo Yu | 131.X - LBNF / DUNE - Operations | Proposed | 0 - obsolete | 2023-01-02 | 2028-01-02 | ​FD2 HV system maintain stable operation in FD2. or FD2 modules-0 operates successfully at 300kV. | 10% | 1 (L) - somewhat substandard | 1-point - single value |  |  |  | 1-point - single value |  |  |  | ​DUNE FD2 operation |  | 1 - Rough guess | ​higher E field on the thin profiles near the cathode cause HV instability, forcing the TPC to run at a lower, stable voltage | ​This is already the alternative design choice to mitigate other greater risks in the system. | ​lower operating voltage of the cathode |  | 2 (L) | 0 (N) | 0 (N) | 1 (Low) | 0 | 0 | 0 | 0 | 2023-01-31 14:51 | Bo Yu | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-029 | LBNF / DUNE | [FD2-PDS] Components fail 30-year cold validation testing | ​​If components fail 30-year cold validation testing then alternative components must be found and qualified, which in turn will cause a delay in the beginning of the detector construction | Threat | Technical Risk | NO | Peter Shanahan | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2021-10-01 | 2024-03-31 | When 30-year qualifications for each component and in the integrated module 0 prototype is successfully completed and operated this risk can be retired.​ | 25% | 0 (N) - negligible technical impact | 2-point - flat range | 200 |  | 1500 | 3-point - triangular | 0 | 1.5 | 6 | Risk hook: 13124.Z401304 --> RT-131-FDC-FD2-029 --> 13124.Z401346 | ​​(1) Probability is engineering estimate of 1 in 3 identified components failing 30-year cold validation. (2) Cost impacts is engineering estimate attempting to represent 1 cheaper component failing at the low range vs 3 expensive components failing at the high range. (3) Schedule impacts is the time needed to reorganize the production with different components (i.e. possibly only the membrane mounted detector) | 2 - Reasonable estimate | ​This risk is realized if the any of the electronics components to be installed inside the liquid Argon fails the 30 years qualification process. If that happens replacement components need to be found and qualified. The case where no component meets the 30 years requirement is handled by risk ​​RT-131-FDC-FD2-010 | ​Identify promising components for the use in liquid Argon in the initial state of the investigation and pursue their qualification in parallel. Investigate both the possibility of analog and digital solutions for the cold electronics. Develop alternative solutions (including the use of warm electronics as described in opportunity RO-131-FDC-FD2-018) | ​If the risk is realized move quickly to the investigation of alternative components or (as a fall back solution) to the case where there is no cathode mounted detector and we just have photon detector on the membrane. |  | 3 (M) | 2 (M) | 1 (L) | 2 (Medium) | 850 | 2.5 | 212.5 | 0.625 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-235 | LBNF / DUNE | [FD1-PD] Active Ganging Modification requiring US intervention | If DAPHNE/Cold active ganging is delayed due to redesign then additional US engineering support/photosensor testing may be required | Threat | Technical Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2022-07-01 | 2023-04-30 | ​Completion of production readiness review | 5% | 0 (N) - negligible technical impact | 2-point - flat range | 15 |  | 60 | 2-point - flat range | 2 |  | 4 | Risk hook: 13122.A12512 --> RT-131-FDC-FD-235 --> 13122.A12516​ | Estimate based on potential determination during validation testing that active ganging circuitry does not meet project specificatinos and additional testing at US institutions is required. It is assumed that intervention would require 2 to 4 months of electrical engineering/designer support and minimal M&S. | 2 - Reasonable estimate | ​Failure to meet specifications during testing in ICEBERG, at photosensor test stations or in ProtoDUNE 2 | ​Extensive validation testing in multiple test stations including ICEBERG, photosensor test stations in the US, Italy and Spain, and ProtoDUNE 2. | ​It is expected that any required re-design will be supported by international collaborators in Italy and Spain. Additional photosensor testing in the US would support this effort. |  | 1 (VL) | 0 (N) | 1 (L) | 1 (Low) | 37.5 | 3 | 1.9 | 0.15 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-236 | LBNF / DUNE | FD1 PD Cabling/Connectors inside APA fail to meet specifications | ​If cabling/connectors are demonstrated not to meet specifications then prototyping/validation may be required beyond the current schedule. | Threat | Technical Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​Production readiness review completed for PD cables/connectors, including cold box test at CERN of initial APA set. | 15% | 0 (N) - negligible technical impact | 2-point - flat range | 20 |  | 35 | 2-point - flat range | 3 |  | 4 | 13122.A12502 ​Fabrication of PD support/cable harnesses for APA frames​ | ​Cable tests in APA frame mounting or CERN cold box testing may reveal a problem requiring an additional development cable run or connector modification. Assumes 1 (low end) to 2(high end) months CSU engineering, and one additional developement cable run ($6,000) | 2 - Reasonable estimate | ​Problems with cable mechanical cryogenic testing or cold box testing at CERN | ​Pre-production testing at CSU, operational testing in ICEBERG |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 27.5 | 3.5 | 4.1 | 0.525 | 2023-01-23 16:37 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-158 | LBNF / DUNE | [CRYO] Difficulties in finding suitable installation subcontractor #1 and #2 | ​IF it is difficult to find a suitable subcontractor for the installation of In-Kind Contributions, THEN we will have to pay a premium and this activity will be more expensive. | Threat | Technical Risk | YES | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-04-01 | 2026-06-30 | ​Completion of installation work. Award of installation Subcontract. | 10% | 1 (L) - somewhat substandard | 2-point - flat range | 934 |  | 2629 | 2-point - flat range | 1 |  | 6 | Risk hook: 131123.02.03.1705MS --> RT-131-FDC-CR-158 --> 131123.02.04.85MS​ | Identified 1-2 companies potentially interested. ​The installation work of the IKCs and misc supporting Far Detector #1 is: $9,339k. ​The installation work of the IKCs and misc supporting Far Detector #2 is $7,611k. The minimum for Far Detector #1 is +10% (= $934k). The minimum for Far Detector #2 is 0 (assuming that they same Subctontractor performs the work, they should know better how to do it). The maximum for Far Detector #1 is +20% (= $1,868k). The maximum for Far Detector #2 is +10%(= $761k). This assumes that the same Subctontractor performs the work, they should know better how to do it. There could be schedule delays associated with updating RFP/Subcontract and/or recompeting if unsuccessful. A minimum of 1 mo for minor udpates up to 6 mo for a full recompete (assuming no DOE involvement required). | 1 - Rough guess | ​Market survey reveals little interest for this work from pool of potential bidders. | ​Perform extensive market survey ahead of RFP to understand market and feasibility. |  |  | 2 (L) | 2 (M) | 1 (L) | 2 (Medium) | 1781.5 | 3.5 | 178.2 | 0.35 | 2024-01-13 12:49 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-239 | LBNF / DUNE | FD1 PD Photosensors fail cold cycle testing | ​If validation testing of photosensors demonstrates they do not meet specifications then this will require extended validation. | Threat | Technical Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​Passing of production readiness review | 15% | 0 (N) - negligible technical impact | 2-point - flat range | 15 |  | 30 | 2-point - flat range | 2 |  | 4 | 13122.A12516 ​Fabrication of module photosensor kit​ | ​2 months (low range) to 4 months (high range) extra testing required due to photosensors failing to meet requirements. Costs are engineering time and minor M&S during this time. | 2 - Reasonable estimate | ​Photosensors observed to underperform/fail in QC testing late in the production cycle (pre-ProtoDUNE 2) | ​Extensive preparatory testing at multiple PD sites |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 22.5 | 3 | 3.4 | 0.45 | 2023-01-23 16:37 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-241 | LBNF / DUNE | FD1 PD/APA Rail/Support Design Interface Issue | ​If validation testing of PD support structure demonstrates failure to meet specifications then this will require extended design and validation | Threat | Technical Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  | ​Production readiness review for PD rails/supports | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 15 |  | 30 | 2-point - flat range | 2 |  | 4 | 13122.A12502 ​Fabrication of PD support rails​ | ​Failure of PD support rail system to meet requirements requires 2 months (minimum) to 4 months (maximum) additional design/testing. Covers engineering, design and M&S | 2 - Reasonable estimate | ​Failure of PD support rail system observed in initial installation tests during APA assembly or cold box testing at CERN | ​Extensive QA testing of design at CSU, PSL and Ash River |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 22.5 | 3 | 2.3 | 0.3 | 2023-01-23 16:38 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-242 | LBNF / DUNE | [FD1-PD] Damage during logistics/handling | ​If Photon Detector components are discoverd to have been damaged at delivery then components may need to be repaired if spares are insufficient and the shipping crate design will need to be modified. | Threat | Technical Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2026-10-01 | 2027-12-31 | ​Risk can be closed upon delivery of all PD components | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 30 |  | 60 | 2-point - flat range | 0 |  | 4 | Risk hookd: ​13122.A14746 --> RT-131-FDC-FD-242 --> 13122.A12778 | ​2 months (low range) to 6 months (high range) work required to address problems with shipping and handling techniques. Assumes 2 to 4 months US engineering, plus some M&S​ | 2 - Reasonable estimate | ​Initial inspection (protoDUNE 2 or DUNE FD) of shipped modules exposes problems with shipping plans, techniques. | ​Pre-production shipping tests, including ProtoDUNE 2 | ​Additional module testing and design/engineering of shipping crates required​ |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 45 | 2 | 4.5 | 0.2 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-030 | LBNF / DUNE | [FD2-PDS] Underestimate in level of effort required for 30-year cold validation | ​If more effort is required than estimated to conduct 30-year cold qualification studies on selected components, then we will not be able to complete the studies without adding labor which will cause a delay of the production readiness review. | Threat | Management Risk | NO | Peter Shanahan | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open - Realized | 4 - approved | 2021-10-01 | 2024-03-31 | ​​If 30-year qualifications for each component are successfully completed within estimated labor resources and module-0 integration at ProtoDUNE2 is successfully demonstrated, this risk can be retired as no further qualification studies are foreseen​.​ | 15% | 0 (N) - negligible technical impact | 2-point - flat range | 100 |  | 350 | 2-point - flat range | 0 |  | 3 | Risk hook: 13124.Z401346 --> RT-131-FDC-FD2-030 --> 13124.Z401354​​ | ​​(1) Probability is engineering estimate of unexpected schedule challenges (e.g. involved studies, required time lapses, peer reviews, etc.) in 30-year qualification activities. (2) Cost impacts is engineering estimate attempting to represent 3-6 months extension to qualification activities. (3) Schedule impacts is engineering estimate to represent 0-3 months extension to qualification activities. | 2 - Reasonable estimate | This risk will be realized when a component's qualification studies are foreseen to be taking more effort that estimated during qualification and QC activities. | ​Current baseine already updated to include significant resources for the 30 year lifetime investigation. These estimates will be updated again before launching the 30-year qualification activities for each component. The estimates and planning will be peer reviewed before launching qualification activities. Adding scientific effort from the collaboration will play a key role in risk mitigation. | ​If the risk is realized, either additional uncosted labor will have to join the effort or a change request will be made for additional cost engineering and technician effort for qualification and QC activities. |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 225 | 1.5 | 33.8 | 0.225 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-031 | LBNF / DUNE | [FD2-PDS] Production mechanical packaging costs exceed estimated cost | ​If production mechanical packaging costs exceed estimate, then there will not be sufficient resources in the baseline to cover the full production costs, which then would lead to a reduction in the number of photon detector modules being built with the consequence that the key performance parameter on the number of active channels would not be met. | Threat | Management Risk | NO | Peter Shanahan | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2021-10-01 | 2024-09-30 | ​If final desig reviews are completed with production design not presenting a mismatch with the cost estimates, then this risk can be retired. | 20% | 0 (N) - negligible technical impact | 3-point - triangular | 10 | 80 | 100 | 1-point - single value |  | 0 |  | Risk hook: 13124.Z401354 --> RT-131-FDC-FD2-031 --> 13124.Z400564 ​​ | ​(1) Probability is engineering estimate that it seems likely that not all mechanical interfaces have been foreseen. (2) Cost impacts is engineering estimate to make mechanical modifications for unforeseen estimates at production scale 1-10% inefficiency (640 units). (3) Schedule impact is estimated at 0 because mechanical modifications should be understood by conclusion of Production Readiness Review, so no additional time is needed during production to implement. | 2 - Reasonable estimate | ​Uncertainty in the design for form-factor and survival of cathode HV discharge | Simulation activities are in the baseline to understand the effects of a cathode HV discharge. | ​Design a more complex mechanical object to facilitate cathode HV discharge survival. |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 63.3333 | 0 | 12.7 | 0 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-033 | LBNF / DUNE | [FD2-PDS] Production phase infrastructure and test stand M&S costs exceed initial estimates | ​​​If M&S intended to support production phase infrastructure and test stands are insufficient, then production progress may be limited, which jeopardizes the schedule. | Threat | Management Risk | NO | Peter Shanahan | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2021-10-01 | 2025-09-30 | Once the initial part of the production (phase 1) is completed with sufficient infrastructure and test stand capacity for meeting baseline schedule this risk can be retired. | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 100 |  | 250 | 2-point - flat range | 0 |  | 3 | Risk hook: 13124.Z401354 --> RT-131-FDC-FD2-033 --> 13124.Z400564​ | ​​​(1) Probability is engineering estimate of unforeseen infrastucture or test stand needs to support production phases, this also includes probability that more production sites than anticipated will be included. (2) Cost impacts is estimate of 3x infrastructure and test stand support at high range. (3) Schedule impacts is engineering estimate of realization mid-phase 1 of production which would incur delays due to additional infrastructure or test stand procurements/lead-time. | 2 - Reasonable estimate | ​​​If production phase is slowed by missing support infrastructure or test stands, or need for LAr at test stands. | ​Revisit the plans for construction and for quality control based on the lessons learned from the corresponding activities that will take place in 2022 and 2023 leading to the installation of photon detector components for the Module 0 testing of the vertical drift detector in the NP02 cryostat. ​The development of the procedures and of the test stands for the quality control during production will take place in 2022 using funds that were added to the baseline with BCR FDC-1018​ | ​​If the risk is realised a baseline change request will be needed to increase the number of test stands / aassembly sites and additional personnel will have to be recruited / trained in order to meet the planned production rate. |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 175 | 1.5 | 17.5 | 0.15 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-248 | LBNF / DUNE | Standing army cost for integration and installation activities at SURF | ​In case of work stop orders at SURF, the integration and installation activities may be delayed, which will affect the end date for the detector construction (threshold KPP) and for the commissioning of the first detector (objective KPP). This will also generate a standing army cost for all the personnel under I&I and under the consortia that is paid for work at SURF. This risk is being proposed to ensure that we consider the possibility of this standing army cost. | Threat |  |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  |  |  | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  |  |  | 1 (VL) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2022-08-10 08:33 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-249 | LBNF / DUNE | Need additional MPOD modules for bias voltage | The current design of the bias voltage supply plant may not allow us to implement detector interlocks with the required fine granularity. If we are required to implement detector interlocks with the granularity of a single APA we then may have to revert to a bias supply distribution system that requires one crate for each row of APA, that entails an increase in costs. | Threat | Technical Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 1 - draft | 2022-01-04 | 2025-10-28 | The risk can be closed only when we decide that the current design of the bias voltage supply system, with a reduced number of Wiener crates and MPOD modules, is compatible with all the requirements on the hardware interlocks for the DUNE detector safety system. If that is not the case, we may have to increase the number of Wiener crates and MPOD modules, such that we can have hardware interlocks at the level of a single APA.​ | 50% | 0 (N) - negligible technical impact | 1-point - single value | 2300 |  |  | 1-point - single value |  | 0 |  | ​13122.2004.143.230 (60% of the cost impact), 13122.2004.183.1070 (40% of the cost impact) | The estimate has been made by changing the number of MPOD crates from 30 (13 for the first detector, 13 for the second detector, 4 spares) to ​56 (25 for the first detector, 25 for the second detector, 6 spares) and the number of MPOD modules from 146 (65 for the first detector, 65 for the second detector, 16 spares) to 330 (150 for the first detector, 150 for the second detector, 30 spares) | 3 - Solid estimate | ​This risk is realized if we decide that we do not want to run with hardware interlocks that operate at the level of multiple APAs (two rows of APAs, 12 APAs) and that we prefer to operate with hardware interlocks that operate the level of a single APA. | We need to investigate the possibility of using different power supplies that may allow us to use a finer granularity for the interlocks. | ​If the risk is realized, the only solution is to purchase additional power supplies. |  | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 0 | 0 | 0 | 0 | 2022-08-10 08:33 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FI-126 | LBNF / DUNE | Internal Cryogenics supplied by partner | ​If the internal cryogenics for Detector #1 is supplied by a partner as In-Kind-Contribution then DOE does not have to supply it. | Opportunity | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​Agreement with International partner to supply Internal Cryogenics for Detectors #1 and/or #2. | 80% | 0 (N) - negligible technical impact | 1-point - single value |  | 667 |  | 1-point - single value |  | 0 |  | ​Manufacture and Ship Internal Cryogenics #1 | ​Fermilab Directorate, Cryogenics Manager and Project Integration Director are actively pursuing international partners to supply In-Kind-Contributions to LBNF cryogenics. An agreement is being negotiated with Poland for the supply of the Internal Cryogenics for Detector #1 The current value of the scope is $667k/detector ($FY20). | 3 - Solid estimate | ​Signature of agreement with Poland for the supply of the Internal Cryogenics for Detector #1, | ​Negotiations with Poland for the supply of the Internal Cryogenics for Detector #1 |  |  | 5 (VH) | 1 (L) | 0 (N) | 2 (Medium) | 667 | 0 | 533.6 | 0 | 2022-08-10 08:26 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-006 | LBNF / DUNE | External work stoppages incur additional subcontractor cost | ​If there is a work stoppage beyond the control of the subcontractor(s) during the Integration phase of work, from handover of the underground space to completion of the Project, then the Project will need to pay additional costs to fixed-price subcontractor(s) due to the inability to accomplish work within the established schedule. Particularly for in-kind contributions, allowance for these costs is not included. | Threat | External Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​when Integration fabrication/installation work is complete; Detector #2 installation complete | 50% | 0 (N) - negligible technical impact | 3-point - triangular | 100 | 750 | 3000 | 3-point - triangular | 0 | 1 | 3 | start of Detector #2 filling; end of project​ | ​Estimate reflects potential exposure of subcontractor labor costs during cryostat installation (warm and cold) and cryogenics for the period T0 (AUP) through T0+3. Risk should be revisited as each major phase of work is accomplished, at least annually. | 1 - Rough guess | Operational problems at facility; staff support issues; supply chain delays | Close coordination with other project partners and members, including SDSTA, SDSD, Integration logistics and compliance office. |  |  | 4 (H) | 2 (M) | 1 (L) | 3 (High) | 1283.3333 | 1.33 | 641.7 | 0.665 | 2022-08-10 08:34 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FI-004 | LBNF / DUNE | Cold Box Reused for Detector #2 Installation | If the FD Installation team is able to re-locate and re-use the 3 cold boxes used for integrated detector testing at Detector #1 to Detector #2, then the Integration team can save budget allocated for the second set of cold boxes for Clean Room #2. | Opportunity | Technical Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | the risk should be revisited after final design is complete to evaluate cost and probability information. | 20% | 0 (N) - negligible technical impact | 1-point - single value |  | 700 |  | 1-point - single value |  |  |  | procurement of cold boxes | estimate reflects the estimate for the cold boxes for clean room #2 (south cavern)​ | 1 - Rough guess |  | ​Develop the design of the cold box, considering modularity and crane coverage constraints, particularly while the clean room is operational until the closure of the cryostat TCO. |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 700 | 0 | 140 | 0 | 2022-08-10 08:26 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-005 | LBNF / DUNE | Ross Cage reaches end of life | If new (2020) Ross Cage reaches end of life prior to the end of the LBNF/DUNE Project, then the Integration Project will incur the cost of a new cage, as well as scheudule delays from downtime.​ | Threat | External Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​end of project or periodic inspections indicate Ross Cage will be sufficient through end of project | 20% | 0 (N) - negligible technical impact | 1-point - single value |  | 300 |  | 1-point - single value |  |  |  | cryostat installation, detector installation​ | Cost estimate represents 2020 cost for fabrication of a new cage (design is complete). ​Schedule estimate assume cost i​s pro-active, rather than reactive. | 2 - Reasonable estimate |  | ​Inspection & evaluation, particularly as FSCF work progresses and cage gets used extensively. |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 300 | 0 | 60 | 0 | 2022-08-10 08:34 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-250 | LBNF / DUNE | [FD1-PD] Research program not able to provide all uncosted labor needs for installation | ​If the research program cannot provide the full amount of uncosted post-doc labor needed for installation, then costed labor must be used. No schedule impact due to risk, as we assume sufficient warning to train replacement personnel. | Threat | Management Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2027-01-01 | 2027-12-31 | ​The risk can be closed once the PDS installation is complete. | 30% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 255 | 1-point - single value |  | 0 |  | Risk hook: 13122.A3340 --> RT-131-FDC-FD-250 --> 13122.A1210 ​ ​​ | ​The total uncosted hours for US Post-Doc involvement in PDS installation is ~3,000 hours. This is multiplied against a generic technician rate of $85/hr, giving a max cost impact of $255k. The max cost impact assumes that the project is unable to use any uncosted labor. The probability is based on the assumption that US institutions go through comparative reviews every 3 years and that some institution may not get its base grant support. ​ | 2 - Reasonable estimate | ​A reduction in the amount of uncosted effort the project can supply. Institutions do not get base grants - cannot supply labor | ​Proactively contact US institutions and get their commitments​. | ​Hire professional labor (on project) to cover shortfall |  | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 127.5 | 0 | 38.3 | 0 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-007 | LBNF / DUNE | Detector #1 and #2 installation in parallel | IF at the start of Detector 1 installation the schedule for Detector 2 installation indicates that the installations will be proceeding in parallel THEN a complete set of equipment needs to be procured for the Detector 2 installation and no equipment will be re-used. Cost is the difference between what is planned now for the Detector 1 M&S and the Detector 2 M&S which is $650k. The probability is 50% as there is significant uncertainty in the excavation, BSI, cryostat construction times. | Threat | Technical Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​The schedule needs evaluation at the start of detector 1 installation to determine if the start of detector 2 installation will overlap detector 1. | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 650 |  | 1-point - single value |  | 0 |  | ​The procurement activities for detector #2 | ​The cost is the difference between the detector 1 infrastructure and the detector 2 infrastructure minus the items that can be used for both detectors like the electrical diagnostic equipment. | 2 - Reasonable estimate | ​Changes to the LBNF schedule can shift the time difference between detector 1 and detector 2 installtion. If delays in the CF, cryostat construction or cold structure construction cause an overlap in installation then the additional material needs purchased. | ​A majority of the materials are duplicated to minimize the time between the start of detector 1 and 2 installation already. No additional mitigation would be cost effective. |  |  | 4 (H) | 1 (L) | 0 (N) | 2 (Medium) | 650 | 0 | 325 | 0 | 2022-08-10 08:34 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-176 | LBNF / DUNE | [CRYO] IDIQ IKC installation and Argon distribution review & approval takes longer than planned | ​IF the DOE procurement review process takes longer than expected AND/OR the selected subcontractor internal review process takes longer than expected THEN the award of the IDIQ for the IKC installation and the Task Order for the Argon Distribution will be delayed. | Threat | Management Risk | YES | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2025-01-07 | 2028-08-31 | ​Retire this risk when the IDIQ for IKC Installation and Task Order for Argon Distribution is awarded. | 40% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 2 | 4 | 6 | Risk hook: 131123.02.01.616MS --> RT-131-FDC-CR-176 --> 131123.02.01.617MS​ | The maximum expected value of this acquisition exceeds $25M. FSO, IRB and HCA reviews are required for Acquisition Plan, RFP and Award. If the process exceeds the timeline from the Procurement Acquisition Lead Times (PALT), then the project will be affected. The Argon Distribution is less than 2.5 months off the critical path. Experience with other acquisitions of similar size and complexity suggests that it is possible to exceeds the PALT timelines. The internal review process of the selected vendor may take 10-15 business days as well and may not start until the subcontractor is sent for signature (based on experience with similar size projects). Cost Impact is escalation, because everything is delayed by corresponding amount of delay here. | 2 - Reasonable estimate | ​​Complicated procurement processes​. Contract requires approval from FRA, IRB and HCA. Process can be long, which adds levels of approval authority and complications. | ​​Keep FSO informed as to status of acquisition plan solicitation and issues that may have arisen during proposal period. Follow up with DOE/FSO to review and approve submittals​. |  |  | 4 (H) | 0 (N) | 1 (L) | 2 (Medium) | 0 | 4 | 0 | 1.6 | 2024-01-13 12:51 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-009 | LBNF / DUNE | I&I Cumulative increase in noise level in detector 1 observed | ​IF cumulative increases in the noise level in detector 1 are observed THEN the installation will need to be stopped and the noise sources mitigated. Possible noise sources are ground loops, RF sources, inadequate filters in the power supplies and the CALCI system. | Threat | Technical Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​If there is a significant source of noise that scales with the system size then it will be observable by the time row 12. The noise can be evaluated at this time and the risk closed. | 25% | 1 (L) - somewhat substandard | 1-point - single value |  |  |  | 2-point - flat range | 0.5 |  | 3 | 13141.A10730 (complete installation and testing of FD1)​ | ​This risk is difficult to estimate as it scales with the system size. ProtoDUNE cannot be used to mitigate this risk as it only has 4 APAs. General experience from other systems indicate that as the size of the system grows effects that are small with only one detector module can become large with many modules are deployed. The probability is roughly 25% as ProtoDUNE would be sensitive to this at some level. The impact would be a 3 month delay as the source could be difficult to find. | 1 - Rough guess | ​Installation of detector rows past row 1. | Frequent monitoring, continuous testing |  |  | 3 (M) | 0 (N) | 1 (L) | 1 (Low) | 0 | 1.75 | 0 | 0.4375 | 2023-01-23 16:40 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-010 | LBNF / DUNE | Equipment design changes for Detector#2 | ​IF there are any changes in the design of equipment for detector #2 THEN noise sources could be introduced that were not observed in detector 1. These sources would be seen after Row1 is installed and would require time to mitigate. The impact would be one month as the search is for changes in equipment. The probability is 25% based on the likelyhood that there are design changes between Detector#1 and #2 or that some parts are unavailable for detector 2. | Threat | Technical Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​Testing after completion of row1. The risk should be re-evaluated after the PRR for Det2 are complete. | 25% | 1 (L) - somewhat substandard | 1-point - single value |  |  |  | 1-point - single value | 1 | 1 | 1 | ​Installation | ​Untill the PRR for detector #2 changes in the design are possible. Any changes will add risk. | 0 - Wild guess |  |  |  |  | 3 (M) | 0 (N) | 0 (N) | 1 (Low) | 0 | 1 | 0 | 0.25 | 2022-08-10 08:34 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-011 | LBNF / DUNE | [I&I] Additional Installation testing required after PDUNE-II | ​IF the results from protoDUNE-II indicate more testing is needed during installation, THEN the installation plan will need to be revised and more test activities added. | Threat | Management Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved | 2023-10-01 | 2026-09-30 | ​When the lessons learned form PDUNE-2 are available, the testing activities can be refined. | 25% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 1 | 1.5 | 2 | Risk hook: 13141.04.02.413 --> RT-131-FDC-FI-011 --> 13141.04.02.417MS ​​ | ​Substantial alignment of the lasers or the testing of other equipment could require adding more testing activities to the schedule. The probability is 25% based on the relative immaturity of the CAL equipment. It is expected this would add an integral of one month to the installation time. The likelihood of deliverables is increased due to the potential for a design from LANL and testing in ProtoDUNE-II. | 1 - Rough guess | ​This is triggered at the start of ProtoDUNE-II data taking which needs to be before the final design of installation is complete. | Additional test setup during PD-II | ​Add additional testing activities to the schedule​ |  | 3 (M) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 1.5 | 0 | 0.375 | 2024-01-13 10:42 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-036 | LBNF / DUNE | [FD2-PDS] Photon detector electronics generates noise on the TPC strips readout | If the photon detector induces noise on the strips of the charge readout planes of the TPC, then additional groinding work will be required prior to mitigate this problem. | Threat | Technical Risk | NO | Peter Shanahan | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2021-10-01 | 2024-06-30 | ​This risk can be closed if at the end o ProtoDU​NE 2 operations if there is no sign of noise induced from the photon detector on the electronics used for the readout of the charge readout planes during FD2 ProtoDUNE 2 operation. | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 100 |  | 500 | 2-point - flat range | 2 |  | 4 | Risk hook: 13124.Z401346 ---> RT-131-FDC-FD2-036 ---> 13124.Z401354 | ​​(1) Probabilitiy is engineering estimate of noise induction likelihood and critical frequencies. (2) Cost impacts is engineering estimate for mechanical shielding mitigation labor of 2 engineers and 2 technicians for 3 to 6 months​. (3) Schedule impacts is engineering estimate to adjust design and installation activities based on mechanical sheilding mitigation. | 2 - Reasonable estimate | This risk is realized if excess noise is observed on the readout of the charge readout planes when operated together with the PDS with power and readout turned on in the cold box test or FD2 ProtoDUNE 2 validation. | ​​Reasonable shielding is implemented in the PDS readout and cabling plan, and simulations will be conducted to minimize risk of inducing noise on TPC at critical frequencies. Prototype and module-0 completion will improve confidence if there is no indication of noise in neighboring detectors. | ​​If risk is realized, mitigations would include mechanical RF shielding solutions and possible modifications to the readout electronics will be designed and integrated requiring labor and M&S change requests.​ |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 300 | 3 | 30 | 0.3 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-053 | LBNF / DUNE | [FD2-CRP] anode PCB production delays | ​If the vendors for the anode PCB (including the drilling) do not deliver on time then the top and bottom CRP assembly factories will be delayed jeopardizing the completion of the CRP on time.​​ | Threat | External Risk | NO | Serhan Tufanli | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-01-01 | 2025-01-10 | The risk can be closed once all drilled anode PCB have been delivered to the top and bottom CRP assembly sites.​ | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 1 |  | 2 | Risk hook: 13124.A367418 --> RT-131-FDC-FD2-053 --> 13124.A367428​ | ​(1) vendors may underestimate fabrication times or experience shortages of materials,; however, we estimate that by 2024 the disruption from Covid will be minimized, and we will have produced several prototype runs with the vendor to gain experience, so a low probability is assigned. (2) If the CRP assembly sites are delayed due to vendor delays, then staff will have to be found and trained at later dates than expected. Estimate engineering and technician labor for $50k for two months at each assembly site. (3) A guess is made that at least one vendor will be 2 months behind schedule by the expected end of US CRP production. ​ | 1 - Rough guess | ​Vendors inform us that they cannot deliver on time. ​ | ​Identify several possible vendors for each part. Several rounds of prototype CRP will be produced with the selected vendors. Orders will be placed as early as possible (after CD-3) before needed at the production sites. | ​Possibly a second vendor could produce a fraction of anode PCB before production is complete.​ |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 1.5 | 0 | 0.15 | 2023-12-12 07:57 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-151 | LBNF / DUNE | Cryo: Need to acquire membrane cryostat materials from China instead of South Korea | ​If the stainless steel market shifts from South Korea to China then the quality of the supply may be affected and potential delays. | Threat | Technical Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  | ​When order placed for cryostat materials | 20% | 1 (L) - somewhat substandard | 1-point - single value |  |  |  | 3-point - triangular | 2 | 3 | 6 | 131123.01.01.572,131123.01.01.684. | schedule impact to reorder materials | 0 - Wild guess |  | ​No foreseeable mitigations |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 3.67 | 0 | 0.734 | 2023-01-23 16:35 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-152 | LBNF / DUNE | Cryo: China takes over LNG markets, GTT goes out of business | ​If the ship building market shifts from South Korea to China, then China will have an interest in expanding their market to the LNG ship building industry. This may impact GTT's business and potentially make it impossible for CERN to contract for the Cryostat. | Threat | External Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  | ​When contract awarded to procure materials for cold cryostat | 5% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 3-point - triangular | 12 | 18 | 24 | 131123.01.01.882,131123.01.01.678 | ​Time for CERN to develop relationship and contract to procure materials and perform design. | 0 - Wild guess | ​booming Chinese economy GTT out of business | Order as soon as possible |  |  | 1 (VL) | 0 (N) | 3 (H) | 2 (Medium) | 0 | 18 | 0 | 0.9 | 2023-01-23 16:35 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-153 | LBNF / DUNE | CERN unable to completely fund Cryostat #1 | If CERN is unable to completely fund Cryostat #1 then DOE may have to provide resources.​ | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​When CERN has placed contract for materials | 30% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 6300 | 1-point - single value |  |  |  | Cold cryostat procurement | 30% x procurement of cold cryostat ($19M) = $6.3M​ Cost estimate of SBND Cryostat is 30% more than budgeted. The cost estimate for this risk is based on SBND experience. | 1 - Rough guess | Steel market prices greater than estimated | no foreseeable mitigations​ |  |  | 3 (M) | 2 (M) | 0 (N) | 2 (Medium) | 3150 | 0 | 945 | 0 | 2022-08-10 08:27 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-CR-001 | LBNF / DUNE | [CRYO] Potential partner to fund FS Process Controls | ​If a partner has a strong desire to contribute to the process controls work then DOE may have to procure fewer items.​ | Opportunity | External Risk |  | Ian L. Young | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | A partner provides funding for process controls items. | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | -3800 | 1-point - single value |  | 0 |  | 13123.02.03.6941,13123.02.03.6945,13123.02.03.6947,13123.02.03.6943. | Cost impact based on value of M&S items in plan. ​Discussed probability with Hema R on Mar 4, 2021. Agreed that 10% is good. | 2 - Reasonable estimate | Commitment from Germany | Work with directorate and potential international partners to leverage interest​ |  |  | 2 (L) | 2 (M) | 0 (N) | 2 (Medium) | -1900 | 0 | -190 | 0 | 2023-01-30 15:30 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-056 | LBNF / DUNE | [FD2-CRP] Bottom CRP require additional cold testing at far site due to damage on receipt | ​​If ​​the bottom CRP have issues during shipping that can only be found at cold then a cold test of all bottom CRP will be required jeopardizing the bottom CRP installation cost and schedule | Threat | Technical Risk | NO | Matthew P. Worcester | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2021-10-01 | 2023-04-01 | ​Prototype CRP are shipped from the US to CERN with no damage to the CRP found in cold box tests. | 20% | 0 (N) - negligible technical impact | 2-point - flat range | 100 |  | 300 | 2-point - flat range | 2 |  | 3 | Risk hook: 13143.50950 (SS) --> RT-131-FDC-FD2-056 --> 13124.A367262X​​ | ​(1) Based on experience with testing protoDUNE SP APAs in the NP04 cold box, there is some chance of finding issues after shipping the bottom CRP (which include the cold electronics) at cold (2) setting up a cold test platform at SURF is estimated to be $44k (within the CRP scope, this may also add costs to the cold electronics scope), so this is used for the cost value, plus an additional $15k for CRP labor to travel to South Dakota (3) the expectation is to learn about issue during shipping with prototypes, so assembling a cold test site at the far detector could begin well before bottom CRP installation, without impacting the schedule; however, if issues are found with bottom CRP on reception at the far site, setting up a cold test platform will delay bottom CRP installation by 6 months, which is the time in the current schedule to set up the cold testing at the US assembly sites. | 1 - Rough guess | ​CRP received at far site are found to be damaged or compromised on receipt. ​ | ​Shipping prototype bottom CRP from the US assembly site to BNL for cold test. Shipping prototye bottom CRP ​to CERN for cold box tests. | ​Set up a cold test platform for bottom CRP at the far detector site. |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 200 | 2.5 | 40 | 0.5 | 2023-12-12 07:57 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-207 | LBNF / DUNE | [FD-CE] insufficient TPC electronics spares - other than ASICs and FEMBs | ​If detector components (cold cables, cryostat penetrations, WIECs, supplies, warm cables) fail the quality control criteria at a rate larger than that planned as part of the construction spares, then additional components need to be procured or fabricated, and then tested. This could entail a delay in the integration/installation of the detector and later in the commissioning and the beginning of physics operation. ​ | Threat | Technical Risk | YES | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-04-01 | 2028-11-24 | ​This risk can be closed when the installation of the second Far Detector module is completed and the FD1 and FD2 cryostats have been sealed. | 10% | 0 (N) - negligible technical impact | 3-point - triangular | 100 | 500 | 1500 | 2-point - flat range | 0 |  | 4 | Total risk probability should be shared equally between the two risk hooks: FD1: 13141.A1280 --> RT-131-FDC-FD-207-A --> 13141.A1290 FD2: 13143.51020 --> RT-131-FDC-FD-207-B --> 13143.51030 | ​In almost all the areas we are planning on 10% of spares for the first detector. For the cost impact we assume that an extra 10% of spares for all detector components are needed to complete the first detector ($1M). We then assume a triangular distribution that has starts at 10% of this value, a maximum at 50% of this value and goes back to zero at 1.5 times the value. For the delay we assume a flat distribution between 0 and 4 months. We assume the cost and schedule impact estimates above are shared between FD1 and FD2. | 2 - Reasonable estimate | ​This risk is triggered if any of the detector components (other than ASICs and FEMBs, that are already handled by another risk) has a low yield and extra spare parts are required to complete the assembly of the detector. | ​This risk is mitigated by a careful planning for spares that foresees starting the fabrication of the components for the second detector ahead of the beginning of the installation of the first detector (if the yield is consistently low this allows using the parts for the second detector as spares for the first one). Careful monitoring during the QC process will allow us to detect the occurrence of issues as early as possible, modify the fabrication process and/or address design issues if needed, and plan for extending the fabrication. For some parts that may have long lead times we will plan on having a larger number of spares. Rules for handling and shipping of parts will also help mitigate losses. | ​Fabricate additional spare parts as early as possible if we realize that the yield is lower than planned. |  | 2 (L) | 2 (M) | 1 (L) | 2 (Medium) | 700 | 2 | 70 | 0.2 | 2024-01-13 13:00 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-060 | LBNF / DUNE | [FD2-CRP] additional iteration of adapter cards needed to address noise issues | ​If the design of the of the adapter cards needs to be modified to noise issues that are observed in cold box tests, then an additional design iteration will be required, leading to additional prototyping costs | Threat | Technical Risk | NO | Matthew P. Worcester | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-08-01 | 2024-09-30 | ​This risk can be closed when tests demonstrate that the design of the adapter boards does not require any modification​ | 5% | 0 (N) - negligible technical impact | 2-point - flat range | 20 |  | 40 | 2-point - flat range | 1.5 |  | 4 | Risk hook: 13124.A381273 ---> RT-131-FDC-FD2-060 ---> 13124.A381283 | The probability of this risk is a rough estimate based how the noise affects the CRP. The estimate of the cost impact is a based on the need for a few weeks of engineering and for the fabrication of new adapter cards. The time impact assumes 1 month delay for engineering, 1 month delay for the fabrication of new adapter cards and 1 month delay for repeating the tests, with variations of -50%​/+30% | 1 - Rough guess | ​​ | ​Possibly none (a possible risk mitigation is to design an alternative adapter card, use it in a CRP test, and demonstrate that the adapter card itself is not the problem, but this somehow corresponds to realizing the risk, although it would possibly cut down the time for the next iteration). | ​If the risk is realized proceed as quickly as possible with the update of the design of the adapter cards, while at the same time preparing a BCR for the cost increase / schedule change |  | 1 (VL) | 0 (N) | 1 (L) | 1 (Low) | 30 | 2.75 | 1.5 | 0.1375 | 2023-12-12 07:57 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-251 | LBNF / DUNE | FD1 PD Warm Electronics requires additional engineering/respin | ​If problems are discovered with warm readout electronics then our inernational partners might require assistance from US electrical engineering to resolve otherwise the project would end up having a detector that may not meet the requirements of the KPPs. | Threat | Technical Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​Production readiness review for PDS warm electronics | 30% | 0 (N) - negligible technical impact | 2-point - flat range | 30 |  | 60 | 1-point - single value | 3 |  | 6 | 1322.A12742​ (PDS warm electronics fabrication) | ​Assumes modifications to DAPHNE design discovered which require a warm electronics re-design beyond those anticipated in the current schedule. Between 3 to 6 months delay, with approximately $10,000 per month assumed cost | - Not yet defined - | ​Problems discovered with DAPHNE readout or communications with DAQ (ICEBERG, Italian/Brazilian/Spanish test sites | ​Two rounds of DAPHNE prototypes are planned, as well as testing in ICEGERG and at other PD test sites |  |  | 3 (M) | 0 (N) | 1 (L) | 1 (Low) | 45 | 0 | 13.5 | 0 | 2023-01-23 16:38 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-015 | LBNF / DUNE | FS Indirects on Electrical Power | If SDSTA's indirect rate charged on the electrical power subcontract increases during the life of the project, then the project will incur additional costs to maintain the power.​ | Threat | External Risk |  | Patrick L. Weber | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​when the project is complete. | 15% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | 220 | 1100 | 1-point - single value |  | 0 |  | ​increased cost only to BCR 234 (new activity required) | Total indirects on contract at current rate equal $2.2m. Most likely scenario assumes 12% increase​. Upper boundary of impact is based on a 50% increase to the rate.​ Probability reflects the fact that increase may only impact a portion of the contract during the life of the Project. | 2 - Reasonable estimate | ​SDSTA increases indirect rates | negotiations ongoing between DOE and Black Hills Energy. Expect resolution in fall 2020. |  |  | 2 (L) | 2 (M) | 0 (N) | 2 (Medium) | 440 | 0 | 66 | 0 | 2022-08-10 08:34 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-064 | LBNF / DUNE | [FD2-HV] Field cage profiles need alodine coating | Current plan is to skip the coating of the FC profiles to cut cost. If ProtoDUNE-VD experience shows the need for the coating, there will be additional cost to CERN. | Threat | External Risk | NO | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-10-01 | 2028-01-30 | FD2 field cage assembly complete. | 20% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 2 |  | Risk hook: 13141.A13659MS --> RT-131-FDC-FD2-064 --> 13124.A381 ​ | The FC profile production is CERN's responsibility therefore no cost impact to DUNE-US. To add a production step to coat the profiles is estimated to add a 2 months delay in the profile delivery to SURF. | 2 - Reasonable estimate | ​ProtoDUNE-VD shows the need for the conductive coating on FC profiles | perform additional tests to evaluate the need for the coating | ​Add alodine coating to the FC profiles​ as an additional fabrication step (may involved another supplier). We are investigating a coating process that could be performed at SURF during the FC assembly​ period. |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 2 | 0 | 0.4 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-016 | LBNF / DUNE | [I&I] Equipment requires major repair | If there is a major failure (beyond normal maintenance) of DOE-owned material handling equipment during the Integration ​phase of work at the Far Site, ​then installation work will be slowed due to unavailability of equipment while repairs are conducted. | Threat | Management Risk |  | Patrick L. Weber | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  | ​end of project | 30% | 0 (N) - negligible technical impact | 3-point - triangular | 25 | 125 | 500 | 3-point - triangular | 0 | 0.1 | 0.5 | 131123.01.01.568 (30% of the risk)​ 131123.01.01.572 (30% of the risk) 13141.A3340 (40% of the risk) | A percentage of budgeted purchase cost of equipment including cranes, aerial lift, alimak, transport tools, clean room equipment. ($2.58m total) Rental equipment excluded. Cost Estimate includes repair estimate + quick-response service call. Schedule impact based on most-impactful failure with cavern crane. | 1 - Rough guess |  | Plan includes periodic maintenance and minor repair, including annual inspections, as appropriate. |  |  | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 216.6667 | 0.2 | 65 | 0.06 | 2023-01-31 14:50 | Jill Dornfeld | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-252 | LBNF / DUNE | FD1 PD warm electronics require extra design | ​IF testing of PD warm electronics reveals flaws requiring extra design THEN extra design/engieering may be required | Threat | Technical Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​Completion of PRR for warm electronics​ | 50% | 0 (N) - negligible technical impact | 2-point - flat range | 150 |  | 300 | 2-point - flat range | 1 |  | 3 | ​13122.A12736 (Initial 10 DAFNE modules) | ​Tests of prototype PD warm electronics are at an early stage, and may reveal weak points in the design requiring additional, unbudgeted engineering to rectify. A particular possibility is that the 4.8 gbs data transfer rate amy not work with DAQ, requiring re-design to utilize a faster FPGA. | 2 - Reasonable estimate | ​Warm electronics validation testing may reveal we​akness in the design following to planned second design revision during the leadup to ProtoDUNE 2, or ProtoDUNE 2 testing may reveal a need to increase the data transfer rate to 9.6 gbs. | ​Warm electronics validation testing at Fermilab, in Colombia, and in Italy. System interface testing at ICEBERG and at ProtoDUNE 2. |  |  | 4 (H) | 1 (L) | 1 (L) | 2 (Medium) | 225 | 2 | 112.5 | 1 | 2023-01-23 16:38 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-253 | LBNF / DUNE | FD1 PD Warm electronics require more costly components (e.g. FPGA) | ​During warm electronics testing it is found that the design requires improvements leading to more expensive components. Of particular concern are the FPGAs. | Threat | Technical Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  | ​Completion of PD warm electronics PRR | 30% | 0 (N) - negligible technical impact | 2-point - flat range | 150 |  | 300 | 1-point - single value |  | 2 |  | 13122.A12740 (DAFNE boards fabrication) | Risk based on estimates for additional costs of faster FPGA/warm electronics motherboard in case of compatability issues communicating with DAQ | 2 - Reasonable estimate | ​Problems found with PD warm electronics during interface testing with DAQ or in testing at ICEBERG or ProtoDUNE 2 | ​vertical slice nterface testing with DAQ (Q4 2020), ICEBERG, ProtoDUNE 2 testing |  |  | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 225 | 2 | 67.5 | 0.6 | 2023-01-23 16:38 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-209 | LBNF / DUNE | [I&I] Excessive noise observed during detector commissioning | ​If during the detector commissioning prior to the closure of the TCO an excessive noise is observed in the detector electronics, then some corrective actions may be required, which could entail a delay in the detector commissioning and the beginning of operations. | Threat | Technical Risk | YES | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-08-01 | 2029-02-28 | This risk can be closed only after successful start of operations with both Far Detector modules​ | 30% | 2 (M) - significantly substandard | 3-point - triangular | 100 | 250 | 2000 | 2-point - flat range | 3 |  | 9 | Total probability should be equally split for the two risk hooks: 1) 13141.01.01.576 --> RT-131-FDC-FD-209-A --> 13141.01.01.862MS 2) 13143.01.01.576 --> RT-131-FDC-FD-209-B --> 13143.01.01.862MS The risks FD-209-A and FD-209-B are uncorrelated | The upper limit on the cost is obtained using the estimate of the cost of the WIBs and power supplies and assuming that half of them need to be replaced (one or the other, but not both). A job this size would also require about 6 months of time. The lower limit on the cost/schedule impact is obtained by assuming that a few weeks will be needed for some minimal rework or additional RF filtering. The distribution of the risk cost impact is assumed to be triangular with a spike at low values as many grounding and shielding modifications would not require a lot of resources. The schedule impact assumes the noise will most likely be observed before half the APA are installed or at the start of the B_CRP installaiton. A minimum of 3 months is assumed if 2 months are needed to identify a solution and order simple parts which can then be implemented in one month. 9 months are assumed if a more complicated solution is required (2 month to identify the problem, 3 mo to place order, 3 month to fab and 1 month to install) | 2 - Reasonable estimate | ​This risk is triggered by the observation that there is excessive noise in the detector once initial tests are performed after the insertion of the APAs inside the cryostat. This risk covers only the changes required on the TPC electronics side, but the risk could also be addressed by changing other detector components (CISC, PDS, HV). If the risk is realized before the closure of the TCO, hardware replacement in the TPC electronics can be envisaged. If it is realized prior to the filling with LAr, additional protections could be put in place. If the risk is realised once the cryostat is completely full, the only possible solution is to add noise filtering inside the WIB or in the DAQ backend. | ​Perform multiple integration tests with as many detector components as possible, starting with the tests with the small TPC in the ICEBERG cryostat at Fermilab, continuing with the 2nd run of ProtoDUNE at CERN. Continue to perform integration tests with the cold boxes at SURF prior to the insertion of the APAs inside the cryostat. Perform global noise measurements after the APA insertion inside the cryostat, prior to the TCO closure. Perform global noise measurements including all LAr instrumentation prior to start filling the cryostat. Maintain enough flexibility in the connection of shielding of cables on top of the cryostat. | ​Depending on when the problem is observed, apply any hardware fixes that are required. Most probably these will not be on the TPC electronics side, but rather on other detector components (HV, PDS, or LAr instrumentation). The worse possible scenario is the one that requires a redesign of the WIB to include more powerful FPGAs where noise filtering can be performed. |  | 3 (M) | 2 (M) | 2 (M) | 2 (Medium) | 783.3333 | 6 | 235 | 1.8 | 2024-01-13 13:02 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-017 | LBNF / DUNE | Material Handling Damage in S Cavern Warehouse | ​Risk covers the cost and schedule impact of a incident in material handling during the course of warehousing in the South Cavern. | Threat | Technical Risk |  | Patrick L. Weber | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft | 2024-03-01 | 2026-12-01 | Installation of all components in Detector Module 1 | 15% | 0 (?) - Not yet defined | 3-point - triangular | 5 | 100 | 1000 | 3-point - triangular | 0 | 0.5 | 2 | Installation of cold membrane installation of detector​ 1 | ​The estimates are an attempt to quanitfy the cost and schedule impact of an incident during increrased handling required for warehousing in the South Cavern. If these were handled by an esternal warehouse contract, the risks would be borne by the warehousing contractor. | 1 - Rough guess | ​Mishandling of items during management of warehouse. | Planning of warehouse space and required procedures along with training for employees.​ |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 368.3333 | 0.83 | 55.3 | 0.1245 | 2022-08-10 08:34 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-018 | LBNF / DUNE | Temporary Warehousing if S Cavern is unavailable for warehousing | ​This risk captures the cost of additional warehousing if the South Cavern is insufficient. | Threat | Technical Risk |  | Patrick L. Weber | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft | 2024-03-01 | 2028-12-01 | Warehouse space no longer required.​ | 10% | 0 (?) - Not yet defined | 3-point - triangular | 5 | 30 | 400 | 1-point - single value |  |  |  | ​Installation of warm structure Installation of cold membrane Installation of detector | The costs attempt to capture the cost of contracting for additional warehousing space in the event that the South Cavern provides insufficient space or is unavailable and additional warehousing contracts must be placed.​ | - Not yet defined - | ​Unavailability of the South Cavern or insufficient space | ​Management of the international logistics chain will limit the peak requirements. |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 145 | 0 | 14.5 | 0 | 2022-08-10 08:34 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-155 | LBNF / DUNE | FS Cryo requires full time Project Management | I​f FS Cryo requires full time Project Management then the current single NS and FS cryo PM will return full time as Far Site Cryogenics PM and resources will need to be added. If this risk (RT-131-FCR-155) is realized, RT-131-NCR-011 is also realized. | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​Completion of testing and commissioning of Near Site LAr Cryogenics. | 30% | 0 (N) - negligible technical impact | 1-point - single value |  | 629 |  | 1-point - single value |  |  |  | ​131.01.02.03.04.01, 131.01.03.04​(Related to RT-131-NCR-011). | The Far SitePM is currently listed as 0.8 FTE of Senior Engineer (with the balance of 0.2 FTE assigned as Near Site PM). A Senior engineer costs ~$370k/year fully burdened. The cost impact is 0.2 FTE of a Senior Engineer for 8.5 yerars (CY2021-mid CY2029): $629k. | 3 - Solid estimate | Far Site Cryogenics PM work more demanding and requires full attention of PM. Near Site Cryogenics PM work more demanding and requires dedicated PM. | ​​Surrounds Far Site Cryo PM with capable resources and progressively increase their responsibilities.​ |  |  | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 629 | 0 | 188.7 | 0 | 2022-08-10 08:27 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-156 | LBNF / DUNE | FS Cryo requires full time Lead Cryo Engineer | I​f FS Cryo requires full time Lead Cryo Engineer, then the current single NS and FS cryo Lead Cryo Engineer will return full time as Far Site Cryogenics Lead Cryo Engineer and resources will need to be added. If this risk (RT-131-FCR-156) is realized, RT-131-NCR-012 is also realized. | Threat | Management Risk |  |  | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​Completion of testing and commissioning of Near Site Cryogenics. | 30% | 0 (N) - negligible technical impact | 1-point - single value |  | 629 |  | 1-point - single value |  |  |  | ​131.01.02.03.04.01, 131.01.03.04 (If this risk happens, this once also happens: RT-131-NCR-012.) | The Far Site Cryo Lead Cryo Engineer is currently listed as 0.8 FTE of Senior Engineer (with the balance of 0.2 FTE assigned as Near Site Cryo Lead Cryo Engineer). A Senior engineer costs ~$370k/year fully burdened. The cost impact is 0.2 FTE of a Senior Engineer for 8.5 yerars (CY2021- mid CY2029): $629k. | 3 - Solid estimate | Far Site Cryogenics Lead Cryo Engineer work more demanding and requires full attention of Lead Cryo Engineer. Near Site Cryogenics Lead Cryo Engineer work more demanding and requires dedicatedLead Cryo Engineer. | Surrounds Far Site CryoLead Cryo Engineer with capable resources and progressively increase their responsibilities. |  |  | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 629 | 0 | 188.7 | 0 | 2022-08-10 08:27 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-212 | LBNF / DUNE | [FD-CE] Single source vendor for TPC electronics components | ​If one of the single source vendors fails to deliver the components then an alternative vendor has to be found, which could entail a delay in the installation schedule and in the commissioning of the detector for operations. | Threat | External Risk | YES | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2020-04-06 | 2025-10-03 | ​This risk can be closed when all the procurements for the parts for which we are likely to have a single vendor (ASICs, cold cables, power supplies) are completed and a sufficient number of spares has been procured. | 5% | 0 (N) - negligible technical impact | 2-point - flat range | 800 |  | 6300 | 2-point - flat range | 8 |  | 16 | Risk hook: 13122.2004.133.330 --> RT-131-FDC-FD-212 --> 13122.2004.133.390 | Losing access to vendor (for ColdADC/COLDATA) implies redoing the masks, engineering time, additional prototypes and testing. This will take approx. 1 year delay and an additional cost = 0.5M (mask) + 100k + 200k = 0.8M (min cost impact). If we lose access to Samtec and have to purchase signal cables from GORE. The additional cost of the signal cable is $3.3M. Total maximum additional cost for FD1 is = $4.1M. For FD2 we assume the risk is mostly the additional cost to purchase the GORE signal cable ($2.2M). The maximum cost impact is the sum of FD1 and FD2 $4.1M + $2.2M = $6.3M.​ | 2 - Reasonable estimate | ​There are three areas for which the TPC electronics project is likely to proceed with a single vendor: the fabrication of ASICs, the cables used to transport clock and controls top the FEMBs and to read out the data from the FEMBs, and the power supplies. If the selected vendor in one of these areas cannot deliver the parts required for the DUNE project, we may have to select a differet vendor, a process that may require a new design for some components and re-certification of detector parts in other cases. The companies we are using in all cases are very well established companies and the likelihood of such a problem taking place is very small. | One mitigation strategy is to purchase all the ASICs once we are convinced of the validity of the design. In the case of cold cables the only mitigation strategy is to qualify additional vendors. This was already tried in the past (without success) with a second company (Gore) in addition to Samtec. ​The final case of a single vendor is that of the low voltage power supplies and the bias voltage power supplies. For the second ones finding an alternative vendor to the preferred one is easy, which is not the case for the first one. We are nevertheless going to investigate alternative vendors. and again, purchasing all the component once the design is finalized is another risk mitigation strategy. | If a given ASIC fabrication process is no longer available it may be preferrable to use a completely different design rather than porting the design to a different fabrication process, as this could take 1-2 years overall (including fabricating and testing prototypes). In the case of cold cables and power supplies we will hopefully have qualified a second vendor and we would be to switch to that second vendor. |  | 1 (VL) | 2 (M) | 3 (H) | 2 (Medium) | 3550 | 12 | 177.5 | 0.6 | 2024-01-13 13:01 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-072 | LBNF / DUNE | FD2 BDE Replacing MiniSAS with SAMTEC cables | In the recent CRP6 cold box test, two out of 24 FEMBs failed to respond to commands issued by the warm electronics. The problem was traced to the connection between the MiniSAS cable and the Frontend Motherboard (FEMB). Similar connection issue was also observed by the SBND experiment, which also uses the MiniSAS cable. ​If the MiniSAS cables are shown to be unreliable to be used for the FD2 bottom CRPs, we will replace the MiniSAS with SAMTEC cables. The SAMTEC cables have been used for FD1 TPC Electronics and have undergone extensive testing in ProtoDUNE-I and will also be tested in the upcoming ProtoDUNE-II-HD run. | Threat | Technical Risk | NO | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Proposed | 1 - draft | 2024-01-10 | 2024-12-31 | ​The new FD2 FEMB connector and cable strain relief modification will be tested in the spring of 2024. If the test results are favorable, this risk can then be closed. | 20% | 1 (L) - somewhat substandard | 1-point - single value |  | 500 |  | 1-point - single value |  | 3 |  | Risk Hook: 13122.PP92250 --> RT-131-FDC-FD2-072​ --> 13122.OBMS92250 | ​The cost impact of switching to SAMTEC cable is based on FY24 vendor quote. The additional cost of procuring SAMTEC instead of MiniSAS cables is about $500K. The schedule impact factors in the time needed to prototype SAMTEC cables and also the additional lead time to fabricate the cables. The delay is estimated on the order of 3 months. | 2 - Reasonable estimate | ​If the test of the FD2 FEMB modification does not meet our expectation, that will trigger this risk. | ​We are modifying the connector and cable strain relief design on the Frontend motherboards to improve the reliability of the connection. We will also test the design modification to verify the inprovement. | ​If the risk is realized, we will purchase a small quantity of the 2.5 m SAMTEC cables and modify the patch panels and test it on CRP#6. After we verified the performance, we will proceed with the order for the SAMTEC cables. |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 500 | 3 | 100 | 0.6 | 2024-01-09 17:30 | Cheng-Ju Stephen Lin | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-259 | LBNF / DUNE | FD1 HV Resistive Kapton film sole source and may be out of production or cost increase | ​If the Kapton source goes out of production or increases cost, then the change in cost and schedule jeopardizes the cathode delivery. | Threat | External Risk |  | Sarah Lockwitz | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 0 - obsolete |  |  | ​The risk can be closed once the Kapton is bought and sufficient spares are made. | 20% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 2-point - flat range | 0 |  | 6 | ​The cathode fabrication would be impacted. | Schedule impact is a rough guess | 1 - Rough guess |  | ​Search for an alternative source or purchase early. A survey of vendors has been initiated. Alternative sources exist, but not production ready |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 3 | 0 | 0.6 | 2023-01-23 16:37 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-260 | LBNF / DUNE | [FD1-HV] Resistive panel lamination factory may be out of business | ​If the resistive lamination factory is unable to laminate the resistive fillm on the cathode panels, it jeopardizes fabrication of the cathode. | Threat | External Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2023-08-16 | 2024-05-01 | ​The risk can be closed once the needed panels are laminated. | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 3 | 13122.A13185 R panel QC inspection #1 - ANL​ | The resistive panel production is in CERN scope so no US cost impact. Schedule impact based on delay (depening on when we know the problem) in setting up alternative vendor and establishing contract with vendors. | 1 - Rough guess | ​current lamination source is out of business | The alternative source associated with RT-131-FDC-FD-226 is also a replacement for our current resistive panel fabricator. They produce FR4 sheets with resistive outer skin, which can replace the resistive film laminated FR4 panels. | ​Use alternative source from RT-131-FDC-FD-226 |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 1.5 | 0 | 0.15 | 2023-02-01 15:33 | Jill Dornfeld | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-077 | LBNF / DUNE | [FD2] ProtoDUNE 2 Operation Reveals Cathode Module Problem | If issues are encountered in operating ProtoDUNE2-VD that imply significant problems for operation of photon detector modules on the cathode in FD2, then it may be necessary to move up to all 320 cathode-mount modules to membrane mount positions.​ | Threat | Technical Risk | NO | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-01-01 | 2024-12-31 | ​2 months following start of FD2 ProtoDUNE 2 operations | 5% | 2 (M) - significantly substandard | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 2 | 13124.Z401346 ---> RT-131-FDC-FD2-077 ---> 13124.Z401354 | ​Minimal changes would be required to shift from the existing cathode mount design for half the PDS to the existing membrane mount for all modules. The following assumptions are included in the estimate: Problems occur during ProtoDUNE 2 operations which demonstrate that the strongly favored cathode mount baseline is not possible.Issue is discovered EARLY in ProtoDUNE 2 running, BEFORE PRRs and ordering of cathode-specific components.Module re-design is not required. Simple change from existing cathode-mount to membrane mount module.US cost changes essentially zero: Cathode and membrane modules cost nearly the sameMembrane cold electronics costs can be covered by cathode cold electronics savingsCost comparison between per-module (avg) membrane cable production is less expensive than fiber harness productionThe cost of the support structure is a non-US item, so to first order would not be covered in the risk register. If we need to double the number of mounts, however, the money would have to be found somewhere. The cost is covered by the savings realized from requiring ¼ fewer dichroic filters in this caseWe will need additional mesh panels if we make this change. This can also be also reasonably be covered from filter window savings. | 2 - Reasonable estimate | ​The risk is realized if running in ProtoDUNE 2 VD demonstrates insurmountable problems operating the cathode mount modules. | ​CERN Cold box testing. HV testing at Fermilab. ProtoDUNE 2-VD preparations and operation. | ​Move some or all of the 320 cathode mount modules to the membrane mount region. |  | 1 (VL) | 0 (N) | 0 (N) | 1 (Low) | 0 | 1 | 0 | 0.05 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-270 | LBNF / DUNE | Cost of CERN's deliverables exceeds current budget allocation | ​If the cost of CERN's deliverables exceeds the current budget allocation, then the lack of some delieverables jeopardizes the HVS fabrication and installation. | Threat | External Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​The risk can be retired once CERN's deliverables are purchased. | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 100 |  | 1-point - single value |  | 0 |  | ​Cathode production, profiles, and power supplies. |  | - Not yet defined - |  | ​Refine cost estimate and explore value engineering options. |  |  | 4 (H) | 0 (N) | 0 (N) | 0 (Negligible) | 100 | 0 | 50 | 0 | 2022-08-10 08:33 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-280 | LBNF / DUNE | Cathode HV power supply is a sole source | ​If the current HV power supply company cannot deliver the specified product, the lack of alternatives jeopardizes the requirements being met on the cathode power side (e.g. noise specifications) | Threat |  |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​Power supply delivered and specifications met. | 10% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 1-point - single value |  | 0 |  |  | ​The cost impact is a very rough guess at the cost of extra filtering needed if another power supply is used. | - Not yet defined - |  | ​So far, additional vendors have not been found that can meet the ripple specification; we will continue to look. | ​The filtering can be increased if another power supply must be used. |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0 | 0 | 0 | 2022-08-10 08:34 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-261 | LBNF / DUNE | FD1 PD SiPM Test Lot Fabrication Delayed (Intl) | ​IF Fabrication of prototype photosensor lots is delayed at vendors THEN this could lead to delays in testing and selection of candidates for ProtoDUNE module fabrication | Threat | External Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved | 2020-10-01 | 2021-09-01 | ​Delivery of photosensor batches | 30% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 2-point - flat range | 2 |  | 6 | 13122.A15554 (test of first 10 modules for ProtoDUNE-2)​ | ​Risk based of sample SiPM fabrication, both from pre-fabricated semiconductor wafers (~2 months) or fincluding semiconductor wafer fabrication (~6 months). Including testing. | 2 - Reasonable estimate |  | ​Prototypes procured from two vendors (Hamamatsu and FBK), and in multiple batches. Close interaction with and supervision of vendors.​ |  |  | 3 (M) | 0 (N) | 1 (L) | 1 (Low) | 0 | 4 | 0 | 1.2 | 2023-01-23 16:38 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-262 | LBNF / DUNE | FD1 PD Additional cold amplifier design respin required (Intl) | ​IF Evaluation of prototype cold amplifier and cable prototypes exposes design flaws THEN additional design respin may be required including prototype development and testing | Threat | External Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2020-10-01 | 2021-07-01 | ​Completion of FDR | 30% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 2-point - flat range | 2 |  | 4 | 13122.A15444 (international contribution to module assembly and QA/QC for ProtoDUNE-2)​​ | ​Risk based on design and fabrication times for early prototype cold electronics and testing | 2 - Reasonable estimate |  | ​Early fabrication and testing of prototype amplifiers, warm and cryogenically. |  |  | 3 (M) | 0 (N) | 1 (L) | 1 (Low) | 0 | 3 | 0 | 0.9 | 2023-01-23 16:37 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-263 | LBNF / DUNE | FD1 PD Dichroic filter instability at cryogenic temeprature | ​IF Dichroic layers of the filters show instabilities when going to cryogenic temperature during ProtoDUNE 2 validation THEN additional prototype development may be required. | Threat | External Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2020-10-01 | 2021-07-01 | ​FDR | 20% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 2-point - flat range | 2 |  | 4 | ​13122.A15444 (international contribution to module assembly and QA/QC for ProtoDUNE-2)​​ | ​Estimate based on the fabrication time of new batches of filters with few different substrates and clening procedures | 2 - Reasonable estimate |  | ​Improvement of the cleaning process at the production site and optimization of the evaporation process. In weekly contact with vendors doing preliminary evaluation of their work |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 3 | 0 | 0.6 | 2023-01-23 16:37 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-264 | LBNF / DUNE | FD1 PD Coating instability at cryogenic temeprature during ProtoDUNE 2 Validation | ​IF the pTP layer is unstable at cryogenic temperature and detaches from the substrate due to differential mechanical stresses THEN additional process development and prototyping may be required. | Threat | External Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2020-10-01 | 2021-07-01 | ​Completion of FDR | 20% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 2-point - flat range | 2 |  | 4 | 13122.A15444 (international contribution to module assembly and QA/QC for ProtoDUNE-2)​​ ​ | ​Estimate based on the time needed to validate new cleaning procedures | 2 - Reasonable estimate |  | ​Extensive test at UNICAMP and optimization of the cleaning procedure fo the filters and of the coating process​. Expanded personnel resources in Brazil to assist with this work. |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 3 | 0 | 0.6 | 2023-01-23 16:37 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-265 | LBNF / DUNE | FD1 PD WLS plate instable at cryogenic temeprature | ​ IF WLS plates show cracking issues when going at low temperatre which impact the efficiency of light collection THEN addirtional prototypes and procedure testing may be required | Threat | External Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2020-10-01 | 2021-07-01 | ​Completion of FDR | 20% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 2-point - flat range | 2 |  | 4 | ​13122.A15444 (international contribution to module assembly and QA/QC for ProtoDUNE-2)​​ | ​Estimated based on the fabrication time of WLS plates and testing duration | 2 - Reasonable estimate |  | ​Extensive test at the SPPD Consortium. Two producers/vendors selected. ​ |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 3 | 0 | 0.6 | 2023-01-23 16:38 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-266 | LBNF / DUNE | FD1 PD Production of mechanical components is delayed (ProtoDUNE 2) | ​If the production of the mechanical components of the modules is delayed or interrupted at production site, then this could lead to delays in module fabrication | Threat | External Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2021-07-01 | 2022-01-31 | ​Completion of ProtoDUNE 2 Module component fabrication | 20% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 2-point - flat range | 1 |  | 3 | ​​​13122.A15442 (ProtoDUNE-2 frame mechanicals)​ | ​Estimate based on vendor performance in sample fabrication tests. | 2 - Reasonable estimate |  | ​Early fabrication of the components. Two producers selcted to produce the components in parallel​ |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 2 | 0 | 0.4 | 2023-01-23 16:37 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-267 | LBNF / DUNE | [FD1-PD] Daphne firmware development delay | ​IF delays in DAPHNE firmware development occur THEN DAPHNE availability for ProtoDUNE 2 readout may be delayed | Threat | External Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved | 2020-10-01 | 2022-01-01 | ​Final checkout of DAPHNE firmware | 30% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 2-point - flat range | 2 |  | 4 | ​13122.A.12492 (ProtoDUNE 2 initial running) | ​DAPHNE firmware development has been delayed by COVID and issues with PD/DAQ communications speed requirements. Initial testing of firmware has begun, but tests in the VST at CERN and in ICEBERG will provide primary validation. Problems may arrise resulting in delays in firmware availability for testing. | 2 - Reasonable estimate |  | ​Extensive testing in Latin America (Paraguay, Colombia, Peru). Additional resources have been identified in Colombia (and possibly at Kansas State University in the US) to assist in this effort. Extensive testing in data transfer tests in Paraguay, in VST at CERN, and at ICEBERG. |  |  | 3 (M) | 0 (N) | 1 (L) | 1 (Low) | 0 | 3 | 0 | 0.9 | 2023-01-31 09:34 | Mohammed Elrafih | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-268 | LBNF / DUNE | [FD1-APA] Delay in UK APA production before 2026 | ​If there are delays in UK APA production then the installation of the APAs will be delayed. | Threat | External Risk | YES | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-01-02 | 2027-06-11 | This risk will be closed in Spring 2027 when the UK has completed the delivery of the APAs to SURF | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 6 | Risk hook: 13122.02.A139388 --> RT-131-FDC-FD-268 --> 13141.A6200 | ​The first 100 UK APAs, approximately 80% of their total production, will finish by the middle of 2026 The maximum delay introduced in the schedule is 6 months, that corresponds to the point where the project will decide that the threshold and objective KPPs will be met by using FD2 instead of FD1. If the APAs are delayed by more than 6 months, then the installation of FD2 will be completed ahead of that of FD1. | 2 - Reasonable estimate | This risk will be realized at the end of 2025 if the UK production rate is insufficient to deliver their APAs before the end of installation. | A fifth winder was sent to the UK from the US to increase their production capacity. The UK is also looking to add a second shift each day to improve the production rate. | If the UK is behind by only a small number of APAs it may be possible for the US to assemble additional APAs using UK provided components. If the deficit is larger the ordering of the FD1 and FD2 installation could be swapped. |  | 4 (H) | 0 (N) | 1 (L) | 2 (Medium) | 0 | 3 | 0 | 1.5 | 2024-01-13 12:55 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-116 | LBNF / DUNE | [FD2-PDS] WLS plates production delayed | ​If WLS plate deliveries are delayed then FD2 PDS detector assembly could be delayed. | Threat | External Risk | NO | Peter Shanahan | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-05-15 | 2025-05-29 | ​This risk may be closed when all WLS filter plates are delivered. | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 1 |  | 4 | Risk hook: 13124.Z400564 ---> RT-131-FDC-FD2-116 --> 13124.Z400592 | Based on production times and delivery reliability during FD2 ProtoDUNE 2 and an engineering estimate of reasonable producton delays. | 1 - Rough guess | ​Delays in WLS plates may occur due to supply chain issues or other manufacturer delays. | ​While or basiline vendor (Glass to Power, Italy) has been selected as out optimum vendor, other vendors have been tested and could be used if necessary. | ​Accelerate acceptance testing and module fabrication speed (possibly involving multiple assembly shifts or additional assembly sites) to recover lost time. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 2.5 | 0 | 0.25 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-117 | LBNF / DUNE | [FD2-PDS] SiPM delivery delayed | ​If SiPM production and testing are delayed then FD2 PDS detector fabrication may be delayed | Threat | External Risk | NO | Peter Shanahan | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-03-08 | 2025-03-21 | ​Risk may be closed when all SiPMs are delivered | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 1 |  | 4 | Risk hook: 13124.Z400640 ---> RT-131-FDC-FD2-117 ---> 13124.Z400684 | Estimate based on experience with FD1 SiPMs by the same vendors and testing experience. | 2 - Reasonable estimate | ​This risk would be triggered if manufacturer delays due to supply chain, packaging or other causes led to a delay in SiPM delivery | ​We have adapted a two-vendor (Hamamatsu and FBK) for SiPMs with the expectation taht delays at one source will not necessarily lead to delays at the other, allowing detector fabrication to continue. | ​Accelerate SiPM acceptance testing and detector assembly operations to recover lost time. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 2.5 | 0 | 0.25 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-256 | LBNF / DUNE | [DAQ] FD1 FD2 DAQ Insufficient scientific effort in US institutions on DAQ development | ​If no support is available for the scientists from US institutions participating in the DAQ development, there could be a delay in the availability of the DAQ for the integration and installation process, which would then impact the achievement of the DUNE KPPs. | Threat | External Risk |  | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2021-01-01 | 2026-10-15 | ​This risk can be closed when all the deliverables provided by scientists in US institutions that are relevant for the DAQ development necessary for the integration and installation process have been completed. | 30% | 1 (L) - somewhat substandard | 2-point - flat range | 0 |  | 21.5 | 2-point - flat range | 0 |  | 3 | Risk hook: 13122.A366413--> RT-131-FDC-FD-256 --> 13122.A366561 ​ ​​ | The time estimate is based on a generic time delay, under the assumption that other DAQ collaborators not from the US take over the tasks that were being done by personnel from US institutions (Columbia, Penn, Minnesota-Duluth). The cost estimate assumes 1 FTE of costed DAQ personnel over the expectred time delay. | 1 - Rough guess | ​Personnel from US institutions (Columbia, Penn, Minnesota-Duluth) are working on the DUNE DAQ, with support coming from the base grants of the institutions. If this personnel is not available for any reason (lack of institutional support, personnel turnaround), there could be a delay in the availability of the DAQ for integration and installation at SURF. | ​Identify alternative institutions that can take over some of the software/firmware tasks that are currently a responsibility of the US scientists. | ​If funding for the US institutions participating on the DAQ development is not available, identify alternative institutions that can take over the responsibility for these tasks. Identify effort from Fermilab that can be supported to further development efforts. |  | 3 (M) | 0 (N) | 1 (L) | 1 (Low) | 10.75 | 1.5 | 3.2 | 0.45 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-118 | LBNF / DUNE | [FD2-PDS] Signal over Fiber (SoF) transmitter kit delivery delayed | ​If SoF transmitter kit delivery to US cold electronics site is delayed then fabrication of FD2 PDS cold electronics fabrication will be delayed, leading to module fabrication delays. | Threat | External Risk | NO | Peter Shanahan | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-10-03 | 2025-09-11 | ​Risk can be closed when all SoF transmitter kits are delivered to US cathode cole electronics fabrication facility (UCSB) | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 1 |  | 3 | ​Risk hook: 13124.Z400672 --> RT-131-FDC-FD2-118 --> 13124.Z400710 | ​Estimate is engineernig estiamte of potential delays in SoF tansmitter kits based on Module 0 fabrication experience and current vendor quotations for custom diode lasers. | 2 - Reasonable estimate | ​This risk would be triggered by delays in fabrication of SoF transmitter kits in France due to manufacturer delays or negative outcomes of QC testing, or shipping delays to US assembly sites. | ​Continued close coordination with component suppliers to ensure high quality and mitigate against prodction delays. Close coordination of shipping plans at both sides of the logistics path. | ​Identify possible alternate vendors and plan to be able to accelerate testing of assemblies to recover lost time. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 2 | 0 | 0.2 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-119 | LBNF / DUNE | [FD2-PDS] Delays in warm electronics fabrication/testing | ​If assembly and testing of warm electronics (DAPHNE) modules is delayed then detector installation activities at SURF may be delayed | Threat | External Risk | NO | Peter Shanahan | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-12-30 | 2026-06-29 | ​All warm electronics modules delivered to SURF | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 1 |  | 4 | Risk hook: 13124.Z401632 ---> RT-131-FDC-FD2-119 ---> 13124.Z401634 | ​Estimate is based on typical delays experienced in custon electronics assembly and testing in the non-COVID period. | 2 - Reasonable estimate | ​Delays in DAPHNE module fabrication due to supply chain or other manufacturer delays, or due to testing delays | ​Begin procurement of key long-lead time items as early as possible. Learn reliability lessons for component and fabrication houses from FD1 DAPHNE production. | ​Accelerate testing and installation schedule as possible. Use spare DAPHNE modules from FD1 to allow detector installation testing to proceed while FD2 DAPHNE modules are fabricated. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 2.5 | 0 | 0.25 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-258 | LBNF / DUNE | FD1 DAQ Replacement of a member of the DAQ core team at Fermilab | ​If one of the members of the DAQ core team at Fermilab stops working on DUNE, that person needs to be replaced which may entail a delay in the availability of the DAQ for integration and installation activities at SURF, which then causes a delay in the achievement of the KPPs. | Threat | Technical Risk |  | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved | 2021-01-01 | 2026-10-15 | ​Completion of the DAQ installation and commissioning for the integration and installation activities at SURF | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 100 | 2-point - flat range | 0 |  | 4 | ​13122.2004.161.350 | ​Assume a delay of a few months if a new person needs to be trained without overlap with the previous member of the DAQ core team at Fermilab. If there is sufficient notice from the person leaving the DAQ CORE team at Fermilab, then a succession plan can be put in place where the old and new person are both paid by Fermilab for the training period. | 1 - Rough guess | ​This risk covers the possibility that one of the members of the DAQ CORE team at Fermilab needs to be replaced. The DAQ CORE team at Fermilab is responsible for the DAQ firmware/software installation, for the operations of the DAQ computers and of the networking at SURF and between SURF and Fermilab, These activities are a responsibility of the host laboratory and cannot be taken over by other members of the collaboration. | ​Put in place succession plans for the personnel of the DAQ CORE team. Train scientific personnel at Fermilab to provide backup for these tasks. | ​If the risk is realised with the person leaving giving sufficient notice, realise the succession plan and train a new expert with overlap with the previous one. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 50 | 2 | 5 | 0.2 | 2023-01-23 16:36 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-013 | LBNF / DUNE | [I&I] Goods Damaged during Shipment | If goods are damaged during shipment and insufficient spares are on hand, then installation schedule may be delayed because the installation of cryostat 1, cryostat 2, detector 1, detector 2 and cryogenics are dependent on essential components items being on hand. ​ | Threat | Management Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-08-01 | 2028-12-31 | ​All FS shipments complete | 10% | 0 (N) - negligible technical impact | 3-point - triangular | 200 | 500 | 5000 | 3-point - triangular | 3 | 6 | 18 | Risk hook: 13141.A2580MS --> RT-131-FDC-FI-013 -->13141.A3340 | ​There are approximately 1500 containers that will be shipped to South Dakota for both detectors. The risk of total loss of a container is 0.001% based on shipping statistics, giving a container loss risk of 1.5%. Partial damage is not tracked to this level. This risk is small compered to general damage during shipping cause by poor packaging and rough handling. Schedule impact includes consideration of time to acquire replacement items. The cost impact includes the repair of the components and the labor involved. | 1 - Rough guess |  | ​Utilize freight forwarder. Provide shipping guidance to all LBNF/DUNE teams. Adequate inventory. QC travelers. | ​acquire replacement materials |  | 2 (L) | 2 (M) | 3 (H) | 2 (Medium) | 1900 | 9 | 190 | 0.9 | 2024-01-13 12:30 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-165 | LBNF / DUNE | Unicamp not funded for Phase 2 activities | ​If Unicamp is not funded for Phase 2 activities, then they will not be able to deliver the Argon purification and regeneration systems for Detectors #1 and #2, and the LAr circulation systems for Detector #1 and #2 and the Argon Condensers System for Detector #2. The project will be missing key components to be able to circulate and purify the Argon for Detector #1 and #2. | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft | 2021-10-01 |  | ​Unicamp is funded for Phase 2 activities. Unicamp delivers equipment to SURF. Equipment is installed and tested. | 20% | 0 (N) - negligible technical impact | 3-point - triangular |  |  |  | 3-point - triangular | 0 | 9 | 12 |  | The minimum cost impact is 0: Unicampo is fully funded and delivers all equipment. The most likely cost impact is that they deliver only the equipment for Detector #1. ​The maximum cost impact is that Unicamp is not funded at all and no equipment is delivered. The minimum schedule impact is 0:Unicampo is fully funded and delivers all equipment. The most likely cost impact is that we have work to do to find alternative ways of delivering equipment for Detector #2. This is a slow process and it takes a while to engage with potential other partners. If DOE ends up funding the missing scope, the schedue impact is likely smaller. The max schedule impact is that we have to find alternative ways of delivering equipment for Detector #1 and #2. This is a slow process and it takes a while to engage with potential other partners. If DOE ends up funding the missing scope, the schedue impact is likely smaller. | 2 - Reasonable estimate | Phase 1 preliminary studies unsuccessful. Brazilian economy (Sao Paulo state in particular) not doing well and Government decides to not fully fund Unicamp for these activities. | ​FRA to support Unicamp during Phae 1 activities. FRA to ensure that Unicamp's setup is adequate for the preliminary testing and R&D that they want to do. |  |  | 2 (L) | 0 (N) | 2 (M) | 2 (Medium) | 0 | 7 | 0 | 1.4 | 2022-08-10 08:28 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-191 | LBNF / DUNE | [FD2] Top drift electronics commercial components become obsolete | ​If the commercial off-the-shelf electronic components used for the readout of the top CRPs in parts of the Top Drift Electronics deliverables become obsolete, a further design and prototyping iteration may be necessary, delaying the availability of such components for installation in FD2​ | Threat | Technical Risk | NO | Steve Kettell | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-08-01 | 2027-12-31 | ​This risk can be closed when all the parts (including spares) for the top drift electronics have been delivered to SURF | 5% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 6 | Risk hook: ​ 13124.A117 ---> RT-131-FDC-FD2-191 ---> 13124.A118 | ​The components that are most likely to become obsolete are the FPGAs and the transceivers. We are assuming that the redesign of the boards for the TDE is relatively simple and that the schedule impact is minot. The cost impact is zero because the TDE is inrenational scope | 1 - Rough guess | ​This risk is realized when at the beginning of production it is realized that there isn't a sufficient stock of components for building the detector components for FD2 and the relevant spares | Follow the market, anticipate the procurement of critical components that hard to find and to replace in the design​ | ​If the risk is realized proceed quickly with the redesign |  | 1 (VL) | 0 (N) | 1 (L) | 1 (Low) | 0 | 3 | 0 | 0.15 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-160 | LBNF / DUNE | [PM] Partner-supplied items are delayed or damaged during shipping | ​If equipment is damaged or delayed during delivery, storage, and transport, rework may be required and assembly could be delayed affecting critical path schedule.​ | Threat | External Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2028-02-28 | 2030-09-30 | ​Items delivered to SURF and inspected prior to acceptance. Verification that skids are transportable down the shaft upon arrival to LBNF storage and do not require disassembly. Items delivered to place of installation and inspected for damage during transportation on site at SURF. | 14% | 1 (L) - somewhat substandard | 3-point - triangular | 0 | 314 | 653 | 3-point - triangular | 1 | 2 | 3.5 | Split total probability equally between two risk hooks: 1) 131123.01.01.586MS --> RT-131-FDC-PM-160-A --> 131123.04.04.03.17 2) 131123.01.01.587MS --> RT-131-FDC-PM-160-B --> 131123.04.04.04.47 The risks PM-160-A and PM-160-B are uncorrelated | If items are coming from overseas the delays could easily add up to 1-2 months, depending on weather conditions, customs, etc. If a damage occured, materials might need to be ordered and rework done. This can easily take 4-6 weeks, depending on the severity and availability of components.The vendor and partner will have to be contacted to establish a suitable course of action. Depending on the timing, the partner may not be present at the site already. The schedule impact would be: - Min --> 1 mo delay. - Most likely --> 1 mo delay + 0.5 mo purchase materials + 0.5 mo rework. - Max --> 2 mo delay + 0.75 mopurchase materials + 0.75 mo rework. The cost impact would be the rework of the components and the labor involved. For materials we assumed: - Min --> 0 (just delay). - Most likely --> 10% of value of a purification skid, likely the single most expensive item being shipped ($290k). - Max --> 20% of value of a purification skid ($580k). For labor: - Min --> 0 (just delay). - Most likely --> 2 weeks of 2 techs ($24k). - Max --> 6 weeks of 2 techs ($73k). Techs at $110/hr (fully burdened) for 50 hr/week. The probability is estimated using the statistics on accidents involving large trucks and resulting in property damage (https://www.fmcsa.dot.gov/safety/data-and-statistics/trends-table-10-large-truck-property-damage-only-pdo-crash-statistics-6, this is 1.38e-6/mile) multiplied by an estimate of the miles traveled by the trucks transporting IKC cryogenics equipment. We expect at least 100 deliveries, traveling an average of 1,000 m. That comes down to 14%.​ | 2 - Reasonable estimate | Logistics issue during handling and/or transport. Equipment larger than expected (e.g. requires disassembly prior to transport underground). Poor QC during fabrication. Poor Factory Acceptance tests prior to shipment. Failed dimensional verification. | Follow instructions from Logistics Manager to ensure adequate care of handling and shipping. Properly pack the items inside suitable crates. Verify credentials of shipping agent/broker. Verify acceptable QA plan for handling and shipping. Appropriate QC during manufacturing. Assist partner as needed with QC process. |  |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 322.3333 | 2.17 | 45.1 | 0.3038 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-161 | LBNF / DUNE | Argon filter media is excessively radioactive | ​If an alternative media is selected for the Argon purification then that media might have higher radioactivity and the detector may be affected. | Threat | Technical Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | Satisfactory measurement of radioactivity of alternative media being considered and verification in actual experiment (ProtoDUNE?) whose performance is known with current media (Cu-0226S). Use current media (Cu-0226S and mol sieve), whose radioactivity level is known and proven. | 30% | 2 (M) - significantly substandard | 1-point - single value |  |  |  | 2-point - flat range | 12 |  | 15 |  | If the radioactivity level is measured after completion of installation and before the equipment is shipped, there is only a potential schedule delay associated with replacing the media with the right one, assuming that the partner bears the cost of purchasing new media. Current manufaturing times for the current media (Cu-0226S) from industrial supplier (BASF). | 2 - Reasonable estimate | ​Unicamp is testing alternate media that they can manufacture in Brazil and may potentially have higher absorption capacity, therefore reducing amoung needed. | ​Measure the radioactivity of the media being considered to ensure they are satisfactory. If so, test the media in a larger facility (ProtoDUNE) to verify no effect on performance of actual Detector. Use the current media (Cu-0226S), whose radioactivity is known and not a problem for DUNE. |  |  | 3 (M) | 0 (N) | 3 (H) | 3 (High) | 0 | 13.5 | 0 | 4.05 | 2022-08-10 08:28 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-051 | LBNF / DUNE | [PM] South Dakota Taxes for I&I Outfitting & Detector Installation Labor | ​If LBNF/DUNE-US project needs to pay contractor excise and SD sales taxes for subcontracted I&I infrastructure outfitting and detector installation labor, then the project budget will be impacted. | Threat | External Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-01-01 | 2028-07-01 | ​resolution of SD tax applicability; all FDC I&I installation work completed | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 734 |  | 1-point - single value |  | 0 |  | Risk hook: 13141.A80030 --> RT-131-FDC-FI-051 --> 13141.A80050 | ​This cost impact includes two elements: (1) SD contractors excise rate (2.04%) applied to 30% of the total value of 131.FDC.05.02, 131.FDC.05.03, 131.FDC.04 = $60m * 30% = $18m, which is an estimate for the material installation work that would be subcontracted to companies. $18m * 2.04% = $367k (2) Rigging, Transport Crew + Survey, anticipated subcontract labor budgeted in 131.FDC.05.01 = $18m * 2.04% = $367k. *Note, coincidentally, each number is $18m. Assumption is that detector installation activities by staff and consortia are not subject to contractors excise tax. Cryogenics (131.FDC.04) and I&I (131.FDC.05) estimates include SD sales taxes. | 2 - Reasonable estimate | ​determination regarding applicability of taxes to LBNF/DUNE FDC activities | ​Fermilab General Counsel has engaged SD-based tax legal experts to advise and resolve applicability. ​ | ​tax to be paid; risk to be realized |  | 4 (H) | 1 (L) | 0 (N) | 2 (Medium) | 734 | 0 | 367 | 0 | 2024-01-13 12:36 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-163 | LBNF / DUNE | Argon purification skid needs to be broken down for transportation down shaft | Argonpurification skids should arrive ready for transportation down the shaft.If one or all need to be transported down the shaft as separate components (vessels, etc.) then there is the potential to damage one of the components and the assembly and commissioning may be delayed. | Threat | Technical Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​Argon purification skids transported to the CUC as skids, not disassembled. Verification that skids are transportable down the shaft upon arrival to LBNF storage. | 20% | 1 (L) - somewhat substandard | 3-point - triangular |  |  |  | 3-point - triangular | 0.25 | 0.5 | 1.5 |  | Purification skids should arrive ready for transportation down the shaft. If they require to be disassembled before being transported down, suitable space and tools would need to be found and items can potentially be damaged during transportation and/or handling. They would also need to be reassembled underground. A minimum schedule impact of 1 week with a most likely of 2 weeks seem appropriate for the circumstances. If a damage occured, materials might need to be ordered and rework done. This can easily take 4-6 weeks, depending on the severity and availability of components. The cost impact would be the rework of the components and the labor involved. For materials we assumed: - Min --> 0 (labor only to disassemble and re-assemble the equipment). - Most likely --> 10% of value of a purification skid. - Max --> 30% of value of a purification skid. For labor: - Min --> 1 week of 2 techs ($xxx). - Most likely --> 2 weeks of 2 techs ($xxx). - Max --> 6 weeks of 2 techs ($xxx). | 1 - Rough guess | ​Argon purification skids larger than expected. Poor Quality Control during fabrication. Poor Factory Acceptance tests prior to shipment. Failed dimensional verification. | ​Appropriate QC during manufacturing. Verify acceptable QA plan for manufacturing. Assist partner as needed with QC process. |  |  | 2 (L) | 0 (N) | 0 (N) | 1 (Low) | 0 | 0.75 | 0 | 0.15 | 2022-08-10 08:28 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-101 | LBNF / DUNE | [I&I] Scope is missing due to poor interface definition at Far Site | If necessary scope is missed within interface definitions at the Far Site, among Detector, Integration, Cryogenics Infrastructure and Conventional Facilities teams, then these scope items will need to be added to the Project to make a functional experiment and achieve the Project deliverables, resulting in additional cost and related schedule. | Threat | Technical Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-10-01 | 2028-06-30 | ​completion of project | 20% | 0 (N) - negligible technical impact | 3-point - triangular | 500 | 2000 | 5000 | 3-point - triangular | 0 | 1 | 3 | Split risk probability equally for two risk hooks: 1) 13141.A80430 --> RT-131-FDC-FI-101-A --> 13141.A80500MS 2) 13141.A82420 --> RT-131-FDC-FI-101-B --> 13141.A85000 The risks FI-101-A and FI-101-B are uncorrelated | ​0.5% of rough cost of all of far site DOE cost = ~3M for high end. Likely not to be major scope item that would require significantly long time. Intended to represent a cumulative cost and schedule impact for the project. Includes interfaces with CF (BSI), Cryogenic infrastructure, and Detector | 1 - Rough guess | ​Insufficient engineering management, communication, and interface definition could mean that some scope is missed. | ​Use systems engineering methodologies to identify and alleviate gaps in scope. Ongoing inter-project interface meetings/discussions to ensure scope alignment and clarity of expectations. ​TOOLS: Integrating 3d models and engineering designs into current models to ensure all parties are on the same page. CAD tools in place and procedure written for periodic model integrations. Getting inter-project agreement in interface dwg for typical FS chamber/cryostat. Creating detailed activities for integration/installation. Periodically revisit interface documents coincident with CAD model updates. | ​evaluate scope gap and resolve issues. |  | 2 (L) | 2 (M) | 1 (L) | 2 (Medium) | 2500 | 1.33 | 500 | 0.266 | 2024-01-13 12:36 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-282 | LBNF / DUNE | [COMP] Hardware Database has not been integrated into operations | ​If the DUNE hardware database is not operational during the Far Detector component construction nor integrated into the Far Detector DAQ, then there would need to be manual configuration of detector components and front end electronics and greater risk of improper configuration of components which would jeopardize the schedule for successfully commissioning the Far Detector and DAQ. | Threat | Technical Risk |  | Michael H Kirby | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2026-01-01 | 2029-03-31 | ​The risk can be closed when the hardware database has been successfully integrated in detector component construction, and the integration of the hardware database into the DAQ configuration has been demonstrated for commissioning of the Far Detector module. | 3% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 3 | Risk hook: 13141.A2580MS --> RT-131-FDC-FD-282 --> 13141.A3340​ | ​The probability is based upon a rough guess of the likelihood that the hardware database would be incomplete or not adequate to meet the needs of configuring the DAQ during far detector commissioning. | 1 - Rough guess | ​Failure for the Computing Consortium Database Working Group to provide interfaces to the hardware database or failure for the interface to meet the needs of the DAQSC Consortium. | ​The Database Working Group has developed a requirements document for the Far Detector Consorium and is currently implementing an instance of a newly development hardware database based upon those requirements. The database will be utilized during the construction, commissioning, and operations of the ProtoDUNE II Single Phase detector to ensure the applicability for DUNE Far Detector. |  |  | 1 (VL) | 0 (N) | 1 (L) | 1 (Low) | 0 | 1.5 | 0 | 0.045 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-283 | LBNF / DUNE | [COMP] Far Detector Event Display not functional | ​If there is not a useful event display available during commissioning of the DUNE Far Detector, then the process of evaluating the DAQ output stream in realtime will be significantly limited and this would jeopardize the successful completion of the Far Detector commissioning. | Threat | Management Risk |  | Michael H Kirby | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2027-01-01 | 2029-03-31 | The risk can be closed when the DUNE Computing Consortium has developed an event display that provides all of the needed functionality for viewing and evaluating some of the DAQ output stream in real time. | 2% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 1 |  | 3 | Risk hook: 13122.01.02.305MS4 --> RT-131-FDC-FD-283 --> 13141.A10540 ​ | ​The probability is based upon experience from previous commissioing of past experiments and the need to develop unexpected capabilities for event displays to understand data problems. The assumption is made that the cost to the project is only a standing army cost from the delay (which is taken into account in a different way). The cost of the development of the event display is not included, because that is off project. | 1 - Rough guess | ​Failure for developed event display to have all needed capabilities during the commissioning of the DUNE Far Detector development so that the commissioning team can identify problems or misconfigurations that would delay successful commissioning or production of high-quality data. | ​Using experience and data from the ProtoDUNE II Single Phase detector, the Computing Consortium will develop an event display that can utilize real-time streams from the Far Detector DAQ to identify known and potential problems. |  |  | 1 (VL) | 0 (N) | 1 (L) | 1 (Low) | 0 | 2 | 0 | 0.04 | 2023-07-06 09:15 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-284 | LBNF / DUNE | [COMP] Data Quality Monitoring Framework is incomplete | ​If the Data Quality Monitoring Framework is not complete at the time of commissioning the Far Detector then the inability to rapidly validate the performance of the Far Detector and the DAQ system jeopardizes the goal of operating and reading out the FD for one week at 50% uptime. | Threat | Management Risk |  | Michael H Kirby | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2026-06-01 | 2027-12-31 | Once a Data Quality Framework has been completed and integrated into the DAQ and data stream with appropriate metrics and alarms for detector performance, this risk can be closed.​ | 1% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 1 |  | Risk hook: 13141.A10730 --> RT-131-FDC-FD-284 --> 13122.01.02.276MS4​ | ​The probability is based upon the experience of ProtoDUNE I Single Phase operations where the Data Quality Monitoring effort was designed and implemented in under 12 months. While the DUNE Far Detector module and DAQ have 25 times greater data volume, the extention of the DQM framework from ProtoDUNE is a tractable problem. The cost impact is purely a standing army cost that is taken into account elsewhere. The development cost of the DQM is off-project. | 2 - Reasonable estimate | ​The failure for a Data Quality Monitoring framework and computing resources to be capable of streaming and analyzing data from a full far detector module during the commissioning of the detector. | ​The Data Quality Monitoring framework is being developed for ProtoDUNE II Single Phase in order to expand the capability in both data volume and metrics measured during operations. This DQM framework will be continued to be developed for larger detectors and more complicated data streams based upon Far Detector simulations. |  |  | 1 (VL) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 1 | 0 | 0.01 | 2023-07-06 09:16 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-021 | LBNF / DUNE | I&I Partner supplied items are delayed or damaged during shipping | ​If equipment is damaged or delayed during delivery, storage, and transport, rework may be required and assembly could be delayed affecting critical path schedule.​​ ​ | Threat | Management Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  | detector #2 installation complete | 10% | 1 (L) - somewhat substandard | 2-point - flat range | 50 |  | 100 | 2-point - flat range | 0.25 | 0.5 | 1 | ​13141.A3340 (begin detector installation in FD1 cryostat)13143.A364838 (begin detector installation in FD2 cryostat) | ​For items coming from overseas the delay could be 1 month, depending on weather conditions, customs, etc. If damage occurs, materials might need to be ordered and repair work performed, requiring 1-4 weeks. The vendor and partner will have to be contacted to establish a suitable course of action. Depending on the timing, the partner may not be present at the site already. The cost impact includes the repair of the components and the labor involved. For materials we assumed: - Min --> 50k - Max --> 15% of value of internal cryogenics ​ | 1 - Rough guess | Logistics issue during handling and/or transport. Poor QC during fabrication. Poor Factory Acceptance tests prior to shipment. Failed dimensional verification. | ​​​​Follow instructions from Logistics Manager to ensure adequate care of handling and shipping. Properly pack the items inside suitable crates. Verify credentials of shipping agent/broker. Verify acceptable QA plan for handling and shipping. Appropriate QC during manufacturing. Assist partner as needed with QC process.​ |  |  | 2 (L) | 0 (N) | 0 (N) | 1 (Low) | 75 | 0.63 | 7.5 | 0.063 | 2023-01-23 16:40 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-022 | LBNF / DUNE | [PM] IKC engineering labor less than planned | ​If the actual IKC engineering labor is less than planned for FDC engineering work, then design completion and procurement activities could be delayed. | Threat | Management Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  | ​all procurement activities complete for FS Cavern Outfitting, FD Installation | 25% | 0 (N) - negligible technical impact | 2-point - flat range | 750 | 0 | 1500 | 2-point - flat range | 0 |  | 4 | 13141.A3620MS (AUP of north cavern) | cost: min: 1 engineer (250) x 3 years = 750k​ max: 2 engineers x 3 years = 1500k schedule: min: time to hire supplemental engineering | 2 - Reasonable estimate | ​IKC from CERN is not available; competing priorities from provider | ​continue to engage CERN engineering resources in ongoing planning; finalize designs as soon as possible and set aside until time to procure material |  |  | 3 (M) | 2 (M) | 1 (L) | 2 (Medium) | 1125 | 2 | 281.3 | 0.5 | 2023-01-31 14:23 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-023 | LBNF / DUNE | [PM] IKC compliance office labor unavailable | ​If the actual Integration PO IKC compliance office labor is less than planned for LBNF/DUNE activities, then design completion and installation activities could be delayed. ​ | Threat | Management Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  | ​all det#1 installation activities complete | 20% | 0 (N) - negligible technical impact | 2-point - flat range | 750 |  | 1500 | 1-point - single value |  | 0 |  | 13122,91,92,CD3NEW (CD3 ESAAB approval, for lack of a better tie point)​ | ​ cost: min: 1 engineer (250) x 3 years = 750k​ max: 2 engineers x 3 years = 1500k | 1 - Rough guess | ​ IKC from CERN is not available; competing priorities from provider | ​ ​continue to engage CERN engineering resources in ongoing planning; finalize designs as soon as possible and set aside until time to procure material​ |  |  | 2 (L) | 2 (M) | 0 (N) | 2 (Medium) | 1125 | 0 | 225 | 0 | 2023-01-31 10:26 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FI-164 | LBNF / DUNE | [I&I] Xenon available from LZ at favorable price | ​If SDSTA supplies Xenon to LBNF/DUNE from LZ at favorable price then the project may save money. | Opportunity | Management Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2029-06-01 |  | ​Agreement reached with SDSTA to supply some or all Xenon needed for LBNF/DUNE from LZ. Award of PO for Xenon procurement. | 5% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | -181 | -905 | 1-point - single value |  | 0 |  | Risk hook: 13122.OBMS92977 --> RO-131-FDC-FI-164 --> 13143.A365742​ | ​LZ has about 10 ton of ultrapure Xenon in its detector at SURF. SDSTA may provide some or all the amount needed for LBNF/DUNE at no cost to the project or at more favorable market conditions (given that the price of Xenon continues to increase). Cost basis is the current Xenon market price: $20/L ($18-22/Liter from Linde on Mar 11, 2021). Required amount: 267 kg (=$904,937). Corresponds to 15 ppm in LAr. Cost Impact: - Low --> 0 (SDSTA charges current Xenon market price). - Mid --> $180,987 (SDSTA charges 80% of current market price). - High --> $904,937 (SDSTA provides Xenon at no charge to LBNF/DUNE). Schedule Impact: No schedule impact, Xenon is planned to come from a gas supplier. There is enough time to plan the deliveries for when they are needed. Xenon coming from SURF will have to travel less. | 1 - Rough guess | ​Agreement reached with SDSTA to supply some or all Xenon needed for LBNF/DUNE from LZ. SDSTA decides not to supply any Xenon from LZ to LBNF/DUNE. | ​Discuss with SDSTA the possibility to supply Xenon to LBNF/DUNE from SDSTA at favorable price (or no charge). Sign agreement with SDSTAto supply Xenon to LBNF/DUNE from SDSTA at favorable price (or no charge). |  | Xenon price (Mar 11, 2021) | 1 (VL) | 1 (L) | 0 (N) | 1 (Low) | -362 | 0 | -18.1 | 0 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-166 | LBNF / DUNE | Tariffs on In-Kind Contributions | ​If LBND/DUNE does not secure duty free import of In-Kind Contributions then the project will have to pay import duties and tariffs. | Threat | External Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​Successful delivery of In-Kind contributions to LBNF/DUNE. Agreement for duty free import of In-Kind contributions from Brazil, Switzerland, CERN. | 0% | 0 (N) - negligible technical impact | 3-point - triangular | 427 | 1702 | 2128 | 3-point - triangular | 0.5 | 1 | 3 | ​Cryogenics Manufacturing, Cryostat Manufacturing. | ​Total value of committed contributions to Detector #1 is $85,122,887 (including $72,078,941 for Cryostat #1). Cost Impact: - Low --> Duty free import. Only processing fee from brokerage firm (0.5% total value = $425,614). - Mid --> Processing fee + Import fee of 1.5% (= $1,702,458). - Max -->Processing fee + Import fee of 2% (= $2,128,072). Schedule Impact: If the paperwork is not in order and/or items are not cleared upon arrival there could be considerable delays in processing. - Min --> 0.5 mo. - Most likely --> 1 mo. - Max --> 3 mo. | 1 - Rough guess | ​Unable to secure duty free import. Items shippped using wrong HTS. Items shipped without proper paperwork. | ​Discuss with FSO the possibility to request duty free imports for scientific equipment. Work with OGC on possible path forwards. Discuss with OHEP to try to achieve duty free waiver from legislation. Work with partners to ensure the right HTS code is used (if possible). If not work with the partners and broker to process the incoming goods according to specified HTS. |  |  | 1 (VL) | 2 (M) | 1 (L) | 1 (Low) | 1419 | 1.5 | 0 | 0 | 2022-08-10 08:28 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-220 | LBNF / DUNE | [FD1-APA] Materials shortage at UK APA production site | ​If material shortages at the UK APA production site happen, then production of APAs would be delayed and we would incur standing army costs | Threat | External Risk | NO | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-04-01 | 2027-07-31 | ​End of UK APA production | 5% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 0.25 | 0.5 | 1 | Risk hook: 13122.D2270 --> RT-131-FDC-FD-220 --> 13122.D2278 | We estimate the schedule impact by assuming delays ranging from 1 week to 1 month for the Daresbury production site and all production lines. | 2 - Reasonable estimate |  | We plan to develop a supply chain management plan and will consider appointing a supply chain manager. This plan will include the details of material source, delivery logistics, critical milestones, and personnel resources required to meet APA production site needs for efficient APA production. All suppliers (vendors, labs, academic institutions) will be included in the implementation of the supply chain plan. | ​Accept the delay. |  | 1 (VL) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0.58 | 0 | 0.029 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-168 | LBNF / DUNE | Far Site Cryo escalation too low | ​If the escalation for Far Site Cryogenics activities is too low, then the cost of activities will be higher than estimated using current escalation rates. | Threat | External Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​Completion of installation of Far Site Cryogenics supporting Far Detctor #1, #2. | 20% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 600 | 1-point - single value |  |  |  | ​Manufacturing and installation of Far Site Cryogenics | ​FS Cryo Manufacturing and Installation activities use the CF escalation rate of 3.5%/year. In the 2015-2018 period these costs have inreased by 12-13% as indicated by Jacobs in their 2018 independent cost estimate of the cost of cryo. During the 2018-2021 the maximum expexted cost increase for the same items was 12.3%, following the Memorandum on Fixed-Price Economic Price Adjustment Clause for Nitrogen System Equipment Acquisition. This memo uses indeces from the the US Bureau of Labor Statistics to determine the variation of prices and applied caps to the max 12-mo change based on historical performance and the clause used for the Nitrogen System Economic Price Adjustments. The delta is 3.94%/year instead of the current 3.5%. | 2 - Reasonable estimate | ​Price of materials and/or manufacturing and/or installation activities increase more than current escalation rate. | ​Monitor price of commodities over time and try to buy when prices are low and/or avoid premiums. |  | Escalation study | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 300 | 0 | 60 | 0 | 2023-05-23 10:06 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-104 | LBNF / DUNE | [I&I] Underground cryostat installation is less efficient than planned | ​If the inefficiencies of working underground are greater than initially estimated then the installation schedule of the cryostat will be impacted. | Threat | Management Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-10-01 | 2025-09-30 | ​After Steel Support Structure is complete. | 40% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 1 | 3 | 4 | Risk hooks a) 13141.A80030 --> RT-131-FDC-FI-104-A--> 13141.​A80050 (FD1) b) 13141.A82030 --> RT-131-FDC-FI-104-B --> 13141.A82050 (FD2) The risk probability should be split between the two risks. The two risks can be realized independently. | ​The current duration of installation is ~12 months. The impact is based on protoDUNE experience. | 2 - Reasonable estimate | Lack of experience working underground with less availability of resources. | CERN engaging with installing contractors to understand the schedule better. |  |  | 4 (H) | 0 (N) | 1 (L) | 2 (Medium) | 0 | 2.67 | 0 | 1.068 | 2024-01-13 12:36 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-170 | LBNF / DUNE | Work stoppage in CUC delays installation Nitrogen System | ​If there is a work stoppage in CUC, THEN the installation of the Nitrogen System will be delayed and possibly the installation of Detector #1. | Threat | External Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​Completion of installation of Nitrogen System | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 0.25 |  | 0.5 | ​131123.04.04.02.95 | ​If the CUC is unavailable, the installation of the Nitrogen System will be delayed and consequently the installation of the APA as well. Min schedule impact: 1 week. Max schedule impact: 2 weeks. | 1 - Rough guess | ​Event outside subcontractor control. | ​Ensure installation is not on critical path. |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0.38 | 0 | 0.038 | 2022-08-10 08:28 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-003 | LBNF / DUNE | [PM] ESH Incident Stops Work Temporarily | ​If a contractor or laboratory/university employee is injured or if material is severely damaged in an ESH incident during FDC work activities, the resulting investigation and implementation of corrective actions could cause schedule delays that impact the critical path. This risk covers the FDC period after the completion of the BSI suproject (September 2025 to December 2028). Between the start of FDC work at SURF (October 2024 and August 2025) this risk is covered by risk RT-131-FSCF-BSI-002 | Threat | Technical Risk | YES | Michael P Andrews | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-08-01 | 2028-06-30 | ​​end of physcial work on the project | 40% | 0 (N) - negligible technical impact | 2-point - flat range | 200 |  | 500 | 3-point - triangular | 0.5 | 1 | 6 | Risk hook: 13141.A80010 (SS) --> RT-131-FDC-PM-003 --> 13141.A80030 | ​If a severe injury occurs, DOE or other stakeholders may require stopping specific work activities until they are satisfied the situation is stable and that work can resume. This could take some time, particularly if there is a fatality. The most likely estimate is that a 1.5 month schedule delay could occur, but perhaps as much as 6 months. If the affected activities are on the critical path, then the worst case condition is that the project has an overall schedule delay. The probability of this risk being realized is taken to be proportioal to the probability that the risk RT-131-FSCF-BSI-002 is realized, based on the relative duration of the time periods where the risks are active.​ | 2 - Reasonable estimate | ​Although work will be planned and contractual provisions written to try to prevent any personnel injuries or unsafe environmental releases, there has been a history on DOE projects, including at Fermilab, of injuries and incidents. This includes unsafe construction practices, being distracted while working, being lax about attention to environmental regulatory requirements, not enforcing contract ESH provisions. | ​ Comprehensive use of ISM program across entire project including complete HA process; good ESH contractual provisions as well as enforcement; working up front during construction contracts to gain buy-in of construction contractor management to ESH issue prevention. Oversight roles and responsibilities for contractor and project team to include ensuring adequate training and attention to site specific risks, and compliance with their ESH program. This includes DOE oversight, Fermi oversight, CMGC safety manager oversight of their contractors - each organization oversees their facets. Fermilab and DOE provide review/oversight on regular basis. During contracting process, contractor provides with past project incident data which includes subtiers, EMRs, compensation carrier, ESH manuals, along with identified subtiers.This means only contractors with acceptable records and safety programs are able to be selected. All these items are already included in the base plan, mainly through management effort and processes already in place. for post-CF activities, use Work Planning & Controls processes to plan detailed installation. Training, Hazard Analyzes, oversight in place for coordination and safe work practices. | ​Work with DOE and other stakeholders to understand cause of incident/injury and take corrective action; work as possible to minimize impact on work.​ |  | 4 (H) | 1 (L) | 1 (L) | 2 (Medium) | 350 | 2.5 | 140 | 1 | 2024-01-13 12:42 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-038 | LBNF / DUNE | FD2 PDS Detector less efficient than estimated | ​​If FD2 PDS detector is less efficient than estimated, then the baseline detector coverage is insufficient and meeting the detector physics requirements is in jeopardy. | Threat | Technical Risk |  | Ryan A Rivera | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 0 - obsolete | 2021-10-01 | 2023-09-30 | ​​Detector efficiency proves to be sufficiently efficient through the ProtoDUNE2 module-0 demonstration phase of FD2 PDS. | 35% | 2 (M) - significantly substandard | 2-point - flat range | 100 |  | 750 | 2-point - flat range | 3 |  | 9 | ​FD2 PDS detector procurement, construction, and installation | ​(1) Probability is engineering estimate based on unknown effects of larger form-factor detector tiles as compared to Horizontal Drift. (2) Cost impact is engineering estimate to cover increasing Cathode detector coverage by 25%. (3) Schedule impacts were estimated by extrapolating schedule impacts for construction and installation of 25% more cathode detector coverage. | 2 - Reasonable estimate | ​This risk is triggered by realizing lower than expected detector efficiency before the conclusion of the ProtoDUNE2 module-0 demonstration.​ | ​Add detector coverage or improve detector efficiency. | ​Add detector coverage or improve detector efficiency.​ |  | 3 (M) | 1 (L) | 2 (M) | 2 (Medium) | 425 | 6 | 148.8 | 2.1 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RU-131-FDC-FD2-016 | LBNF / DUNE | FD2 PDS Commodity price uncertainty | ​If commodity prices change, then production M&S costs will be affected.​​ | Uncertainty | External Risk |  | Ryan A Rivera | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 3 - pending approval | 2021-10-01 | 2026-09-30 | ​​​Production purchase orders placed with vendors.​​ | 20% | 0 (N) - negligible technical impact | 2-point - flat range | -175 |  | 700 | 2-point - flat range |  | 0 |  | ​​Production M&S purchase orders are complete when construction is complete: "13124.A471 T5 MS: Production Warm Electronics, Synchronization, and Monitoring System constructed - PDS", "13124.A470 T4 MS: 100% of Production Tile Assemblies constructed PDS" , "131.FDC.03.07.03.02 Cathode PDS procurement", and "131.FDC.03.07.05.02 Membrane PDS procurement"​ | ​​(1) Probability is engineering estimate based on past experience. (2) Cost impact is engineering estimate assuming only a small subset of production component prices are affected substantially by market forces with the range form -5% to +20​% of total production budget. (3) No schedule impact for commodity price changes.​ | 2 - Reasonable estimate | ​Commodity prices change due to market forces.​ | ​​Obtain quotes and market surveys for critical components, choose the least expensive vendor whenever possible, | ​​Conduct market survey; opportunity realized for production purchase order cost de​creases and risk realized for production purchase order cost increases.​ |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 262.5 | 0 | 52.5 | 0 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-017 | LBNF / DUNE | FD2 PDS Commodity prices escalate faster than inflation | ​If commodity prices increase, then production M&S costs will be increased.​​ | Threat | External Risk |  | Peter Shanahan | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 0 - obsolete | 2021-10-01 | 2026-09-30 | ​​​​Production purchase orders placed with vendors.​​ | 20% | 0 (N) - negligible technical impact | 1-point - single value |  | 160 |  | 1-point - single value |  | 0 |  | ​​​Production M&S purchase orders.​​​ | ​​​(1) Probability is engineering estimate based on past experience. (2) Cost impact is engineering estimate assuming only a small subset of production component prices are increased​ substantially by market forces. (3) No schedule impact for commodity price changes.​ | 2 - Reasonable estimate | ​Commodity prices change due to market forces.​ | ​​​​Obtain quotes and market surveys for critical components.​ | ​​Conduct market survey; threat realized for production purchase order cost in​creases. |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 160 | 0 | 32 | 0 | 2023-06-03 09:42 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FD2-018 | LBNF / DUNE | FD2 PDS Insulation solution allows for warm electronics in cryostat | ​If an insulation solution allows for warm FD2 PDS electronics in cryostat, then we can realize cost savings on the component selection and avoid the need for (or reduce the scope of ) the 30-year qualification acivities | Opportunity | Technical Risk |  | Ryan A Rivera | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2021-10-01 | 2022-09-30 | ​If insulation solution is realized prior to the ProtoDUNE2 module-0 construction phase, then the opportunity is realized and applied to rest of schedule and production purchase requisitions. If insulation solution is not realized prior to the ProtoDUNE2 module-0 construction phase, then the opportunity is retired and not realized. | 20% | 1 (L) - somewhat substandard | 2-point - flat range | 150 |  | 900 | 1-point - single value |  | -3 |  | 13124.A461 (30 year qualification milestone T4 MS: All components validated for 30-years in cold - PDS) | ​(1) Probabitlity is engineering estimate based on technical risk of insulator solution. (2) Cost impact is engineering estimate based on cost savings avoiding 30-year cold qualification activities and simplified component selection. The cost estimate is derived by adding insulation cost estimate of $0-200K and subtracting bias hardware costs of $0K-400K and 5-10% less design effort of $150K-300K​. (3) Schedule impact is engineering estimate assuming simplification of 30-year cold qualification activities. | 2 - Reasonable estimate | ​Demonstration during R&D phase that insulator solution should be part of baseline FD2 PDS design. | ​In-kind effort needed to demonstrate insulator solution in parallel to baseline activities. | ​ |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 525 | -3 | 105 | -0.6 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-019 | LBNF / DUNE | [FD2-BDE] insufficient personnel for QC of cold electronic components during production | ​If not enough personnel is available to perform the quality control tasks during the detector construction phase, then there could a delay in the delivery of components to the CRP assembly sites or to SURF, and an impact on the overall FD2 installation schedule. | Threat | Management Risk |  | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2024-01-01 | 2028-09-30 | ​The risk can be closed after all the detector components for FD2 have completed the quality control process.​ | 30% | 0 (N) - negligible technical impact | 3-point - triangular | 25 | 50 | 75 | 3-point - triangular | 1 | 2 | 3 | Risk hook: 13122.2004.1311.330 --> RT-131-FDC-FD2-019 --> 13124.2.1.3​ ​ | ​The risk probability is chosen to be 30% to reflect the moderate risk level. The assumption is that one or two institutions not able to perform their QC responsibilities due to lack of personnel. The range of cost estimate is for hiring 1 to 2 technicians for about 3 months to perform the QC tasks. The impact on the schedule is from 1 to 3 months to account for the time it takes to hire technicians and also possibly for moving the test equipment to a new institution. | 2 - Reasonable estimate | ​During the production phase, a QC site is not able to perform the task due to personnel shortage. | For most QC activities, multiple institutions are involved to expedite the process as well as for redundancy. The test equipment is also designed to be transportable in case it nees to be moved to another institution.​ Another risk mitigation is establishing early MoUs between the consortium and the institutions involved in the QC process. | ​If the risk is realized, the affected task will either be delayed while recruiting more personnel or be transferred to another institution. |  | 3 (M) | 0 (N) | 1 (L) | 1 (Low) | 50 | 2 | 15 | 0.6 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-001 | LBNF / DUNE | (FD2) DAQ/SC: Slow Controls effort/cost underestimated | If the requirements on the SC system are incomplete, additional effort/cost will have to be found urgently, close to the time of installation. | Threat |  |  | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft | 2026-10-01 | 2028-04-01 | ​All SC requirements are complete, with interfaces to all detector subcomponents fully defined. | 30% | 0 (?) - Not yet defined | 3-point - triangular | 100 | 200 | 300 | 3-point - triangular | 1 | 3 | 5 | ​Integration of FD2 slow controls; detector operation and commissioning | ​Continue regular dicsuccions and requirements capture with the other consortia; use PD-II to re-evaluate the dimensioning of the SC system for VD | - Not yet defined - |  | ​continue regular dicsuccions and requirements capture with the other consortia; use PD-II to re-evaluate the dimensioning of the SC system for FD2 |  |  | 3 (M) | 1 (L) | 1 (L) | 1 (Low) | 200 | 3 | 60 | 0.9 | 2023-01-23 16:34 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-002 | LBNF / DUNE | FD2 DAQ/SC: Different interfaces to different types of electronics | ​If it is not possible to unify the interfaces for timing distribution and readout, then additional work is required for development, testing and maintenance. | Threat |  |  | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2022-06-01 | 2023-06-01 | ​Successful integration of readout electronics to DAQ in NP02 | 50% | 1 (L) - somewhat substandard | 1-point - single value |  | 0 |  | 2-point - flat range | 2 |  | 4 | 13124.A9017MS (milestone for start of installation of module 0) | ​Based on previous experience of interface customization. This is an international risk, that only introduces a delay for the test of CRPs in the cold box and later a delay in the test of Module 0 of the vertical drift detector in the NP02 cryostat. | 1 - Rough guess |  | ​continue regular discussions with the electronics and PDS consortia; foresee the need of additional effort |  |  | 4 (H) | 0 (N) | 1 (L) | 2 (Medium) | 0 | 3 | 0 | 1.5 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-020 | LBNF / DUNE | (FD2) DAQ/SC: FD Installation & integration | ​If the availability of the infrastructure for DAQ/SC is delayed, temporary solutions to allow for initial installation of detector components has to be put in place. | Threat | Management Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved | 2026-06-01 | 2027-03-01 | ​FD2 ready for detector installation. | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 50 |  | 1-point - single value |  | 1 |  | 13124.A9017MS |  | 1 - Rough guess |  | ​ensure that the dependencies in the installation schedule are carefully followed up |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 50 | 1 | 5 | 0.1 | 2023-01-23 16:34 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FD2-021 | LBNF / DUNE | (FD2) DAQ/SC: Favorable technology evolution | ​If progress in computing and network technologies contiunes steadily, it is possible to optimize the DAQ layout to reduce cost | Opportunity |  |  | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft | 2024-04-01 | 2024-10-01 | ​Procurement of DAQ/SC equipment completed. | 20% | 0 (?) - Not yet defined | 2-point - flat range | 300 |  | 700 | 1-point - single value |  | 0 |  |  |  | - Not yet defined - |  | ​follow technology evolution closely and evaluate new products |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 500 | 0 | 100 | 0 | 2023-01-23 16:34 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RU-131-FDC-PM-055 | LBNF / DUNE | [PM] Fluctuations in the exchange rates cause variations of the costs of FDC components | ​If the exchange rate of the USD relative to other currencies fluctuates, the cost of some detector components procured from U.S. vendors may increase or decrease relative to the budgeted cost, with variations that exceed the cost uncertainty. This could result in a significant deviation from the expected construction cost. | Uncertainty | External Risk |  | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 2 - see Comments | 2021-05-18 | 2027-10-31 | ​This risk will be closed at the completion of all the procurements of the components that are fabricated outside the U.S. | 100% | 0 (N) - negligible technical impact | 2-point - flat range | -750 |  | 750 | 1-point - single value | 0 |  |  | ​13124.3.3.8 (FEMB procurement, 15% of cost impact) 13124.4.2.1 (Cold power cables, 15% of cost impact) 13124.4.3.1 (Cold signal cables, 35% of cost impact) 13124.6.2.2 (Fabrication of Warm Interface boards 20% of cost impact) 13124.7.1.2 (Low voltage power supplies: 5% of cost impact) 13124.7.2.2 (Bias voltage supplies: 10% of cost impact) | ​We have identified $3.7M of FD2 components (printed circuit boards and discrete components), cold cables, and power supplies that are likely to be subject to currency fluctuation uncertainties. We assume a maximum rate fluctuation of -20% to +20% with uniform probability. | 2 - Reasonable estimate | ​This risk is realized if there is a significant variation of the exchange rate of the USD relative to foreign currency of the suppliers. | ​No risk mitigation strategy is available. Currency exchange rates are subject to market fluctuations. | ​No action is available to reduce risk impacts after the risk event occurs. |  | 5 (VH) | 1 (L) | 0 (N) | 2 (Medium) | 0 | 0 | 0 | 0 | 2023-03-24 18:39 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-233 | LBNF / DUNE | [FD1-HV] Experience in PD II leads to a significant redesign | If the HV performance during PD II does not improve upon PD I performance, then there may be a significant redesign of the HV system | Threat | Technical Risk | NO | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-09-01 | 2024-12-31 | ​The risk can be closed once the experience from ProtoDUNE II or from Module 0 of the vertical drift detector is accepted and the design is finalized. | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 200 |  | 500 | 2-point - flat range | 2 |  | 6 | Risk hook: 13122.A12999MS --> RT-131-FDC-FD-233 --> 13122.A13307 | The cost assumes one engineer + one designer for 2 to 3 months, plus time and cost to prototype new assembly tools, and additional construction costs. | 1 - Rough guess | If there are significant issues with the ProtoDUNE-SP II or Module 0 operations, there could be a need for a significant redesign. | ​Test setups of individual components. No major devialtions from the sucessful ProtoDUNE-SP I design. | ​Revert to original TDR design. |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 350 | 4 | 35 | 0.4 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-006 | LBNF / DUNE | FD2 BDE Single source vendor for CE components | ​If one of the single source vendors fails to deliver the components (ASICs, power supplies, and or cables), then alternative vendor would have to be found. For the ASICs, it would also require redesigning the ASICs using a different technology. This would result is both cost increase and schedule delay. | Threat | External Risk |  | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2021-05-19 | 2027-10-31 | ​This risk can be closed when all the procurements for the CE components which are from single source vendors are completed. | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 1600 |  | 3300 | 2-point - flat range | 6 |  | 9 | 13124.3.3.8 (FEMB production, 25% of cost and schedule impact) 13124.4.3.1 (cold cables production, 25% of cost and schedule impact) 13124.7.1.2 (low voltage power supplies, 25% of cost and schedule impact) ​13124.7.2.2 (bias voltage supplies, 25% of cost and schedule impact) | ​The cost impact is assumed to be a flat distribution between the cost of redesigning and test the ASICs and FEMBs ($1.6M) and redo the engineering of cold cables ($3.3M). The delay is assumed to be 1 year with a fluctuation of +/- 33%. | 2 - Reasonable estimate | ​If any of the single source vendors fails to deliver the components on time, that will trigger this risk. | ​For the ASICs, the risk mitigation plan is to start the ASICs production as early as possible to minimize the impact of this risk if it occurs. For other components, we are exploring alternative vendors as back up for some of the other components. For low voltage and HV bias power supplies, CAEN is another vendor that could provide the power supplies. For the cold cables, we will continue to qualify other potential vendors. | ​For the power supplies, we already have a second vendor that we can use. For the cold cables, we will hopefully have qualified another vendor that we could use ahead of time. The ASICs has two options: either redesign the ASICs or port the design to a different fabrication process. The decision will need to be made based on which solution will have less cost and schedule impact at that time. |  | 2 (L) | 2 (M) | 2 (M) | 2 (Medium) | 2450 | 7.5 | 245 | 0.75 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FD2-023 | LBNF / DUNE | FD2 BDE FEMBs are installed on the CRP without the CE boxes | ​If noise level on the FEMB without the CE boxes is acceptable, then the FEMBs can be installed on the CRP without the CE boxes. This will eliminate the fabrication cost of the CE boxes. | Opportunity | Management Risk |  | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2021-05-19 | 2027-10-31 | ​The risk can be closed when the decision is made whether or not the CE boxes are needed. | 5% | 0 (N) - negligible technical impact | 1-point - single value |  | 220 |  | 1-point - single value |  | 0 |  | ​13124.3.3.10 (25%) CE box fabrication​​​ 13124.3.3.13 (25%) 13124.3.3.16 (25%) 13124.3.3.19 (25%)​ | ​The estimate is based on a quote from vendor. The unit cost for the aluminum version of CE box is $93. For FD2, we will need to fabricate 2290 boxes. The total cost of CE box is about $220K. | 3 - Solid estimate | ​This opporitunity will be trigggered when the study shows that the noise level on the FEMB is acceptable without the CE box and the decision is made not to use it. | ​This is an opportunity. We will do a careful study to evaluate the need to shield the FEMB with the CE box to minimize electronics noise.​ | ​If this opportunity is triggered, we will not fabricate the CE boxes. |  | 1 (VL) | 1 (L) | 0 (N) | 1 (Low) | 220 | 0 | 11 | 0 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-007 | LBNF / DUNE | [FD2-BDE] Insufficient un-costed labor at SURF for installatiion | ​If sufficient un-costed labor cannot be recruited to SURF for CE installation, the laboratory technicians will have to be used. This will increase the installation labor cost. | Threat | Management Risk |  | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2021-05-19 | 2029-10-31 | This risk can be closed when the bottom CE installation at SURF is completed​ | 30% | 0 (N) - negligible technical impact | 3-point - triangular | 97 | 194 | 292 | 1-point - single value |  | 0 |  | Risk hook: 13143.50950 --> RT-131-FDC-FD2-007 --> 13124.9.6.1 ​ | ​The probability is rather high at 30% given the difficulty in recruiting uncosted labor to station at SURF for extended period of time. We assume $110/hr (fully loaded) rate for a laboratory technician. The low range of the cost estimate assumes hiring 1 technician for 6 months. The high range assumes hiring 3 technicians for 6 months. There is no schedule impact. | 2 - Reasonable estimate | ​If we cannot recruit the needed number of uncosted labors to station at SURF for installation, this risk will be triggered. | ​Will try to recruit uncosted labors well ahead of time to mitigate the risk. | ​Will try to identify laboratory technicians ahead of time so if the risk is trigger, technicians are available to work at SURF. |  | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 194.3333 | 0 | 58.3 | 0 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-024 | LBNF / DUNE | FD2 HVFT and Extender fail to hold 300kV in R&D 1 phase | If the new feedthrough and extender designs do not hold 300kV in HV test stand in early 2021, then there will be a rework causing cost increase and sched. delays. | Threat | Technical Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft | 2021-05-01 | 2021-07-31 | ​Iceberg HV test in early summer demonstrate stable operation up to 300kV | 30% | 1 (L) - somewhat substandard | 2-point - flat range | 100 | 200 | 300 | 2-point - flat range | 3 |  | 6 | ​Full scale HV system test in NP02 in the fall |  | 1 - Rough guess | ​Some aspect of the design has unexpected vulnerability | ​conduct a review before running the test. Implement diagnostics in the test | ​identify the culprit, update design, rerun the test |  | 3 (M) | 1 (L) | 1 (L) | 1 (Low) | 200 | 4.5 | 60 | 1.35 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-234 | LBNF / DUNE | [FD1-PD] Additional Module Design/Validation Required (US) | IF testing desmonstrates weaknesses in module mechanical design then additional design/prototyping may be required, delaying PD module fabrication. | Threat | Technical Risk | NO | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-04-01 | 2024-03-31 | ​Conclusion of Photon Detector production readiness review | 15% | 0 (N) - negligible technical impact | 2-point - flat range | 50 |  | 150 | 2-point - flat range | 2 |  | 4 | Risk hook: 13122.A12248MS --> RT-131-FDC-FD-234 --> 13122.A12640​ | Estimate is based on an engineering estimate of the reliability of the photon detector module mechanical design. Design has passed initial design review and multiple prototyping steps. Time and cost estimates are based on between 2 and 4 months of additinal ME/designer and minimal additinal prototype development. | 2 - Reasonable estimate | ​During testing observed mechanical failure of structure or degradation of performance due to mechanical design limitations | ​Extensive testing at Ash River, UNICAMP and ProtoDUNE 2 of Photon Detector mechanical structures. | Additional design and engineering activities to bring design into compliance. Additional prototype development and testing to validate revised design​ |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 100 | 3 | 15 | 0.45 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-008 | LBNF / DUNE | FD2 HVS Feedthrough and extender fail to hold 300kV in R&D phase 2 | ​ If the new feedthrough and extender designs pass the test in Iceberg but do not hold 300kV in HV test in NP02 in late 2021, then there will be a rework causing cost increase and schedule delays. | Threat | Technical Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved | 2021-06-01 | 2021-12-30 | ​HVFT and extender test in NP02 reaches stable operation at 300kV | 10% | 1 (L) - somewhat substandard | 2-point - flat range | 10 |  | 50 | 2-point - flat range | 2 |  | 3 | 13124.A240 (construction of components for module 0) | Given the successs of the NP02 tests, we no longer believe that major modifications to the extender will be needed and that there will be further tests in NP02. At most there will be smaller scale tests in the ICEBERG cryostat, resulting in shorter delays and smaller expenses. The impacts mentioned here involve the fabrication of new parts and a test run in ICEBERG. ​​ | 1 - Rough guess | ​unexpected problem in scaling the test, or other unexpected issue with NP02 HV system | ​careful review of the existing and the new elements in the NP02 HVS test. Implement diagnostics. | ​Identify the cause, redesign, and re-test at smaller scale |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 30 | 2.5 | 3 | 0.25 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-025 | LBNF / DUNE | FD2 HVS fails to hold 300kV in module-0 test | ​ If the HV delivery system and field cage designs do not hold 300kV in the module-0 test, then there will be a rework causing cost increase and schedule delays. | Threat | Technical Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  | ​HVS maintains stable operation of 300kV in module-0 test for a reasonable long period. | 10% | 1 (L) - somewhat substandard | 2-point - flat range | 100 |  | 300 | 2-point - flat range | 3 |  | 6 | 13124.A254 (completion of production readiness reviews) | ​Redesign needed and will have to be validated by an ICEBERG test. NP02 run not anticipated | 1 - Rough guess | ​New field cage design failed to perform at larger scale | Thorough design review and QC at production/installation. ​implementing sufficient diagnostics | ​redesign, re-test affected component at mid-scale. |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 200 | 4.5 | 20 | 0.45 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-011 | LBNF / DUNE | FD2 cathode planarity out of spec in prototypes | ​If cathode planarity doesn't meet the specs, then there will be a redesign causing cost increase and sched. delays | Threat | Technical Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft | 2021-06-01 | 2023-12-20 | ​Module-0 demonstrate acceptable mechanical stability of the cathode. | 20% | 1 (L) - somewhat substandard | 1-point - single value |  | 0 |  | 2-point - flat range | 2 |  | 12 | FD2 ​cathode production |  | 1 - Rough guess | Design of the cathode and its suspension ​material deform beyond designed value at large scale | ​add additional cold box tests of the cathode module. | ​redesign, retest in cold |  | 2 (L) | 0 (N) | 2 (M) | 2 (Medium) | 0 | 7 | 0 | 1.4 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-026 | LBNF / DUNE | [FD2-HVS] field cage profile damage | ​If a large fraction of the field cage profiles are damaged during shipping, then a replacement batch is needed, resulting in higher cost for CERN | Threat | External Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2024-01-02 | 2027-01-02 | FC module assembly is finished | 20% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 3 | Risk hook: 13124.A369421 --> RT-131-FDC-FD2-026 -->13124.A420 ​ ​ | ​CERN has produced the field cage profiles 3 times for NP04 and other prototyping activties so far. One of the shipments was delivered to CERN with a damaged shipping crate and content. The probability of 20% is based on this experience. Since this is non-US, it won't impact US project cost. Depending on when the damage occurs before the assembling of the field cage, some delays in assembly is possible while CERN is re-ordering them. | 1 - Rough guess | ​shipping and handling damages | Increase FC profile production to have sufficient spares (10% spare is planned), and early shipment and inspection of packages​ | rush order additional profiles. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 1.5 | 0 | 0.3 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FD2-027 | LBNF / DUNE | FD2 cathode resistivity | ​if the cathode resistivity is sufficiently high, it may not be necessary to include the shield plane on the anode, which may reduce the fabrication cost on the anode, especially if it is 2-view​ | Opportunity | Management Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft | 2021-06-01 | 2023-12-20 | ​module-0 demonstrate good performance | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | -1000 |  | 1-point - single value | [5 empty] | - Not yet defined - |  |  |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | -1000 | 0 | -100 | 0 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-238 | LBNF / DUNE | [FD1-PD] WLS Filter Coating Unstable | ​If filter optical coatings are found to be unstable then additional validation testing in the US may be required. | Threat | Technical Risk | NO | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-04-01 | 2024-08-30 | ​Completion of PRR | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 15 |  | 30 | 2-point - flat range | 3 |  | 6 | Risk hook: 13122.A12592 --> RT-131-FDC-FD-238 --> 13122.A12596​​​​ | Assumes additional quality validation (3 months (low range) to 6 months (high range) required in US. Estimated monthly testing cost of $5K, including labor and M&S. ​ | 2 - Reasonable estimate | ​Coating failure discovered in ICEBERG, US coating stability test facility, Brazil testing, FD1 ProtoDUNE 2. | ​Extensive coating testing in Brazil and at US facilities / Fermilab | ​Additional design/eingeering activities to deal with potential changes, additional prototype testing to validate revised design |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 22.5 | 4.5 | 2.3 | 0.45 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-009 | LBNF / DUNE | [FD2-HV] insufficient non-costed labor for Field Cage underground activities | If sufficient un-costed labor cannot be recruited to SURF for I&I support, then lab technicians will have to be used leading to a cost increase for the project | Threat | Management Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2027-11-10 | 2028-06-14 | FD2 HVS installation if complete | 30% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | 16 | 63 | 1-point - single value |  | 0 |  | Risk hook: 13124.A369421 --> RT-131-FDC-FD2-009 -->13124.A420​ | ​Entire cost on un-costed labor for FC assembly & installation for FD2 is currently 900hrs. assuming a generic tech labor rate of $70, the total cost to replace the uncosted labor is 63k. Use a 3 point distribution with middle point at 1/4 of the range (16k). No cost impact assuming replacement labors are readily available​.​ | 2 - Reasonable estimate | This risk could be caused by the lack of funding for some of the institutions that had previously committed to participate in the integration and installation activities at SURF (this could be caused for example by a cancellation of their base grant following a comparative review). Another possible trigger are travel restrictions for international partners | This risk is being mitigated by providing information to DOE on the institutions that are critical for the detector construction and installation and by involving international partners in all the aspect of the detector construction. | If this risk is realized, additional personnel will have to be recruited from the national laboratories or in situ to compensate for the labor shortage, with a consequent cost increase to the project. To avoid any delays in the integration and installation activities, the new personnel will have to be on site a few weeks ahead of the installation such that they can be trained for the tasks that need to be performed. |  | 3 (M) | 0 (N) | 0 (N) | 0 (Negligible) | 26.3333 | 0 | 7.9 | 0 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-243 | LBNF / DUNE | [FD1-PD] Storage Environmental Control found to be unsatisfactory | ​If prior to, or during, storage at SDWF it is discovered that environmental controls are insufficient to maintain integrity of the photon detector modules, then improvments will need to be made to meet the requirements, necessitating additional engineering | Threat | Technical Risk | NO | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2025-01-01 | 2027-09-30 | ​Risk can be closed at conclusion of module installation | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 20 |  | 60 | 1-point - single value |  | 2 |  | Risk hook: 13122.A12780 --> RT-131-FDC-FD-243 --> 13122.A12782​ | ​Assumes 2 month delay in shipping due to shortcomings discovered in local storage. Assumes minimal US engineering, with some required M&S to mitigate conditions. | 2 - Reasonable estimate | ​Problems with photon detector modules due to storage discovered during initial storage spot inspections or installation | ​Storage facility design will be informed by ProtoDUNE 2 experience and pre-production dry runs. Just-in-time production | ​Additional design and engineering activities to deal with potential changes to environmental control |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 40 | 2 | 4 | 0.2 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-246 | LBNF / DUNE | [FD1-PD] Integration/Installation Time/Cost over-run | ​If photon detector design and new installation procedures result in increases of personnel and time during installation then addition of up to 20% in labor cost may be realised. No delay is anticipated as ProtoDUNE 2 will provide sufficient warning of need to allow us to provide required labor. | Threat | Management Risk | NO | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-08-01 | 2027-10-31 | ​Completion in installation of a significant number of modules in DUNE FD module 1 | 20% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 75 | 1-point - single value |  | 0 |  | Risk hook: 13141.A1210 --> RT-131-FDC-FD-246 --> 13141.A1220​ | up to 20% change in PD module installation cost due to uncertainty in labor estimates | 2 - Reasonable estimate | ​Initial installation in DUNE FD 1 indicates a need for an up to 20% increase in the labor required for PD module installation. | ​Ash River, PSL, ProtoDUNE 2 installation testing | ​Additional labor resources will need to be identified to cover installation time over-runs​ |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 37.5 | 0 | 7.5 | 0 | 2023-12-12 07:50 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-009 | LBNF / DUNE | [PM] SURF underground cavern expansion project impacts LBNF/DUNE project | ​​If the SURF underground cavern expansion project is scheduled during the LBNF/DUNE project then FDC installation activities may be delayed due to competition for shaft access, ventilation, underground work spaces and underground occupancy. The bypass excavation is included in a separate risk (RT-131-FDC-PM-126) | Threat | Management Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-08-01 | 2029-04-30 | ​​completion of FDC project | 15% | 0 (N) - negligible technical impact | 3-point - triangular | 5700 | 11400 | 22800 | 3-point - triangular | 1.5 | 3 | 6 | Risk hook: 13141.A80010 (SS) --> RT-131-FDC-PM-009 --> 13141.A80030 | March 2023 schedule shown by SDSTA for full cavern expansion indicates work would begin in July 2027, while cryogenics & FD2 installation is ongoing. On this timeline, the cryostat installation for #1 and #2 would be complete.​​​ The cost estimate is based on the impact on the contractor for the installation of the cryogenic system, where the cost is $11.4M for 3 months. At the time where this risk could be realized other contactors have already completed their work, and any other additional costs will be part of the schedule contingency.​ | 1 - Rough guess |  | ​​Utilize joint coordination team to coordinate various schedules ​ |  |  | 2 (L) | 3 (H) | 1 (L) | 2 (Medium) | 13300 | 3.5 | 1995 | 0.525 | 2024-01-13 12:43 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-254 | LBNF / DUNE | [DAQ] Delay in availability for detector integration | ​If the DAQ is not available (for any reason) at the beginning of the integration of the TPC electronics and of the photon detector on the APAs then these activities could be delayed or slowed down, which would result in a delay of achieving the KPPs. This risk covers also the possibility that the DAQ has problems when trying to include a large number of APAs (scaling issues). This would also result in a delay of the combined readout tests, again resulting in a delay of the KPPs | Threat | External Risk | NO | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-01-01 | 2027-10-15 | ​This risk can be closed when all the DAQ detector components are installed and commissioned at SURF | 5% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 2 | Risk hook: 13141.A3350 --> RT-131-FDC-FD-254 --> 13141.A10730 | Schedule delay is a rough guess. Support for electronics testing will be a major focus of the DAQ at this time, so any issues related to firmware or software development can have the maximum attention/work from DAQ experts. Issues related to components are already mitigated by the plans for an early procurement and vertical-slice testing of ~10% of production equipment prior to installation at SURF, making that equipment immediately available. | 1 - Rough guess | ​There can be multiple reasons for a delay in the availability of the DAQ: the outfitting of the DAQ room on the cryo mezzanine is delayed, international partners do not deliver all the DAQ components in time, delays in the implementation of the firmware and software required to operate the DAQ, unstable firmware/software that prevent the users from relying on the DAQ, scaling issues that are not observed when dealing with a limited number of APAs. | ​At least initially (tests on the APA assembly tower and tests in the cold box), this risk can be mitigated by using DAQ components that are either already in hand (we are using the same components or earlier versions of the components for some of the TPC electronics test stands). We could also rely on earlier generation of DAQ components from ProtoDUNE or other experiments. One way to mitigate the risks is therefore to estimate the minimal number of DAQ components that are necessary during the integration and installation process (9 APAs equivalent) and ensure that these are available at SURF. During the installation of the APAs inside the cryostat and the corresponding tests it is not necessary to have access to a complete DAQ setup. If a sufficient number of DAQ components is available, fibers can be moved around. During the integration and installation certain components of the DAQ (the trigger system for example) are not really required. Thus risks to the integration and installation process can be mitigated by giving higher prority to the firmware and software development for those components. The second run of ProtoDUNE and the early adoption of the network based readout also serve as a risk mitigation. The only mitigation for scaling issues is to try to read out all the available rows of APAs during the detector installation. This allows the investigation of scaling issues as the installation progresses, allowing for an early detection of problems. | ​Depending on how the risk is realised the following actions could be taken: a) if the delay is caused by the availability of firmware or software or if it caused by problems uncovered during the integreation and installation, additional resources should be made available, with funding provided by the project b) if the delay is caused by the availability of DAQ hardware components, the integration and installation process can continue by moving fibers around in the DAQ room |  | 1 (VL) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 1 | 0 | 0.05 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-257 | LBNF / DUNE | [DAQ] FD1 Availability of DAQ personnel on site at SURF | ​If DAQ personnel is not available on site at SURF during the integation and installation, there could be delays in these activities, which would then have an impact on the achievement of the KPPs​ for FD1. | Threat | External Risk | NO | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-01-01 | 2027-10-15 | ​This risk can be closed when the FD1 DAQ components used during installation have been installed and all the firmware/software servers have been commissioned. | 20% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 2 | Risk hook: 13122.A451930 --> RT-131-FDC-FD-257 --> 13122.A451940​​ | The total estimated time for installation is expected to be 5 months. If up to 40% of effort is not available, that will lead to a delay of up to 2 months. | 1 - Rough guess | If not enough DAQ personnel are available to assist in DAQ installation activities, there will be a delay in the completion of the work. | Tools should be put in place to allow for remote access to the DAQ systems and for collaborative work between personnel working at SURF in the cavern and DAQ experts that are either in Europe or in other US locations. DAQ experts should be trained in such a way that there isn't a single person with a particular expertise that can help solve problems that are encountered during the integration and installation activities at SURF. This includes putting in place succession plans for DAQ experts. ​Involve the Fermilab visa office to address any issues related to visa problems. | ​If this problem is caused by lack of travel funds, the DUNE project should consider providing travel support. If the problem is due to visa issues, try to get help from the Fermilab visa office. If the problem is caused by personnel leaving, identify and train a replacement. |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 1 | 0 | 0.2 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-035 | LBNF / DUNE | FD2 PDS Cathode plane HV potential variation requires modifications to power distribution | ​If Cathode plane HV potential variation requires modification to PDS power distribution, then this impacts detector coverage design and or power distribution design and jeopardizes detector performance and schedule. | Threat | Technical Risk |  | Ryan A Rivera | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  | ​If risk is not realized before conclusion of Production Readiness Review, then risk can be retired. | 50% | 2 (M) - significantly substandard | 2-point - flat range | 200 | 1000 | 2000 | 1-point - single value |  | 0 |  | 13124.A463 (this risk should be realized or retired at the latest at the time of the production readiness review) | ​(1) Probability is engineering estimate based on uncertainties in interfaces/impacts of broadcasting power and signal across long distances along cathod plane. (2) Cost impact is engineering estimate assuming we must design in additional isolation and finer (2x) granularity power/signal distribution. ( | 2 - Reasonable estimate |  | BCR FDC_1002 (https://fbcr.fnal.gov/BCR/View/1598) included simulation effort to understand this risk and approaches to mitigate it. In order to assess the impact of the Cathode HV variation risk (RT-131.FD2-035), two independent simulations are foreseen with a physical demonstration to follow. For now, this BCR only includes an assessment via simulation. Preliminary demonstration not included for now. The impact of only simulation assessment is ~$125K. The need for a demonstration will be evaluated after this initial assessment. The delay introduced by this risk was removed on 01/28/22 because we are going to decide what kind of photon detector to use prior to the PRR and we will also engineer this solution by that time. | ​If this risk is realized, there are more than one solution to mitigate it. Considersations must include immunity from HV discharge damaging the PDS electronics and will require a topology and/or technology baseline change. |  | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 1100 | 0 | 550 | 0 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-012 | LBNF / DUNE | [PM] Unavailability of SURF-/FRA-supplied systems at SURF - Low P / High impact | ​IF access to systems and spaces is not possible as required THEN schedule delays may occur.​ (hoist, power, brattices, pumping systems, fans, refuge chamber). This is the low probability high impact version of this risk. This risk covers the FDC period after the completion of the BSI suproject (September 2025 to December 2028). Between the start of FDC work at SURF (October 2024 and August 2025) this risk is covered by risk RT-131-FSCF-BSI-021. We assume that short stoppages are covered under the duration uncertainty and therefore we do not have an equivalent of risk RT-131-FSCF-BSI-012.​ | Threat | External Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-08-01 | 2028-06-30 | ​​Completion of FS work | 20% | 0 (N) - negligible technical impact | 3-point - triangular | 750 | 1500 | 4500 | 3-point - triangular | 1 | 3 | 6 | Risk hook: 13141.A80010 (SS) --> RT-131-FDC-PM-012 --> 13141.A80030 | ​Potential system failures that would affect the entire project include short repairs to infrastructure, temporary access restrictions, power outage, ventilation fan failure or failure to shaft ​systems​ (shaft, hoists, conveyances). FDC burn rate is $4.6M per month is part of the schedule delay. Contractor delay costs as noted below are included in cost impacts. ​​Cryostat installation $20M = cost of delay is $800k per month Cryogenics Installation peak cost $11.4M (3 mo) = cost of delay is $4M per month The cost impact we quote uses $0.75M/month which is an average between the cryostat installation and the cryogenic installation. This risk covers the FDC period after the completion of the BSI suproject (September 2025 to December 2028). Between the start of FDC work at SURF (October 2024 and August 2025) this risk is covered by risk RT-131-FSCF-BSI-021​. | 1 - Rough guess | ​SURF cannot provide these systems for LBNF/DUNE: ventilation, hoisting, water controls, access/logistics support. FRA cannot provide systems such as power, HVAC in the caverns. | ​Implemented SURF Reliability​ Projects to increase uptime. Regular maintenance is necessary to be sure equipment is available. Several reliability projects associated with hoists have been added to the project scope to reduce this risk, but until completed these project themselves may increase the risk of a delayed start.​ Ensure spares are available on-site for repairs | ​If systems fail, wait for repairs to be made. Previous experience: April/May 2021: skip rope deformation resulted in 1 week shaft shutdown July 2021: hoist programming issue resulted in 2 day shaft shutdown |  | 2 (L) | 2 (M) | 1 (L) | 2 (Medium) | 2250 | 3.33 | 450 | 0.666 | 2024-01-13 12:41 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FD2-037 | LBNF / DUNE | [FD2-PDS] Additional collaborating funding agencies identified | ​If the funding agencies from international collaborators commit to support some aspects of the project, then these additional resources can be leveraged and used to reduce the scope of the DOE project, resulting in a cost reduction. | Opportunity | External Risk |  | Ryan A Rivera | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 0 - obsolete |  |  | This risk will be closed once the scope of the contributions from international partners has been fully defined (opportunity realized) or once it is clear that these contributions will not happen. | 15% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | -1000 | 1-point - single value |  | 0 |  | 13124.A456 - By the time of the preliminary design review of the PDS system we should have reached an agreement on the US scope | ​(1) Probabilitiy is estimate based on international collaboration verbal interest. (2) Cost impacts is esimate based on international collaboration verbal levels of interest. (3) Schedule impact is estimate based on transfer of activities rather than acceleration of activities. | 2 - Reasonable estimate | This risk is realized once there is a credible commitment in terms of labor and M&S from an international partners. | Pursue negotiations with international partners to involve them in the photon detector consortium activities for FD2. This opportunity has already been partially realised with BCR 1004 where $6.6M have been transferred to international partners. As a consequence the risk impact and probability have been reduced. We are continuing to try to involve international partners. | ​If the opportunity is realized make the appropriate changes in P6 |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | -500 | 0 | -75 | 0 | 2023-04-17 17:32 | Marco Verzocchi | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-126 | LBNF / DUNE | FDC SD Taxes for IKC cryostat | If the LBNF/DUNE-US project needs to cover contractor excise taxes for international contributions then the project budget will be impacted. | Threat | External Risk |  | Patrick L. Weber | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved | 2023-10-01 | 2027-10-01 | Clarity on the applicability of SD taxes to international partner contributions. ​ | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 3600 |  | 1-point - single value |  |  |  | 131123.01.01.822 (Import duties, warm structure, cryostat #1, #2) | ​The estimate is based on an estimated $180M in foreign contributions. SD has a 2% contractor's excise tax that may be applicable. | 1 - Rough guess | ​The State of SD applies contractor's excise tax to foreign contributions. | ​FRA has hired local tax counsel to advise on the applicability of the tax. May ask for determination from department of revenue | ​None. |  | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 3600 | 0 | 1800 | 0 | 2022-10-05 17:21 | Patrick L. Weber | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-285 | LBNF / DUNE | FD1 CE Switch to the White Rabbit time distribution system | ​If the collaboration decides to replace the Bristol timing distribution system to the White Rabbit system, an additional design and prototyping for the Warm Interface Board will be necessary, resulting in increased development costs. | Threat | Technical Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2021-09-01 | 2023-08-31 | ​This risk can be closed once the Collaborationt takes a decision on the timing distribution system that will be used for FD1, FD2, and ND. | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 800 |  | 1000 | 2-point - flat range | 0 | 4 | 8 | ​13122.2004.114.280 | ​We estimate that a there is a minimal cost increase of $700k in terms of M&S ($630k for 65 White Rabbit switches plus the corresponding optical fibers required to connect the switches to the WIBs and PTCs, plus one extra round of WIB prototypes), plus an additional $100k-$300k of engineering for the WIB design modifications. | 2 - Reasonable estimate | ​This risk will be realized if the Collaboration decides to use the White Rabbit timing distribution protocol in every subdetector replacing the Bristol timing distribution system, | ​We can try to design the next version of the WIB to be compatible both with the Bristol and White Rabbit timing distribution protocol, but this may not be possible. If we manage to design the WIB to be compatible with both systems, the cost impact may be reduced, but will not go to zero (since we will need to purchase additional White Rabbit switches and the fiber plant). | ​If the risk is realized we will have to make design modifications to the WIB and make a BCR to purchase the additional hardware |  | 2 (L) | 1 (L) | 2 (M) | 2 (Medium) | 900 | 4 | 90 | 0.4 | 2023-01-23 16:36 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-013 | LBNF / DUNE | FD2 BDE Switch to the White Rabbit timing distribution system | ​If DUNE decides to use White Rabbit timing distribution system for FD1 and FD2, additional White Rabbit distribution modules and fibers would need to be purchased. | Threat | Technical Risk |  | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved |  |  | ​This risk can be closed or realized once the Collaboration makes a decision on which timing distribution system to use for FD1, FD2, and ND | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 427 |  | 1-point - single value |  | 0 |  | ​13124.6.2.2 (fabricate first 25% of WIBs) | ​The probabibility of choosing the White Rabbit timing system is fairly high. At the moment we estimated it to be about 40%. The cost is based on vendor quote from Seven Solutions. For FD2 bottom CRP electronics, we will neet to purchase 43 WR Z16 modules at $9700 each. In addition, we budgeted another $10K for the fibers. The total cost is $427,100. There is no schedule impact since any redesign work is already done for FD1 | 2 - Reasonable estimate | ​The risk will be realized when the Collaboration decides to use the White Rabbit timing distribution system. | ​No mitigation plan needed. If the decision is to use White Rabbit, all the boards for the bottom CRP electronics would have already been redesigned for FD1. | ​If the risk is realized, we will need to purchase White Rabbit timing distribution modules as well as optical fibers. |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 427 | 0 | 42.7 | 0 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RU-131-FDC-FD-156 | LBNF / DUNE | Steel commodity fluctuations for APA production | ​If the commodity pricing of steel fluctuates, then the cost of building APA frames and transport frames will be impacted | Uncertainty | External Risk |  |  | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​All APA frame material and transport frame material has been purchased | 100% | 0 (N) - negligible technical impact | 3-point - triangular | -100 | 0 | 150 | 1-point - single value |  |  |  | ​131.02.02.02.07.01, 131.02.02.02.07.03​ | ​Estimate from steel commodity fluctuations. BOEs are not based on recent pricing (5/2021), but on historical pricing before COVID. Risk manages current large fluctuations. | 2 - Reasonable estimate |  | ​Monitor the market pricing​. ​Place orders earlier than planned if market conditions are favorable​. Delay placing orders if possible when market conditions are unfavorable. |  |  | 5 (VH) | 0 (N) | 0 (N) | 0 (Negligible) | 16.6667 | 0 | 16.7 | 0 | 2022-08-10 08:35 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-269 | LBNF / DUNE | [FD1-PD] Assembly delays in Brazil | ​IF PD module assembly takes longer or requires development of additional tooling to expedite assembly THEN fabrication of PD production modules may be delayed | Threat | External Risk | NO | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-08-01 | 2025-05-01 | ​Completion of PD module assembly | 15% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 1 |  | 3 | Risk hook: 13122.A14832 --> RT-131-FDC-FD-269 --> 13122.A14746 | ​Based on an estimated worst-case 25% increase in assembly time | 1 - Rough guess | ​Risk realized if observed during manufacturing are needed to meet the production schedule | ​Extensive practice assembly at UNICAMP facility. Identification of additional ​​personnel/institutions/resources in Brazil. ProtoDUNE Fabrication experience. ​​​ |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 2 | 0 | 0.3 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-271 | LBNF / DUNE | [FD1-PD] Delays in SiPM Fabrication/testing | ​IF delays occur in SiPM fabrication/testing in Europe THEN delivery of production PD modules may be delayed | Threat | External Risk | NO | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2022-11-29 | 2024-06-04 | ​Completion of assembly/testing of PD mounting boards​ | 5% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 1 |  | 3 | Risk hook: 13122.A12592 --> RT-131-FDC-FD-271 --> 13122.A12596 | ​Engineering estimate of potential delays of photosensor production | 2 - Reasonable estimate | ​​​​Delays are observed during SiPMs testing in Europe | ​Keep alive the option for two SiPM vendors. Extensive testing of ProtoDUNE size production lots. |  |  | 1 (VL) | 0 (N) | 1 (L) | 1 (Low) | 0 | 2 | 0 | 0.1 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-290 | LBNF / DUNE | [PM] Steel commodity fluctuations for APA production | ​If the commodity pricing of steel fluctuates, then the cost of building APA frames and transport frames will be impacted | Threat | External Risk |  | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete |  |  | ​All APA frame material and transport frame material has been purchased | 50% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 50 | 1-point - single value |  |  |  | ​131.02.02.02.07.01, 131.02.02.02.07.03 | ​​Estimate from steel commodity fluctuations. BOEs are not based on recent pricing (5/2021), but on historical pricing before COVID. Risk manages current large fluctuations. | 2 - Reasonable estimate |  | ​Monitor the market pricing​. ​Place orders earlier than planned if market conditions are favorable​. Delay placing orders if possible when market conditions are unfavorable.​ |  |  | 4 (H) | 0 (N) | 0 (N) | 0 (Negligible) | 25 | 0 | 12.5 | 0 | 2023-04-24 11:12 | Marco Verzocchi | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-281 | LBNF / DUNE | [COMP] Limited Networking from SURF to FNAL | If the networking from the DUNE Far Detector at SURF and FNAL computing in Batavia has limited capability at the time of initial detector commissioning, then the ability to operated the FD Data Acquisition system for at full capacity may not be possible and this would jeopardize the goal of operating and reading out​​ the FD for one week at 50% uptime. | Threat | External Risk | NO | Michael H Kirby | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2025-01-01 | 2027-10-30 | ​Once a network connection between SURF and FNAL has been established by ESNet and the Networking group from Core Computing Division has shown stable oeprations and bandwidth in excess of 10 Gb/s, this risk can be closed. | 5% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 1 |  | Risk hook: 13122.A366415 --> RT-131-FDC-FD-281 --> 13141.A10540 | ​The probability is based upon on-going discussions between the DUNE Computing Consortium, CCD Networking Group, and ESNet to establish network requirements for the DUNE experiment and a timeline for addressing those requirements. The schedule delay is estimated under the assumption that the data is transferred at 1 Gbit/s (current capability) instead of using the 10 Gbit/s link since it will take an additional 3 weeks to transfer the data from 3.5 days of FD operation at 1 Gbit/s. The only cost impact is a standing army cost that is taken into account at the project level. | 2 - Reasonable estimate | ​Failure for ESNet to receive funding for ungrading networking by 2025, and failure to provide 10 Gb/s networking by 2027. | ​Continued work between DUNE Computing Consortium, CCD Networking Group, and ESNet to review network requirements for the DUNE experiment, the timeline for network infrastructure improvements, and the securing of funds to implement those improvements. |  |  | 1 (VL) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 1 | 0 | 0.05 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-294 | LBNF / DUNE | [FD1-PDS] [CD3a] Additional DAPHNE (V3a) revision required | IF testing of DAPHNE V3 at CERN cold box demonstrate insufficient performance THEN an additional DAPHNE prototype module may be required | Threat | Technical Risk | NO | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-10-01 | 2024-08-30 | Completion of testing in CERN Cold Box | 10% | 0 (N) - negligible technical impact | 3-point - triangular | 100 | 175 | 250 | 3-point - triangular | 2 | 3 | 4 | Risk hook: 13122.A12218MS --> RT-131-FDC-FD-294 --> 13122.A370255 | Engineering estimate based on previous DAPHNE prototype upgrade development costs (DAPHNE V2a to V3). Assumes that due to previous QA efforts only minor changes are required, minimizing required engineering support | 2 - Reasonable estimate | This risk is realized if DAPHNE V3 is shown to have insufficient performance in CERN cold box testing | ​Extensive testing of DAPHNE V2 and V2a prototypes, as well as KRIA FPGA development kits | ​Development/testing of additional DAPHNE prototype may be required​ |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 175 | 3 | 17.5 | 0.3 | 2023-12-12 07:57 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-296 | LBNF / DUNE | [DAQ] FD DAQ and networking interface requires additional effort | ​If the interface between the network and DAQ does not allow for expected bandwidth through the DAQ dataflow nodes, then additional effort and additional dataflow servers may be needed in order to meet the requirements for readout of the detector. | Threat | Technical Risk | NO | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2027-08-01 | 2029-03-01 | ​Integration testing with the full DAQ and networking at SURF is complete and shows the required performance is met. | 10% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | 69 | 116.3 | 2-point - flat range | 0 |  | 3 | Rtotal risk probability should be equally split over the following risk hooks: 1) 13122.A366415 --> RT-131-FDC-FD-296-A --> 13122.01.02.305MS4 2)13122.A366427 --> RT-131-FDC-FD-296-B --> 13122.A366863 and 13122.A455638 (two successors) The risks FD-296-A and FD-296-B are uncorrelated | ​The cost estimates include the possibility of 50% to 100% more dataflow worker nodes are needed to meet throughput requirements; the schedule impact for includes time for installation and additional effort for traffic shaping development. Assume 1 FTE over the period of schedule delay. | 1 - Rough guess | ​Integration testing with the full DAQ and networking reveal that the required data bandwidth/throughput does not meet KPPs. | ​Regularly communicate with and develop detailed specifciations with networking experts prior to placing procurements. Develop a plan to work with networking experts during DAQ hardware commissioning phases to perform optimization as needed. | ​If a problem should arise, evaluate quickly if additional hardware will likely be required and start procurement processes. Begin development work to re-optimize DAQ application traffic to fit existing networking conditions. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 61.7667 | 1.5 | 6.2 | 0.15 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-297 | LBNF / DUNE | [DAQ] FD Data filter is not optimized or deployed efficiently | If the data filter design and development is not mature enough by the beginning of commissioning and it cannot be optimized or deployed efficiently, then additional effort will be needed to meet the requirements on readout of the detector and data volume. | Threat | Technical Risk | NO | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2027-10-01 | 2028-12-31 | ​A complete data filter is fully integrated with the DUNE DAQ software and integration tests show the required performance is met for target data reduction. | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 22.5 | 2-point - flat range | 0 |  | 3 | Risk hook: 13122.A455978 --> RT-131-FDC-FD-297 -->13122.A366417​ | ​Additional effort is needed in order to bring the data filter performance up to the needed level. Assume 1 FTE over a period of up to 3 months. | 1 - Rough guess | ​The data filter integration with the rest of the DAQ fails to operate as efficiently as needed, and requires additional design and/or development work. | ​Ensure data filter development work ends with full demonstration and integration with the DAQ well ahead of when it is needed for commissioning. | ​Plan design and development work to meet the requirements given existing integration testing results, and then perform development and re-test integration. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 11.25 | 1.5 | 1.1 | 0.15 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-013 | LBNF / DUNE | FS Detrimental Changes to the Overall DOE funding profile before CD-2 Baselining | ​IF DOE changes the overall project funding profile (not just one year's funding) before CD-2, THEN there could be a delay to the project completion | Threat | Management Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 0 - obsolete |  |  |  | 25% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 3-point - triangular | 0 | 12 | 18 | ​ 13122.01.02.276MS4 T4 MS - Cryostat #1 Manhole Sealed (Detector Fully Installed & Tested) 13124.KPPA9040 FD2 Complete | ​ There is a large range of possible changes to funding profile that would delay the project. Assess this as a schedule impact, since the funding delay directly affects the project schedule and the burn rate calculated from this. Based on the funding profile from the past, the project has experienced a one year delay more than once to the Near Site each year respectively. Assume impacted activities are NS, due to then-priority for FS. With a move to subprojects, and continued focus on funding FSCF activities in tech limited manner, this risk for FS activities is aimed at completing FD1 and FD2. | 2 - Reasonable estimate | ​DOE may need to act in response to overall program funding changes, changes in priority, delays in other projects, politicial situations | ​​Be alert to how to replan work quickly. Have backup plans ready, develop alternate scenarios. Use contingency if necessary and possible to keep critical path items on track. Be sure priorities are clear among project and collaboration leadership. | ​Identify critical path activities and respond to those first​. |  | 3 (M) | 0 (N) | 3 (H) | 3 (High) | 0 | 10 | 0 | 2.5 | 2022-08-10 08:35 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-109 | LBNF / DUNE | [PM] FS Medical Services Needed on-site | ​If it determined that medical services are needed on-site during installation, then additional staff or subcontracted services will be needed. | Threat | Management Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-04-01 | 2028-07-01 | ​when FD2 installation is complete | 20% | 0 (N) - negligible technical impact | 1-point - single value |  | 5500 |  | 1-point - single value |  | 0 |  | Risk hook: 131122.0404.M00030MS3 --> RT-131-FDC-PM-109 -->13141.A3622MS | Cost estimate is from the ES&H Division occupational medicine estimate included in the host lab taskforce report. Includes contract labor and M&S. | 2 - Reasonable estimate |  | In communciation with FERMI lab ES&H to provide and fund this service.​ | ​secure the services of a subcontracted medical service. |  | 2 (L) | 2 (M) | 0 (N) | 2 (Medium) | 5500 | 0 | 1100 | 0 | 2024-01-13 12:47 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-302 | LBNF / DUNE | [DAQ] FD CCM and DQM do not meet required specifications | ​If the DAQ CCM and DQM software are not able to meet the requirements to ensure high DAQ uptime for good quality data, then additional time will be needed in order to work on design/development. | Threat | Technical Risk | NO | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-09-01 | 2028-12-31 | ​The risk can be closed once integration activities with FD1 are complete and demonstrate the high uptime requirement of the KPP. | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 0 | 2 | 6 | Risk hook: 13122.A455978 --> RT-131-FDC-FD-302 -->13122.A366417​​ | ​Depending on the level of problems, a redesign of CCM and DQM services may be needed, which may take a month to two months. In all cases, development and integration work will be needed to improve and optimizie, which will likely take 2 months, but could take an additional two months. | 1 - Rough guess | ​Integration testing with the full DAQ reveals that the CCM and/or DQM software are not performant at scale. | ​Perform scaling tests at the ProtoDUNEs to ensure CCM and DQM infrastructure can support full detectors with some headroom. Focus final development, integration, and review activities on achieving performance at scale. | ​Perform measurements to understand where bottelnecks in CCM and DQM are. Plan design and development activities around fixing specific issues, and minimizing changes to interfaces to other subsystems that would require more effort. Quickly identify developers that can contribute to work. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 2.67 | 0 | 0.267 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-303 | LBNF / DUNE | [DAQ] FD1 FD2 Inability to efficiently do DAQ work remotely | ​If DAQ developers and support personnel are not able to connect to and work efficiently with the DAQ cluster at SURF remotely (for whatever reason, but including insufficient network connectivity, insufficient remote control for DAQ servers and hardware, etc.), then there could be a delay in integration and final development work for the DAQ at SURF. | Threat | External Risk | NO | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-07-01 | 2027-12-31 | ​This risk can be closed with the completion of installation and initial commissioning activities. | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 7 |  | 11.5 | 2-point - flat range | 1 |  | 2 | Risk hook: 13122.A455318 --> RT-131-FDC-FD-303 --> 13122.A366415​ | ​Expert work to update needs for remote work may require an additional 2-4 weeks (1 FTE, ~$3-7.5K). Expect that it may take between 2 and 4 weeks to identify and arrange proper personnel travel to SURF ($4K) for that work to be done. | 1 - Rough guess | ​When installing and performing initial commissioning of DAQ equipment, if tests of the remote access to the DAQ system fail and cannot be quickly debugged and fixed, then additional work will be needed. | ​Tools should be put in place and tested to allow for remote access to the DAQ systems and for collaborative work between personnel working at SURF in the cavern and DAQ experts that are either in Europe or in other US locations. Identify in advance what the response will be in as much detail as possible if there is a problem identified. Train personnel who will be located for activities at SURF already to handle trouble-shooting and fixing of such problems. | ​If a problem should arise, work quickly to get personnel at SURF to fix the problem and limit any schedule delays. Replan work to allow development to continue remotely without use of the system at SURF. |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 9.25 | 1.5 | 0.9 | 0.15 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-305 | LBNF / DUNE | [FD1-APA] US adds additional APA assembly scope due to insufficient rate of assembly in UK. | ​If the UK cannot produce APAs according to schedule then the US may have to assemble more APAs from UK-provided components | Threat | External Risk | NO | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-01-01 | 2027-07-01 | End of APA production | 30% | 0 (N) - negligible technical impact | 3-point - triangular | 150 | 300 | 600 | 1-point - single value |  | 0 |  | Risk hook: 13122.02.A139278 --> RT-131-FDC-FD-305 --> 13122.02.A139980​ | ​Each APA assembled at the University of Chicago costs approximately $150k in labor. The most likely number of APAs that would need to be assembled is 2, but the number could also be 4. There is insufficient time in the schedule between the end of APA 14 assembly and the end of installation to assemble more than 6 APAs. | 2 - Reasonable estimate | ​The UK is unable to keep to a production schedule that would ensure 137 APAs delivered to SURF before the end of installation | ​The risk is mitigated by the shipment of a fifth winder to Daresbury from PSL in late 2022 which increases the production capacity by 25%. Additionally, the UK could add more shifts to complete the production on time. The UK is considering adding a 6th winder. | ​A small number of APAs are assembled at the University of Chicago using UK provided components. |  | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 350 | 0 | 105 | 0 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-113 | LBNF / DUNE | [PM] Ross shaft logistics scheduling challenges impact FDC installation schedule | ​If the usage capacity of the Ross shaft cannot be optimized for both material and personnel, then FDC installation activities will be delayed and the schedule will be impacted. | Threat | Management Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-08-01 | 2028-10-01 | ​This risk can be closed when all underground far detector installation (#1 and #2) is complete, as those work phases represent the highest personnel and material loads that must utilize the Ross Shaft. | 40% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 3 | 4 | 6 | Risk hook: 13141.A82030 --> RT-131-FDC-PM-113 --> 13141.A82040 | ​No cost impact, but increased time will be needed to execute all installation activities, ranging from 3 to 6 months, based on approximately 12 months of installation work per FD. | 1 - Rough guess | Ross shaft scheduling capacity exceeds 90% due to inceased loading times, reduced shaft speed, mis-estimated loads/sequencing.​ | ​Instalation work occurs in phases, with each phase optimized as much as possible, with significant attention to Ross shaft scheduling. | ​If the risk occurs, the design for the schedule impacts will be realized.​ |  | 4 (H) | 0 (N) | 1 (L) | 2 (Medium) | 0 | 4.33 | 0 | 1.732 | 2024-01-13 12:41 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-126 | LBNF / DUNE | [PM] SURF underground drift expansion project impacts LBNF/DUNE project | ​If the SURF underground drift expansion project activities are delayed into the timeframe of the LBNF/DUNE FDC subproject, then FDC installation activities may be delayed due to competition for shaft access, ventilation, underground work spaces and underground occupancy. The full cavern excavation is included in a separate risk. | Threat | External Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-10-01 | 2024-11-01 | ​SDSTA expansion drift completed or otherwise scheduled not to conflict with FDC activities | 20% | 0 (N) - negligible technical impact | 3-point - triangular | 400 | 800 | 1600 | 3-point - triangular | 0.5 | 1 | 2 | ​Risk hook: 13141.A80010 (SS) --> RT-131-FDC-PM-126 --> 13141.A80030 | The cryostat installation costs are a CERN responsibility. However we expect that the project may have to cover the extra costs due to schedule delays. These amounts to $200k per week, which gives the cost estimates given above. Any other cost impact to the project comes from the schedule delay which are taken into account when translating the schedule delay into a cost impact | 2 - Reasonable estimate | ​SDSTA expansion extends beyond scheduled timeframe | delay FDC hiring; notify CERN as early as possible about delays prior to cryostat installation mobilization​ | ​rearrange sequence of activities to share shaft, other logistical resources |  | 2 (L) | 2 (M) | 0 (N) | 2 (Medium) | 933.3333 | 1.17 | 186.7 | 0.234 | 2024-01-13 12:34 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-171 | LBNF / DUNE | [PM] Insufficient scientific personnel for the FD1 integration and installation | ​If the institution participating in the FD1 consortia cannot recruit all the contributed scientific effort required during the integration and installation of the detector at SURF, the project may need to hire additional technicians, leading to both a cost increase (salaries) and a possible delay in the achievement of the KPPs (time required to hire the additional personnel) | Threat | Management Risk | YES | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-07-01 | 2028-03-31 | This risk can be closed at the end of the installation of FD1​ | 30% | 0 (N) - negligible technical impact | 2-point - flat range | 450 |  | 1800 | 2-point - flat range | 0 |  | 3 | ​Risk hook: 13141.A2580MS (SS) ---> RT-131-FDC-PM-171 --> 13141.A3340 | The probability of 30% assumes that one third of the research groups in the US go through the comparative reviews every year and are at risk of not getting their grant renewed. The cost impact assumes that between 3 and 12 additional technicians will be hired by the project at a cost of $150k per year (the upper limit represents 30% of the total scientific FTEs from US institutions). The schedule impact assumes that plans could be made ahead of the installation, but also that there could be problems with recruiting the personnel​ | 2 - Reasonable estimate | ​This risk is triggered when some of the US group who are planning to participate in the installation activities fail to get their research grant renewed | ​Several risk mitigations have been put in plance: a) conduct surveys of the available personpower (the last one was done in July 2025 in preparation of a NSG review) b) involve the collaboration to recruit additional personnel for these tasks c) inform the funding agencies of the institutions that have committed to the detector integration and installation work | Try again to recruit personnel from the collaboration, hire technicians​ |  | 3 (M) | 2 (M) | 1 (L) | 2 (Medium) | 1125 | 1.5 | 337.5 | 0.45 | 2024-01-13 12:33 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-182 | LBNF / DUNE | [PM] Oro Hondo shaft ventilation path is blocked (FDC) | IF the Oro Hondo shaft ventilation path becomes blocked THEN exhaust air requirements may not be met. This risk covers the FDC period after the completion of the BSI suproject (September 2025 to December 2028). Between the start of FDC work at SURF (October 2024 and August 2025) this risk is covered by risk RT-131-FSCF-BSI-015 | Threat | External Risk | YES | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2025-09-01 | 2030-09-30 | ​End of the project | 5% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 50000 | 2-point - flat range | 0 |  | 24 | ​Risk Hook: 13141.A2850MS (SS) ---> RT-131-FDC-PM-182 ---> 13141.A3340 | Based on the need to drill a new shaft to re-establish air flow. The probability of this risk being realized is taken to be proportioal to the probability that the risk RT-131-FSCF-BSI-015​ is realized, based on the relative duration of the time periods where the risks are active.​ | 1 - Rough guess | ​The shaft is not lined and is known to have a pile of debris at its bottom due to falling material. It was last scanned in 2010 that still leaves ~ 300 ft open to bottom of shaft. Concern is that the shaft condition is not monitored and if a large rock came loose, it could occlude the shaft, impacting most of the underground ventilation. The shaft has been stable for ~100 years.​ | Removal of debris pile at bottom; monitoring of height of pile; regular survey of shaft interior as part of monitoring plan to be cognizant of movement and potential problems. In October 2015. Ricky Allen, John Emick, and Bryce Pietzyk went to the 3500L during the scheduled fan shut down for the purpose of measuring the depth of rock buildup in the Oro Hondo Shaft. The measurement indicated that the top of the muck pile is at a level of 3845. This gives 345’ of space in the Oro Hondo Shaft for material to build up before it hinders ventilation. Since the measured muck elevation is almost identical to what the 2010 laser scan results show, material does not appear to be accumulating at a fast rate. Based upon the slow rate of fill Bryce recommends getting level measurements on an annual basis. June 15, 2016: SURF is planning to laser scan the ORO HONDO shaft in FY17 January 7, 2017: SURF performed a laser scan of the shaft and developed a process to allow future scans to be performed. The level of material is believed to be stable, though this provides a much more precise comparison for the future. Starting in 2018, annual scans are being performed. Scanned in April 2019. Awaiting results​ | ​​Abandon shaft, construct a new one.​​​ |  | 1 (VL) | 3 (H) | 3 (H) | 2 (Medium) | 25000 | 12 | 1250 | 0.6 | 2024-01-13 12:32 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-039 | LBNF / DUNE | FS Union Work Stoppage Delays Project at Far Site | ​If work stoppages occur on NS contracts with union labor, then the subsequent contract activities could be delayed, as well as the follow on project scope such as beamline or NS Cryo, or NSI. Then the overall project critical path may be delayed for the period equal to the work stoppage, increasing the standing army cost and increasing escalation on the delayed activiites. | Threat | Management Risk |  | Janet E. Bishop | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​​FSCF Construction complete - nominally set at end of 2024 for this purpose | 5% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 3-point - triangular | 0 | 0.25 | 0.5 | ​131122A200 Demobilization (BSI) | ​Based on past experience: When a work stoppage occurred on the NuMI Tunnels and Halls Project, no work was performed by the excavation contractor for ~ one week. The Fermilab Meson Roof Repair project was delayed when the non-union contractor was challenged by union officials and it took 2 weeks to sort how to satisfy the union. Any critical path delays have associated increases in level of effort work and associated costs. Based on past experience, assume 2 weeks as max, one week as most likely, and 0 as min. | 1 - Rough guess | ​The conventional facilities, cryo installation, and detector installation will utilize some combination of union contractors, non-union contractors, and laboratory/university technicians. The union contractors may either strike themselves, or may stop work to not cross the picket line of another union on strike. This has occurred at Fermilab, and caused delays of several days, even up to a week. Much of the construction/installation work is on the critical path, particularly the conventional facilities. | ​​Create good communications with union officials | ​​Establish means to provi​​​de alternate access during union work stoppages to keep other workers going.​ |  | 1 (VL) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0.25 | 0 | 0.0125 | 2022-08-10 08:32 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-040 | LBNF / DUNE | FS ESH Incident Stops Work Temporarily | ​If a contractor or laboratory/university employee is injured or if material is severely damaged in an ESH incident during FS work activities, the resulting investigation and implementation of corrective actions could cause schedule delays that impact the critical path | Threat | Technical Risk |  | Michael P Andrews | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​​end of physcial work on the project | 10% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 3-point - triangular | 1 | 3 | 6 | ​ ​​131122.0404.M00020MS T6 MS - FSCF - BSI - Construction Contract Begin Closeout ​131123.01.01.64MS T4 MS - LAr Cryostat #2 Construction Complete 13122.01.02.276MS4 T4 MS - Cryostat #1 Manhole Sealed (Detector Fully Installed & Tested) 13124.KPPA9040 FD2 Complete | ​ ​If a severe injury occurs, DOE or other stakeholders may require stopping specific work activities until they are satisfied the situation is stable and that work can resume. This could take some time, particularly if there is a fatality. The most likely estimate is that a 3 month schedule delay could occur, but perhaps as much as 6 months. If the affected activities are on the critical path, then the worst case condition is that the project has an overall schedule delay. Probability reduced to 10% and applied to multiple activities. Based on overall project duration of 9+ years and complexity of job sites. Discussions were held with KAJV and a consensus was reached on the impacts and probabilities related to construction period activities. | 1 - Rough guess | ​Although work will be planned and contractual provisions written to try to prevent any personnel injuries or unsafe environmental releases, there has been a history on DOE projects, including at Fermilab, of injuries and incidents. This includes unsafe construction practices, being distracted while working, being lax about attention to environmental regulatory requirements, not enforcing contract ESH provisions. | ​ Comprehensive use of ISM program across entire project including complete HA process; good ESH contractual provisions as well as enforcement; working up front during construction contracts to gain buy-in of construction contractor management to ESH issue prevention. Oversight roles and responsibilities for contractor and project team to include ensuring adequate training and attention to site specific risks, and compliance with their ESH program. This includes DOE oversight, Fermi oversight, CMGC safety manager oversight of their contractors - each organization oversees their facets. Fermilab and DOE provide review/oversight on regular basis. During contracting process, contractor provides with past project incident data which includes subtiers, EMRs, compensation carrier, ESH manuals, along with identified subtiers.This means only contractors with acceptable records and safety programs are able to be selected. All these items are already included in the base plan, mainly through management effort and processes already in place. for post-CF activities, use Work Planning & Controls processes to plan detailed installation. Training, Hazard Analyzes, oversight in place for coordination and safe work practices. | ​Work with DOE and other stakeholders to understand cause of incident/injury and take corrective action; work as possible to minimize impact on work.​ |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 3.33 | 0 | 0.333 | 2022-08-10 08:32 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-041 | LBNF / DUNE | FS Codes or standards change resulting in scope increases FS | ​​If new safety/environmental codes and standards are introduced over the life of the multi-year facility, then changes in design may be necessary that increase the scope. With increased scope, the cost and schedule will be increased. | Threat | External Risk |  | Janet E. Bishop | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​​Complete work at the Far Site | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 1750 | 2-point - flat range | 0 |  | 2 | ​ 131123.01.01.63MS T4 MS - LAr Cryostat #1 Start Construction 13141.A48710 Facility Modifications #1 13141.A47930 Installation of Detector Infrastructure on top of Warm Cryostat #1 | ​​Assume 0.5% impact on FSCF cost of 350M = 1750k. Assume modest impact on design time, mainly for infrastructure | 1 - Rough guess | ​Design codes and laws change during a long project, and sometimes these are imposed even when a faciltiy is almost through design or construction. | ​ ​5/24/16 TKL Status: FSCF staff has met with Lead, SD AHJ. CF and ES&H staff have met with FNAL FLS AHJ's on multiple occasions. Be congnizant of FESHM and building code changes to understand impacts as early as possible. | ​​revise design to meet codes if required.​ |  | 2 (L) | 2 (M) | 0 (N) | 2 (Medium) | 875 | 1 | 87.5 | 0.1 | 2022-08-10 08:32 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-042 | LBNF / DUNE | FS Underestimated Cost of Duties for Imports | ​If the Project has underestimated the cost of duties for FS imported deliverables (DOE purchases or IKC), then the Project will have to pay additional tariffs to the US Department of Commerce​ | Threat | External Risk |  | Janet E. Bishop | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​​All FS shipments complete for LBNF/DUNE | 50% | 0 (N) - negligible technical impact | 2-point - flat range | 100 |  | 5000 | 1-point - single value |  |  |  | ​ 131123.01.01.63MST4 MS - LAr Cryostat #1 Start Construction​ LAr Cryostat #2 Start Construction​ | ​ Estimates are detailed in dunedocdb1339 based on April 2021 material lists from LBNF/DUNE project team. FS estimates (cryostat, cryo & detector total ~$7m) Duties can be up to 25% of the market value. For the Far Site, this would impact cryostat, detector components and cryogenic purchases and IKC, with a range of 4% to 25% for various commodities and countries. Duty rates can change at any time, based on US policy, by country and import item. | 1 - Rough guess |  | ​ ​The Project is supporting DOE OHEP and OMB to obtain a HTS code for LBNF/DUNE. The Project and Fermilab are also following the example of SBN to use ITA-338P (Request for Duty-free entry of scientific instruments or apparatus) documentation for all IKC. Leveraging FNAL's import/export control manager​​​ |  |  | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 2550 | 0 | 1275 | 0 | 2022-08-10 08:32 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-043 | LBNF / DUNE | FS Ross skip hoist brakes failure | ​If the skip hoist brakes at Ross shaft fail, then the FS scope in progress at the time will stop and follow on work on the critical path will be delayed, causing standing army and escalation impacts for that follow on work. | Threat | Management Risk |  | Janet E. Bishop | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​​all FS project work complete | 1% | 0 (N) - negligible technical impact | 1-point - single value |  | 500 |  | 1-point - single value |  | 2 |  | ​ 131122.0403.M0025MS4 T4 MS - FSCF - TMI Contract Complete 131122.0404.M00020MS T6 MS - FSCF - BSI - Construction Contract Begin Closeout 131123.01.01.64MS T4 MS - LAr Cryostat #2 Construction Complete | ​ Since this risk is that the brakes fail to actuate in time to prevent crashing into the beams in the headframe and/or chairs at the 5000L, the cost is both for repair of the structures damaged as well as repalcement of the rope, which would potentially be over-stressed in this event. Follow up for the brakes is most likely adjustment and not​ actual repair. The impact is estimated at 2 months and $200k to repair damage in the headframe if the skip crashed into the crash beams, $100k to repair the chairs at the 5000L, and $200k to replace the ropes. It is not recommended to replace the skip brakes, since the probability of a failure is low and the cost of addressing a failure is lower than the cost of installing new brakes. This risk is tied to work scopes that would use the skips - excavation, BSI, and cryostat | 2 - Reasonable estimate | A failure of the braking system is likely to come in the form of a conveyance stopping too slowly in an emergency event. Since the skip hoist is used only for material moves, the result of this could be damage to equipment.​ | ​​Replace existing brakes with modern braking system described in Risk Supplement, but not recommended for this risk at this time. Note that sufficient redundancy exists in the hoist systems to prevent a free-falling skip situation.​ |  |  | 1 (VL) | 1 (L) | 0 (N) | 1 (Low) | 500 | 2 | 5 | 0.02 | 2022-08-10 08:32 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-044 | LBNF / DUNE | FS Ross skip drum cracks require repair | ​​If the Ross skip drum cracks require repair, then the ​FS work in progress at the time while the drum is repaired, as well as follow on critical path activities will be delayed, causing additional standing army cost and escalation to activiities on critical path. ​ | Threat | Management Risk |  | Janet E. Bishop | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​​all FS Project work complete​ | 1% | 0 (N) - negligible technical impact | 1-point - single value |  | 687 |  | 1-point - single value |  | 1.5 |  | ​ 131122.0403.M0025MS4 T4 MS - FSCF - TMI Contract Complete 131122.0404.M00020MS T6 MS - FSCF - BSI - Construction Contract Begin Closeout 131123.01.01.64MS T4 MS - LAr Cryostat #2 Construction Complete | ​ ​A proposal has been received by SURF to repair the skip drum cracks for $687k using a metal stitching technique. The discovery of propagating cracks upon routine inspection would result in the hoist being shut down to perform the same repairs as recommended for mitigation. This would have a similar cost, and may prevent excavation for up to 6 weeks if all cracks were repaired. Some subset of the cracks could be addressed instead, so this impact would be a maximum. This risk impacts work scope that uses the skips, so affects FSCF and cry | 2 - Reasonable estimate | ​The Ross skip hoist drum (where the wire rope is wound) was the first of its kind installed in the world. There is speculation that the rods used to tension the drum and keep it round were not properly torqued when installed, which may have contributed to a number of cracks propagating throughout the drum. | ​​monitoring and inspection to ensure if crack propagation increases, risk can be re-assessed and repairs made if required. The drum has cracks that are regularly monitored. Holes have been drilled at the ends of the cracks to reduce the risk of continued propagation, but there remains a risk that the higher demand for LBNF rock removal will result in a failure at one of these crack locations. Based on a low probability of failure, and a modest impact, it is recommended to accept this risk. | ​​​Repair means stitch welding existing cracks.​ |  | 1 (VL) | 1 (L) | 0 (N) | 1 (Low) | 687 | 1.5 | 6.9 | 0.015 | 2022-08-10 08:32 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-045 | LBNF / DUNE | FS Extended U.S. Congressional Continuing Resolution after CD-2 | ​IF there's an extended Congressional continuing resolution after CD-2 THEN limited availability of funding could delay the project if it doesn't have enough carryover funding. | Threat | Management Risk |  | Janet E. Bishop | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​​need to pass year of peak annual U.S. funding, presently FY25 | 10% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 3-point - triangular | 1 | 3 | 9 | ​ ​13111.10620MS - T4 MS - FY22 - Funding Available for Non-Obligated Tasks 13111.10640MS - T4 MS - FY23 - Funding Available for Non-Obligated Tasks 13111.20275MS - T4 MS - FY24 - Funding Available for Non-Obligated Tasks 13111.20325MS - T4 MS - FY25 - Funding Available for Non-Obligated T | ​This schedule estimate is based on the fact that the amount of the funding profile will not change after baselining the project since DOE commits to a project after CD-2 and tries very hard not to change the profile. But an extended CR beyond the 3 months planned into the project schedule could delay the ability to place larger contracts. There is a small chance that a single year could require large obligations early in the year when there is a year long continuing resolution (this is the scenario). | 2 - Reasonable estimate | ​Congressional continuing resolution | ​​Already have 3 months CR planned into schedule and major awards in January. Work with HEP to be clear about funding needed at beginning of each year to possibly front-load DOE Financial Plan for the project annually. Understand how to incrementally fund large procurements | ​​use cost contingency to keep critical path activities on track |  | 2 (L) | 0 (N) | 2 (M) | 2 (Medium) | 0 | 4.33 | 0 | 0.433 | 2022-08-10 08:32 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-046 | LBNF / DUNE | Old timber at Far Site combusts spontaneously | ​​IF spontaneous combustion events in old stopes and drifts occur, THEN work may have to stop underground, with consequential delays to that work as well as the follow on activities on the critical path, increasing standing army cost and escalation on the delayed activities. | Threat | Technical Risk |  | Janet E. Bishop | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​​Complete FS project | 1% | 1 (L) - somewhat substandard | 1-point - single value |  |  |  | 3-point - triangular | 2 | 4 | 6 | ​ 131122.0403.M0025MS4 T4 MS - FSCF - TMI Contract Complete 131122.0404.M00020MS T6 MS - FSCF - BSI - Construction Contract Begin Closeout 131123.01.01.64MS T4 MS - LAr Cryostat #2 Construction Complete 13122.01.02.276MS4 T4 MS - Cryostat #1 Manhole Sealed (Detector Fully Installed & Tested) 13124.KPPA9040 FD2 Complete​ | ​ ​schedule impact: if fire has to burn itself out, could have delay cost impact: cleanup costs covered by cooperative agreement Builders risk insurance during CF construction would likely pay some contractor cost | 1 - Rough guess | ​​Presence of old timber in underground spaces; policy of SURF ERT is to only directly fight fires if they pose direct threat to personnel | ​The mitigations current in place include continuous monitoring of carbon monoxide, controlled ventilation paths, and maintaining the water level above much of the lower levels. Evaluate if risk is insurable through the contractor's builder's risk policy. | ​​evacuate all personnel to safety; allow fire to self-extinguish; assess damage prior to re-entry​ |  | 1 (VL) | 0 (N) | 1 (L) | 1 (Low) | 0 | 4 | 0 | 0.04 | 2023-01-23 16:41 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-047 | LBNF / DUNE | FS SURF infrastructure projects impact LBNF/DUNE project | ​​If SURF infrastructure projects are scheduled during LBNF/DUNE project then construction or installation might be delayed | Threat | Management Risk |  | Janet E. Bishop | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​​completion of FS project | 50% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 750 | 2-point - flat range | 0 |  | 0.5 | ​ 131122.0403.M0025MS4 T4 MS - FSCF - TMI Contract Complete 131122.0404.M00020MS T6 MS - FSCF - BSI - Construction Contract Begin Closeout 131123.01.01.64MS T4 MS - LAr Cryostat #2 Construction Complete 13122.01.02.276MS4 T4 MS - Cryostat #1 Manhole Sealed (Detector Fully Installed & Tested) 13124.KPPA9040 FD2 Complete | ​​As example, Ross fire protection water line installationdid limit Ross site access. There was not a significant challenge or project delay. | 1 - Rough guess |  | ​​Utilize joint coordination team to coordinate various schedules ​ |  |  | 4 (H) | 1 (L) | 0 (N) | 2 (Medium) | 375 | 0.25 | 187.5 | 0.125 | 2022-08-10 08:32 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-048 | LBNF / DUNE | FS Unavailability of SURF or FRA supplied systems at SURF- low prob, high impact | ​IF systems at SURF don't work as required THEN schedule delays may occur.​ (ventilation or shaft systems) | Threat | External Risk |  | Janet E. Bishop | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​​completion of FS work | 5% | 0 (N) - negligible technical impact | 3-point - triangular | 2000 | 6000 | 12000 | 3-point - triangular | 2 | 6 | 12 | ​ 131122.0403.M0025MS4 T4 MS - FSCF - TMI Contract Complete 131122.0404.M00020MS T6 MS - FSCF - BSI - Construction Contract Begin Closeout 131123.01.01.64MS T4 MS - LAr Cryostat #2 Construction Complete 13122.01.02.276MS4 T4 MS - Cryostat #1 Manhole Sealed (Detector Fully Installed & Tested) 13124.KPPA9040 FD2 Complete | ​ Potential system failures that would affect the entire project include ventilation fan failure or failure to shaft ​systems​ (shaft, hoists, conveyances). Highest impact would be a fan failure, which could take 2 months for an electrical component, 6 months for a new fan wheel. 12 months to replace the cage. cost impact is based on contractor standing army costs of $1M/month low probability due to upgrades during Reliability Projects to provide new equipment | 1 - Rough guess | ​​shutdown of some part of ventilation system or hoisting system | ​Implement planned SURF Reliability​ Projects to increase uptime. Regular maintenance is necessary to be sure equipment is available. Several reliability projects associated with hoists have been added to the project scope to reduce this risk, but until completed these project themselves may increase the risk of a delayed start. Ensure spares are available on-site for repairs | ​​If risk occurs, mobilize temporary equipment such as generators, fans, utilize yates shaft for access​ |  | 1 (VL) | 3 (H) | 2 (M) | 2 (Medium) | 6666.6667 | 6.67 | 333.3 | 0.3335 | 2022-08-10 08:32 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-049 | LBNF / DUNE | FS General Security at SURF | ​If someone intent on harm is able to access critical infrastructure such as the hoist or electrical supply and harm critical systems, then access to the underground could be affected and the project delayed. | Threat | Management Risk |  | Janet E. Bishop | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​​end of project | 1% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 1000 | 2-point - flat range | 0 |  | 6 | ​ 131122.0403.M0025MS4 T4 MS - FSCF - TMI Contract Complete 131122.0404.M00020MS T6 MS - FSCF - BSI - Construction Contract Begin Closeout 131123.01.01.64MS T4 MS - LAr Cryostat #2 Construction Complete 13122.01.02.276MS4 T4 MS - Cryostat #1 Manhole Sealed (Detector Fully Installed & Tested) 13124.KPPA9040 FD2 Complete​ | ​​assume impairement of shaft infrastructure would require replacement of major components. LIkely would take some time to assess situation, procure parts, make repairs, say 6 months $1M. | 0 - Wild guess | ​​People intent on harm could be disgruntled employees or members of the public. They would have to be able to get unauthorized access to the systems. | ​​Robust security systems such as gate checks, building security systems, and controls on who can access equipment. HR processes to ensure discharged employees cannot re-access the site. These are captured in the project's updated and approved Security Vulnerability Assessement Report. | ​assess problems, make plan, repair damage​ |  | 1 (VL) | 1 (L) | 1 (L) | 1 (Low) | 500 | 3 | 5 | 0.03 | 2022-08-10 08:32 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-050 | LBNF / DUNE | FS Unavailability of SURF or FRA supplied systems & spaces at SURF- high prob, low imp | ​IF access to systems and spaces is not possible as required THEN schedule delays may occur.​ (hoist, power, brattices, pumping systems, fans, refuge chamber) | Threat | External Risk |  | Janet E. Bishop | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​Complete FS project​​ | 33% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | 250 | 500 | 3-point - triangular | 0 | 0.25 | 0.5 | ​ 131122.0403.M0021MS4 T4 MS - FSCF - North Cavern Excavation Complete 131122.0403.M0025MS4 T4 MS - FSCF - TMI Contract Complete 131122.0404.M00010MS T4 MS - FSCF - BSI - Construction Phase 1 LNTP (limited for mobe) 0d 131122.0404.M00040MS T6 MS - FSCF - BSI - HVAC System Complete - Handover to Cold Structure 131122.0404.M00020MS T6 MS - FSCF - BSI - Construction Contract Begin Closeout 13141.04.02.35MS T4 MS - Authorization for Use and Possession - South Cavern 13141.04.02.366MS T6 MS - FSCF Complete - Prepare to take over Ross Shaft schedule ​ 13141.A3620MS T4 MS - Authorization for Use and Possession of North Cavern 13141.01.01.65MS T4 MS - LAr Cryostat #1 Construction Complete 131123.01.01.64MS T4 MS - LAr Cryostat #2 Construction Complete 13122.01.02.276MS4 T4 MS - Cryostat #1 Manhole Sealed (Detector Fully Installed & Tested) 13124.KPPA9040 FD2 Complete​ | ​ Potential system failures that would affect the entire project include short repairs to infrastructure, temporary access restrictions, ventilation fan failure or failure to shaft ​systems​ (shaft, hoists, conveyances). Cost impact is based on contractor standing army cost​​s of $1M/month | 1 - Rough guess | ​SURF cannot provide these systems for LBNF/DUNE: ventilation, hoisting, water controls, access/logistics support. FRA cannot provide systems such as power, HVAC in the caverns | ​Implement planned SURF Reliability​ Projects to increase uptime. Regular maintenance is necessary to be sure equipment is available. Several reliability projects associated with hoists have been added to the project scope to reduce this risk, but until completed these project themselves may increase the risk of a delayed start.​ Ensure spares are available on-site for repairs | ​ ​If systems fail, wait for repairs to be made. April/May 2021: skip rope deformation resulted in 1 week shaft shutdown July 2021: hoist programming issue resulted in 2 day shaft shutdown |  | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 250 | 0.25 | 82.5 | 0.0825 | 2022-08-10 08:32 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FI-061 | LBNF / DUNE | [COMP] Computing Networking Surface | ​If, FNAL computing division takes responsibility for implementing and maintaining the FNAL @ SURF network on the surface, then the costs can be removed from the Project. ​ | Opportunity | Management Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2024-08-01 | 2029-09-28 | ​When work scope is complete or agreement with FNAL Core computing Division about scope responsibility | 10% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | -398 | -1977 | 1-point - single value |  | 0 |  | Risk hook: 13141.A3620MS --> RO-131-FDC-FI-061 --> 13141.A366975 ​ | ​estimate is provided by FNAL Core Computing Division for the SURFACE networking equipment (1 September 2021) peak of distribution is only maintenance of network equipment for FY26 to FY29, maximum is if also the purchase of the network equipment is included | 2 - Reasonable estimate | ​agreement on FNAL CCD deliverables | Add networking cost to FDC subproject​ |  |  | 2 (L) | 2 (M) | 0 (N) | 2 (Medium) | -791.6667 | 0 | -79.2 | 0 | 2023-12-12 07:57 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RO-131-FDC-FD2-038 | LBNF / DUNE | FD2 HVS Additional CERN labor for installation | ​If additional labor is provided by CERN during the underground installation period, it could reduce DUNE-US budget on costed installation labor. | Opportunity | External Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​Formal agreement is reached with CERN | 50% | 0 (N) - negligible technical impact | 2-point - flat range | 75 |  | 150 | 1-point - single value |  | 0 |  | ​13124.A​420 (first installation activity at SURF for the HVS) | There is strong likelyhood that CERN will provide ~2 persons 5 months to support FD2 HVS installation activities at SURF. But no formal agreement has been reached. | 2 - Reasonable estimate |  |  | ​HVS can potentially reduce costed labor budgeted in the FC assembly and installation activites. Or, the CERN staff could help out the cathode installation and mitigate the specific cathode labor shortage risk |  | 4 (H) | 0 (N) | 0 (N) | 0 (Negligible) | 112.5 | 0 | 56.3 | 0 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-051 | LBNF / DUNE | [FD2-HV] IN2P3 labor shortage | ​If IN2P3 cannot supply required underground labor for cathode installation, then there might be a delays in the cathode installation and in achieving the project's key performance parameters | Threat | External Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2027-12-10 | 2023-02-27 | ​The risk can be closed after IN2P3 signs a formal MoU with DUNE committing resources to the installation of FD2 | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 1.5 |  | Risk hook: 13143.50650 --> RT-131-FDC-FD2-051 --> 13143.50680 ​ | Cathode is entirely non-US so no direct cost impact. Assuming labor shortfall (4p instead of 6p) forces the cathode assembly and installation to be 50% longer (1.5 months) | 2 - Reasonable estimate | ​Unexpected budget shortage at IN2P3, problems with international travel | Firm up installation labor requirements, secure formal agreement with IN2P3​ | Stretch out the cathode installation by 50% |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 1.5 | 0 | 0.15 | 2023-12-12 07:57 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-061 | LBNF / DUNE | FD2 PDS Collaborating international partners deliver scope late | ​If international partner institutions deliver agreed upon scope late, then module assembly and ​​installation activities will be delayed or costed labor may be required to shorten timescale of remaining deliverables. | Threat | Management Risk |  | Ryan A Rivera | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft | 2025-01-01 | 2028-01-01 | ​This risk will be close once international partners have delivered on the agreed upon scope and the detector can be commissioned. | 10% | 1 (L) - somewhat substandard | 2-point - flat range | 100 |  | 750 | 2-point - flat range | 1 |  | 6 | 13124.A470T4 MS: 100% of Production Tile Assemblies constructed PDS 13124.A471T5 MS: Production Warm Electronics, Synchronization, and Monitoring System constructed - PDS | ​​(1) Probability is based on past international project experience. (2) Cost impact is estimate of adding 0.5 FTE technical costed effort at low end and 4 FTE technical costed effort at high end to construction activities (current baseline estimates 9 FTE of technical effort). (3) Schedule impacts is inefficiency estimate to onboard new technical labor.​ | 2 - Reasonable estimate | ​If international scope delivery is estimated to impact the critical path of the project. | ​Monthly reporting from collaborating institutions and regular analysis of Estimate to Complete. Regular working group meetings to align schedule and cost expectations. | ​If the risk is realized, adding technical effort to assist in construction and testing will be needed to avoid schedule delay. |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 425 | 3.5 | 42.5 | 0.35 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
C-RT-131-FDC-FD-004 | LBNF / DUNE | FD1 PD Student labor availability at CSU | ​If student labor is unavailable at CSU, the outside technicians will have to be hired for cable/rail fabrication | Threat | External Risk |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 10 |  | 30 | 2-point - flat range | 1 |  | 2 | 13122.A12548 (T6 MS 100% PD-APA kits complete) ​ | ​Assume a 1 to 3 month period of COVID-related limited access to labs for student labor, the result would be a schedule slip and might or might not require hiring temproary non-students with concomitant increase in cost to keet overall schedule. | 1 - Rough guess |  | ​Developing plans to spread assembly labor across multiple locations to reduce risk​ |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 20 | 1.5 | 2 | 0.15 | 2023-01-23 16:38 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
C-RT-131-FDC-FD-007 | LBNF / DUNE | FD1 PD Delay in module assembly and testing | ​If assembly and testing of modules is delayed due to COVID, then availability for installatuion at ProtoDUNE-II may be delayed and/or alternate (potentially US) sites found | Threat |  |  | David Wayne Warner | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 30% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 50 | 2-point - flat range | 1 |  | 3 | 13122.A12238MS ​ | ​Assume one or both vendors ecperience partial COVID shutdowns resulting in production delays. May require moving some module assembly/testing currently planned for Brazil to US to meet schedule. | 1 - Rough guess |  | ​Multiple sites in Brazil​ |  |  | 3 (M) | 0 (N) | 1 (L) | 1 (Low) | 25 | 2 | 7.5 | 0.6 | 2023-01-23 16:37 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
C-RT-131-FDC-CR-001 | LBNF / DUNE | Cryo integration activities take longer than planned. | ​If cryo integration activities at Far Site become more complex and more difficult working remotely, then they will take longer than planned. | Threat | Technical Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 25% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 0 | 2 | 4 | 131123.02.01.753,131123.02.01.763,131123.02.01.7732, 131123.02.02.1715,131123.02.02.679,131123.02.02.597. | At some point we may run into productivity issues, especially as the equipment to be integrated grows in complexity. It may become difficul to explain via Zoom/Phone.​ | 1 - Rough guess |  | ​Schedule periodic meetings and ensure good communication among team members.​ |  |  | 3 (M) | 0 (N) | 1 (L) | 1 (Low) | 0 | 2 | 0 | 0.5 | 2023-01-23 16:35 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
C-RT-131-FDC-CR-002 | LBNF / DUNE | Cryo: Partners work delayed for lack of LBNF support or COVID outbreak at partner's site or Coun | ​If partners require in person support by LBNF personnel or there isa COVID outbreak at the partner's site or in the partner's Country, then work may be delayed due to travel restrictions and impossibility to work and/or COVID lockdown. | Threat | External Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 4 | 6 | 8 | 131123.02.02.440MS - T6MS Condensers System Final Design Reviews Completed. 131123.02.02.441MS -T6MS Purification System Final Design Reviews Completed. 131123.02.02.442MS -T6MS LAr Pumps System Final Design Reviews Completed. 131123.02.02.443MS -T6MS Internal Cryogenics Final Design Reviews Completed. | ​Partners may require LBNF supervision to validate some tests or troubleshoot equipment. Schedule impact based on 14 day quarantine period for low. Health impacted for mid-point and bad reaction and possible hospitalization with extended recovery period for max. Schedule impact based on Brazil not being able to go to work site because of extensive lockdown | 1 - Rough guess |  | ​Schedule periodic meetings and ensure good communication.​ ​Follow COVID guidelines.​ |  |  | 4 (H) | 0 (N) | 2 (M) | 3 (High) | 0 | 6 | 0 | 3 | 2023-01-23 16:35 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
C-RT-131-FDC-CR-003 | LBNF / DUNE | Cryo: Partners work delayed for COVID outbreak at partner's site or Country. | ​If there is a COVID outbreak at the partner's site or in the partner's Country, then work may be delayed due to impossibility to work and/or COVID lockdown. | Threat | External Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 4 | 6 | 8 | 131123.02.03.4225 - Install LAr Filtration #1 - Equipment | Schedule impact based on 14 day quarantine period for low. Health impacted for mid-point and bad reaction and possible hospitalization with extended recovery period for max. Schedule impact based on Brazil - not being able to go to work site because of extensive lockdown | 1 - Rough guess |  | ​Follow COVID guidelines.​ |  |  | 4 (H) | 0 (N) | 2 (M) | 3 (High) | 0 | 6 | 0 | 3 | 2023-01-23 16:35 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
C-RT-131-FDC-FI-002 | LBNF / DUNE | I&I Incorporating Lessons Learned from ProtoDUNE-II | ​If ProtoDUNE-II activities cannot proceed according to plan due to travel restrictions or lab shutdown, then lessons learned cannot be incorporated into final designs for detector and integration | Threat |  |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  |  | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 1 |  | 3 | 13122.01.02.CD3NEW (CD3 ESAAB approval) ​ | ​Estimate is based on a a month-by-month extended design period for the FD installation team | 1 - Rough guess |  | ​ Utilize zoom for prototyping activities -- Resequence prototyping activities in the event of material (supply) delays -- Implement quarantine rules for travel​ |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 2 | 0 | 0.2 | 2023-01-23 16:40 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-052 | LBNF / DUNE | FD2 CRP US production takes longer than expected | ​​If the assembly of the CRP at the US production sites takes longer than estimated then either staff will have to continue working longer than expected (either overtime or extened duration) or another production site will need to be activated. | Threat | Technical Risk |  | Matthew P. Worcester | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft | 2024-01-01 | 2024-11-01 | ​​If the US assembly sites have been producing CRP for 4 months (starting in July 2024) and are on or ahead of the expected pace of 1 CRP per week, it can be assumed that the rest of production will stay on schedule (note that this does not include the risk of the materials suppliers failing to deliver, which is a separate risk). | 20% | 0 (N) - negligible technical impact | 2-point - flat range | 100 |  | 1000 | 1-point - single value |  | 0 |  | ​Completion of US CRP production. | ​(1) as there will be significant prototyping, we should have a strong idea of whether the US factories can sustain a 1 CRP per week pace. It is hard to estimate now, but the experience from assembling CRP #1 suggests 1 per week is possible for 1 CRP. (2) If the US factories experience slight delays, then engineering and technician effort may need to be maintained for longer than expected. A first minimum estimate is labor needs to be maintained (or added) at ~$50k per factory for two months to complete assembly, for $100k. If by Jan 2024 (7 months before expected factory startup) it is determined by prototyping that US production will be much slower than 1 CRP per week, a full 3rd factory needs to be prepared at an maximum estimated cost of $1000k. (3) Because the US CRP production is not driving the installation schedule, a slight delay in production will not impact installation. | 1 - Rough guess |  | ​​Prototype CRPs will be constructed in the US and Europe. Design choices will be made to simplify assembly where possible.​ |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 550 | 0 | 110 | 0 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-112 | LBNF / DUNE | [CRYO] Oxygen deficiency hazard (ODH) incident caused by rock fall from the cavern | If a rock falls from the ceiling and ruptures one of the feedthroughs on top of the cryostat then Argon gas is released at the 4850L of the SURF facility creating an Oxygen Deficiency Hazard (ODH). | Threat | Technical Risk | YES | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2028-01-01 |  | ​Completion of the fill. Completion of LBNF/DUNE. See explanation of estimate also. | 1% | 2 (M) - significantly substandard | 3-point - triangular | 0 | 50 | 100 | 3-point - triangular | 0 | 2 | 4 | Risk hook: 131123.04.02.46MS4 --> RT-131-FDC-CR-112 --> 131123.03.191 | ​Assessment of ODH risk and its mitigation are specifically covered by FESHM 4240. All “Catastrophic” failure probabilities identified in the LBNF ODH assessments are “Extremely Unlikely” (DOE Likelihood Classification per DOE STD 3009-2014). From Josh Willhite: "This includes the probability of rock falling on top of the cryostat and damaging some of the feedthroughs. Given the extensive ground support that will be employed, the early warning system provided by the shotcrete (4 inch deep), the planned ground monitoring system, the SURF plan for regularly scheduled (quarterly minimum) inspections of the undeground spaces, the relatively small spaces between structural members of the cryostat support, and the planned design of protective measures for the feedthroughs, the probability of occurrence is estimated to be a single point event of less than 1% over the 50 years life time of the facility." Cost impact is related to the need to replace the broken feedthrough. Schedule impact is related to the potential loss of work during the event until safe conditions are restored and the need to repair the broken feedthrough. | 1 - Rough guess | ​Rock falling from the ceiling and rupturing a feedthrough. | Following FESHM 4240 and working with ESH personnel from Fermilab and SURF, ODH monitoring and interlocks will be established to prevent exposure in identified ODH risk areas. All safety documentation is reviewed by a cryo safety panel before any cryogens can be introduced into any LBNF cryo equipment. The Detector's Cavern is currently classified as ODH Class 1. Personnel accessing it will also need proper training. An evacuation plan will be in place and will be triggered by the ODH alarm. Access will be restored once safe conditions are established. Consider the option of adding protection to each cryostat feedthrough. Estimate: $2,000/feedthrough for 243 feedthroughs in Single Phase configuration, for total cost of $486k. |  |  | 1 (VL) | 0 (N) | 1 (L) | 1 (Low) | 50 | 2 | 0.5 | 0.02 | 2024-01-13 12:49 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-054 | LBNF / DUNE | FD2 CRP interface card component shortage in the US | ​If the resistors and capacitors to populate the CRP interface cards are not available prior to production (after CD-3) then slightly different values than nominal will be purchased or interface card assembly will be delayed to wait for nominal values jeopardizing the US CRP performance and production. | Threat | External Risk |  | Matthew P. Worcester | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2023-10-01 | 2024-07-01 | ​All the CRP interface card components have been delivered to the assembly house. | 30% | 1 (L) - somewhat substandard | 2-point - flat range | 30 |  | 60 | 2-point - flat range | 0 |  | 8 | 13124.A479 | ​(1) Similar shortages have happened during previous prototype electronics assembly, e.g. protoDUNE. (2) If sufficient similiar valued resistors and capacitors can be ordered, then cost impact will be negligible, however the performance of the CRP could be impacted. If the correct components need to be rush ordered once they are in stock, cost could increase on the order of several thousand dollars. (3) If sufficient similiar valued resistors and capacitors can be ordered, then schedule impact will be negligible. If the correct components need to be waited for, then the interface card assembly could be delayed, which might delay the start of the US CRP assembly factories by 1-2 months. | 1 - Rough guess |  | ​Identify several vendors for the components. Purchase the correct components in smaller batches prior to CD-3.​ Expedited orders could be placed once the correct components are in stock. | ​ |  | 3 (M) | 0 (N) | 2 (M) | 2 (Medium) | 45 | 4 | 13.5 | 1.2 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-117 | LBNF / DUNE | [CRYO] Need to remove LAr during cryostat filling process when it is <25% full | ​If there is a need to empty Cryostat #1 during the filling process at <25% full, and there is no buffer tank or extra cryostat available to transfer the liquid argon immediately, then the project will have to vent the argon. | Threat | Technical Risk | YES | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2028-01-01 | 2028-12-31 |  | 2% | 0 (N) - negligible technical impact | 1-point - single value |  | 7707 |  | 1-point - single value |  | 3.5 |  | Risk hook: 131123.04.02.46MS4 --> RT-131-FDC-CR-117 --> 131123.03.191 | Details found in risk supplement form: $7.7M and 103 days (assuming to have at least additional 30 kW ofheating power to increase the boil off). Extensive cryostat QC keeps the probability low. | 2 - Reasonable estimate | Problem with the cryostat or FD | Prototype the cryostat & FD as much as possible. Extensive cryostat QC. | Vent the LAr, likely using heaters (assumed at least 30 kW of additional heating power in the current analysis). | docdb#1308 | 1 (VL) | 2 (M) | 1 (L) | 1 (Low) | 7707 | 3.5 | 154.1 | 0.07 | 2024-01-13 12:50 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-057 | LBNF / DUNE | [FD2-CRP] Bottom CRP support requires additional design consideration following Module 0 test. | ​If the supports for the bottom CRP are too weak to hold the weight of the CRP in module 0 then the supports will have to be reengineered jeopardizing the module 0 schedule.​​​ | Threat | Technical Risk |  | Matthew P. Worcester | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2022-10-01 | 2023-03-01 | ​The US bottom CRP have been successfully installed in module 0 resting on the supports. | 5% | 0 (N) - negligible technical impact | 1-point - single value |  | 108 |  | 2-point - flat range | 0 |  | 3 | Risk hook: 13124.A10832 --> RT-131-FDC-FD2-057 -->13124.A10834 ​ | ​(1)​ engineering and prototyping are planned before module 0 installation, so probability is low. (2) if the supports fail in module 0 then the reengineering is expected to require 50% FTE of the labor currently estimated (​​$65k) to design the supports and full fabrication costs of new supports. ($43k) for a total of $108k. (3) prototype supports are planned in Oct 2022; if those fail then reengineering and fabrication of new supports will be required, which will start from the engineering work already done and take an estimated 6 months. | 1 - Rough guess | ​Experience from Module 0 installation | ​Engineering by an experienced group is planned for module 0 supports. Prototype testing will be done before installation in module 0. | ​Accept risk for required redesign. ​​ |  | 1 (VL) | 0 (N) | 1 (L) | 1 (Low) | 108 | 1.5 | 5.4 | 0.075 | 2023-05-03 18:50 | Marco Verzocchi | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-126 | LBNF / DUNE | [CRYO] Significant ODH Event in Detector Cavern or CUC | ​If there is a significant ODH event then work will need to stop and workers will need to be evacuated. | Threat | Technical Risk | YES | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2028-06-30 |  | ​Completion of fill of cryostat #1 + stable operations after, including circulation of LAr through purification system. | 2% | 0 (N) - negligible technical impact | 2-point - flat range | 500 |  | 1000 | 2-point - flat range | 1 |  | 2 | Risk probability should be split equally over the following two risk hooks: 1) 131123.04.02.46MS4 --> RT-131-FDC-CR-126-A --> 131123.03.191 2) 131123.04.02.75MS --> RT-131-FDC-CR-126-B --> 131123.03.10.55 Risks CR-126-A and CR-126-B are uncorrelated | ​​Assessment of ODH risk and its mitigation are specifically covered by FESHM 4240. All “Catastrophic” failure probabilities identified in the LBNF ODH assessments are “Extremely Unlikely” (DOE Likelihood Classification per DOE STD 3009-2014). Total probability is estimated to be 1%. A significant ODH event will require an investigation and likely some repair. Min could be $500k and 1 mo. Max could be $1M and 2 mo. | 1 - Rough guess |  | ​Following FESHM 4240 and working with ESH personnel from Fermilab and SURF, ODH monitoring and interlocks will be established to prevent exposure in identified ODH risk areas. All safety documentation is reviewed by a cryo safety panel before any cryogens can be introduced into any LBNF cryo equipment. The Detector's Cavern is currently classified as ODH Class 1. Personnel accessing it will also need proper training. An evacuation plan will be in place and will be triggered by the ODH alarm. Access will be restored once safe conditions are established. |  |  | 1 (VL) | 1 (L) | 0 (N) | 1 (Low) | 750 | 1.5 | 15 | 0.03 | 2024-01-13 12:50 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-055 | LBNF / DUNE | FD2 CRP Bottom CRP shipping fixtures complexity | ​If the bottom CRP shipping fixtures need to be technically complex then more engineering effort will be needed than in planned​ | Threat | Technical Risk |  | Matthew P. Worcester | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved | 2022-12-01 | 2023-07-01 | ​Shipping bottom CRP to CERN for cold box test shows no issues developed on CRP during shipping or module 0 tests | 20% | 0 (N) - negligible technical impact | 1-point - single value |  | 87 |  | 1-point - single value |  | 0 |  | 13124.A10826 | ​(1) CRP are not expected require a complex shipping fixture like the APAs, so the risk is low (2) Current design of the bottom CRP shipping fixtures is 250h engineering hours, so as a central value assume that an increase in complexity will double that to 500h (3) The shipping fixtures have time to be designed and fabricated well before needed at the US factory sites, so the schedule is not impacted. | 1 - Rough guess |  | Design of shipping fixture for US CRP #4 for module 0 and shipping to CERN for cold box tests. |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 87 | 0 | 17.4 | 0 | 2023-01-23 16:39 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-023 | LBNF / DUNE | [PM] [CD3a] South Dakota Taxes for cryostat #1 warm structure and labor | ​If it is determined that South Dakota state sales and use tax (6.5%) and contractors excise tax (2%) must be paid for the cryostat #1 warm structure, then the Project will need to pay the taxes for this in-kind contribution from CERN. | Threat | External Risk | NO | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-06-01 | 2026-06-01 | Guidance from the SD Department of Revenue on how SD will treat this from a tax perspective. ​ | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 977 |  | 1-point - single value |  | 0 |  | Risk hook: 13141.A80030 --> RT-131-FDC-FI-023 --> 13141.A80040 | Material taxes are estimated at 8.5%, which includes 6.5% for sales and use tax and 2% for contractor's excise tax. Labor is estimated at only 2%. This risk is only for the warm materials / labor for cryostat #1. A separate risk captures the cold materials /installation for cryostat #1 and warm/cold materials/installation of cryostat #2. The values below are for warm/cold materials/installation of two cryostats. ​$21M in materials for warm structure​ - $1.793M $8M in labor for warm structure - $0.16M $22.5M in materials for the cold cryostat - $1.913M $16M in labor for the cold cryostat - $0.32M Total: $4.186M For this risk: $1.793M + $0.16 = $1.953/2 warm cryostats = $0.9765M = materials & labor for a single warm structure | 2 - Reasonable estimate |  | ​Fermilab counsel is working with SD tax counsel to engage with the SD Department of Revenue to ask for clarification and make arguments on why this should not be taxed. | None​ |  | 4 (H) | 1 (L) | 0 (N) | 2 (Medium) | 977 | 0 | 488.5 | 0 | 2023-12-12 07:57 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-172 | LBNF / DUNE | [CRYO] Need alternate LN2 supply for APA integrated cold boxes | ​If the Nitrogen System is delayed more than 6 months then we will need an alternate way to provide cooling to the APA integrated cold boxes and it will cost more. | Threat | External Risk | YES | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-06-01 | 2026-01-30 | ​Nitrogen System delivered to SURF. | 20% | 1 (L) - somewhat substandard | 1-point - single value |  | 655 |  | 1-point - single value |  | 0 |  | Risk hook: 13141.A2581MS --> RT-131-FDC-CR-172 --> 13141.A11599MS​ | ​If the Nitrogen system delivery is delayed more than 6 months, it may not be installed and commissioned on time to support the needs of the APA integrated cold boxes and an alternate LN2 delivery method is needed. Assuming to deliver LN2 via portable dewards, the following items are needed: - Equipment (3 portable dewars, 1 underground storage, valves, VJ pipes, connections to existing system): $343,121 ($FY22). - LN2 fluid for 75 tests: $116,494 ($FY22). - Labor to move portable dewards up/down, fill them up on surface, transfer to underground storage: 1,920 hr Mech Tech. Assumning a fully burden rate of $98.59/hr (in $FY21), the total is $195,723 (in $FY22). The total is then: $655,338. Portable dewars and underground storage are typically built to order, it may take up to 6 mo to receive them. If the potential delay is known ahead of time, it should be possible to start ordering long lead items early, hence the 0 schedule impact. It should be possible to know this information. | 3 - Solid estimate | ​Delay in manufacturing of the Nitrogen System. Delays in CD-3 approval, which delay the start of manufacturing. Other higher priority work for the selected vendor delays Nitrogen System activities (engineering, manufacturing, installation/commissioning). | ​Engage with vendor and ensure timely deliverable. Engage with DOE and project leadership to ensure FDC CD-3 DOE review and ESAAB approval are aligned with project needs. Monitor situation 9-12 mo before start of APA testing to ensure enough time is available to procure these items, if needed. |  |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 655 | 0 | 131 | 0 | 2024-01-13 12:51 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
C-RT-131-FDC-PM-001 | LBNF / DUNE | PM Cost increase due to supply chain issues in FY22 | ​If there are significant cost increases or delays due to supply chain issues that are going to affect the construction of the components for ProtoDUNE-II, then the pre-production costs will increase and commissioning of the detector will be delayed, with a cascade effect on the production readiness reviews of FD1.​ | Threat | External Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​This risk will be closed at the time of commissioning the ProtoDUNE-II detector | 50% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 1000 | 1-point - single value |  | 0 |  | ​13122.A1032 (installation of APAs in ProtoDUNE-II) | ​There are roughly $10M of M&S expenses in FY2022, but we estimate that only 10% of these are affected at this point by supply chain issues (these are the mostly in the area of electronics). We assume that there can be a delay of up to 4 months in the installation of ProtoDUNE-II since this risk is being actively managed by trying to anticipate purchase and use multiple vendors to procure the components that are problematic. | 1 - Rough guess | ​Issues with the procurement of parts needed in the fabrication of detector components for ProtoDUNE-II | ​Investigate multiple sources for the procurement of parts, use different components with minor design changes. This risk is already partially realized and has been actively managed for the past few months. | ​Small modifications to the design which would entail extra costs. Use of different vendors or recycling components from ProtoDUNE-II |  | 4 (H) | 1 (L) | 0 (N) | 2 (Medium) | 500 | 0 | 250 | 0 | 2023-01-23 16:41 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
C-RT-131-FDC-PM-002 | LBNF / DUNE | PM Cost increase due to supply chain issues in FY23 | If there are significant cost increases or delays due to supply chain issues that are going to affect the construction of the components for Module 0 of the vertical drift detector and for the pre-production of components for FD1, then the pre-production costs will increase and commissioning of the detector will be delayed, with a cascade effect on the production readiness reviews of FD2 and on the production of components for FD | Threat | External Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved |  |  | ​Commissioning of Module 0 in NP02 | 50% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 4000 | 1-point - single value |  | 0 |  | ​13124.A9018MS (Module 0 installation in NP02 complete) -100% of the cost impact, 50% of the schedule impact 13122.01.02.CD3NEW (CD3 ESAAB, drives FD1 construction) - 50% of the schedule impact | ​There are about $15M of M&S expenses in FY23, but we think that the supply chain issues affect at most $4M, which are expenses related to electronic components. We assume that the supplychain issues will cause a delay of up to 4 months. We are actively managing this risk trying to minimize its impact with the appropriate risk mitigation activities. | 1 - Rough guess | ​ ​Issues with the procurement of parts needed in the fabrication of detector components for Module 0 of FD2 and the pre-production of detector components for FD1. | ​Investigate multiple sources for the procurement of parts, use different components with minor design changes. This risk is already partially realized and has been actively managed for the past few month​ | ​mall modifications to the design which would entail extra costs. Use of different vendors or recycling components from ProtoDUNE-I​ or ProtoDUNE-II |  | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 2000 | 0 | 1000 | 0 | 2023-01-23 16:41 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-203 | LBNF / DUNE | [FD1-CE] Damage to the FEMBs / cold cables during or after integration with the APAs | ​If the FEMBs or the cold cables are damaged during or after the integration with the APAs then it will be necessary to replace the damaged parts, repeat the quality control process in the cavern, and if the damage takes place after the installation of the APAs inside the cryostat it may be necessary to take one (or more APAs) out of the cryostat. As a consequence there could be a schedule delay in the detector installation. | Threat | Technical Risk | YES | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-08-01 | 2026-09-30 | ​This risk will be closed when the cryostat for the 1st Single Phase Far Detector module is closed and the LAr filling starts, because at that point it will no longer be possible to access the FEMBs and the cables and replaced them. | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 50 |  | 175 | 2-point - flat range | 0.5 |  | 2.5 | Risk hook: 13122.2004.164.466 --> RT-131-FDC-FD-203 --> 13122.2004.164.340 | This risk catches two possible issues: one is the damage to the connection between FEMB and cold cables, which in ProtoDUNE had occurred with a probability close to 10%, and the second one is the damage to the cables during routing, which did not take place in ProtoDUNE (but cable routing is much more complex in DUNE). We assume that the first probability is reduced by a factor 10, but still assume a total probability of 10% to account for the much more complex cable routing in DUNE. To estimate the time impact we assume that one in ten APA pairs needs to go through a delay of 2 days before going through cold testing (delay of 15 days) as a minimum, and we settle on a maximum where five APA pairs are taken out of the cryostat after installation introducing a delay of 2 weeks each (delay of 50 days). We assume a flat distribution between the two. For the cost impact we assume that one third of the personnel in South Dakota is paid technician, and that the remaining two thirds receive some travel support, and assume a cost impact proportional to the delay. | 2 - Reasonable estimate | ​This risk has been realized already in ProtoDUNE (which prompted some design modifications aimed at reducing the occurrence of this risk). The risk is realized when there is a damage to either the FEMBs or the cables or both when performing the integration and installation activities. Examples of the risk realization: damage to the cable connector on the FEMB, cable not properly seated in the connector, damage to the cable during the routing of the cables through the side tubes of the APA or through the cryostat penetration, cable not properly seated on the CE flange. | ​Multiple actions have already been taken to reduce the occurrence of this risk. The connection between the signal cables and the FEMB has been redesigned to make it more robust and tests are planned to confirm the validity of the design. Multiple tests are planned to validate the cable routine strategy . ESD protections will be put in place to minimize the probability of such damage. Frequent testing of the electronic chain is planned at SURF to ensure that any problem is detected at the earliest possible stage, such that it can be fixed with minimal cost/schedule impact, including tests after routing the cables through the APA frames and tests in the cold box. Tests of the full readout chain for each APA are part of the installation strategy. These tests must be completed successfully prior to the installation of the next APA in the same column and prior to the deployment of the corresponding field cage element. | ​If the risk is realized then FEMBs or cables may have to be replaced and if needed the APA needs to be retested inside the Cold Box or in the worse case extracted from the cryostat. The integration setup at SURF allows for parallel processing of four APA pairs, while the schedule assumes that there are only three production lines. The fourth one can be used to recover APAs that have problems in the integration and installation. If needed, we can recuperate parts of the delays incurred by having additional personnel participating in the integration and installation activities. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 112.5 | 1.5 | 11.3 | 0.15 | 2024-01-13 12:57 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-173 | LBNF / DUNE | [CRYO] Insufficient lifting equipment for cryo installation | ​IF the infrastructure provided to lift cryo equipment for installation is insufficient THEN additional lifting equipment will need to be procured and/or installed AND it will cost more. | Threat | Management Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Managed | 4 - approved | 2025-10-01 | 2028-07-31 | ​Completion of installation of cryo equipment in CUC and Notrth/South Detector Caverns. | 35% | 1 (L) - somewhat substandard | 3-point - triangular | 0 | 557 | 916 | 1-point - single value |  | 0 |  | 131123.02.03.4205 Install Uninsulated GAr Pipes/Valves #1 - CUC. 131123.02.03.8607 Install Uninsulated GN2 Vent Pipes/Valves #1-2 - CUC. 131123.02.03.7051 Install Uninsulated Pipes #1. 131123.02.03.4585 Install VJ Argon Pipes/Valves - CUC and #1. 131123.02.03.4935 Install VJ Argon Pipes/Valves CUC and #2. 131123.02.03.7053 Install Uninsulated Pipes #2. 131123.02.03.7781 Install Uninsulated GAr Valves #2 - CUC. 131123.02.03.6565 Install PSVs, VSVs and Lockout Mechanisms #1. 131123.02.03.6585 Install GAr Boil-off and Venting Valves #1. 131123.02.03.6595 Install GN2 Supply to Insulation System (Valves and PSA) #1. 131123.02.03.6605 Install PSVs, VSVs and Lockout Mechanisms #2. 131123.02.03.6625 Install GAr Boil-off and Venting Valves #2. 131123.02.03.6635 Install GN2 Supply to Insulation System (Valves and PSA) #2. 131123.02.03.4225 Install LAr Filtration #1. 131123.02.03.4385 Install GAr Filtration #1-2. 131123.02.03.4265 Install LAr Filtration #2. 131123.02.03.4465 Install Regen Filtration #1. 131123.02.03.4505 Install Regen Filtration #2. 131123.02.03.4655 Install Argon Condensers System #1. 131123.02.03.4685 Install Condenser LAr Pumps #1. 131123.02.03.5005 Install Argon Condensers System #2. 131123.02.03.5985 Install Main LAr Pumps System #1. 131123.02.03.6045 Install Main LAr Pumps System #2. 131123.02.04.85MS T6 MS - Start Cryogenics Installation for Cryostat FD1. 131123.02.04.88MS T6 MS - Start Cryogenics Installation for Cryostat #2. | ​There are no cranes in the CUC. The monorails in the Detector Caverns are not sufficient to lift and position cryo equipment for installation. FSCF will leave rock bolts with the capability to add lifting eyes in the ceiling in strategic location (over cryo equipment in CUC, over mezzanines and main LAr circulation pumps in North and South Caverns). FS Integration provides basic lifting equipment, but it is likely not enough for Far Site Cryo installation. - Min Cost Impact: $0 (and 0 mo). Existing equipment is sufficient. Subcontractors provide any additional equipment that they might need. - Max Cost Impact: $916,044 (and 2 mo for mobi/demobi). Existing lifting equipment insufficient. Subcontractors do not provide addtional lifting equipment. Project needs to instrument SELECTED lifting eyes with backing plates and Double Swivel Shackles (DSS). We will know ahead of time whether this risk would be realized, so we will start procurement/installation to be ready on time. - Most likely Cost Impact: $556,650 (and1 mo for mobi/demobi).Existing lifting equipment insufficient. Subcontractors do not provide addtional lifting equipment. Project needs to instrument REDUCED number of lifting eyes with backing plates and Double Swivel Shackles. FSCF Cost (ARUP): $903/lifting eye (supply, grout, plate, installation). Double Swivel Shackles cost: $525/each (materials only). This means $378/each for installation/grout/plate. Assumed total cost per lifting eye: $903.40/each (added Loctite to secure connection). Selected number of lifting eyes: 1,014. Reduced number of lifting eyes: 616. Alternative approach is for FS Cryo to provide additional specialized lifting equipment. 1 Large capacity, high reach Telehandler and 1 Rough Terrain Scissor lift, including 3 years of maintenance (at 5%/year) is $441,485. Other equipment and/or more of the same might be needed. It fits with the lifting eyes estimate. | 2 - Reasonable estimate | ​Insufficient capabilities to lift cryo equipment during installation. | ​Installation analysis. Engage with potential vendors to define lifting needs and whether they can provide equipment or equipment is expected to be provided by project. |  | Summary cost estimate | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 491 | 0 | 171.9 | 0 | 2023-01-30 15:46 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-174 | LBNF / DUNE | [CRYO] Alternate plan Nitrogen System | ​IF the Nitrogen System Phase 2 proposals are not executable THEN the project will execute an alternate plan, which will cost more and delay the schedule. | Threat | External Risk |  | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 1 - draft | 2022-10-01 | 2023-03-31 | ​Nitrogen System Phase 2 award. | 5% | 1 (L) - somewhat substandard | 3-point - triangular | 0 | 11328 | 21356 | 3-point - triangular | 0 | 14 | 20 | ​131123.02.02.792 | ​Alternate Plan A: - Cost impact: +$11,328k over Nitrogen System updated ICE (May-2022). Includes additional labor (9 FTEs) for 76,908 hr and the following travel: + 1 trip/mo for 3 people for refrigeration system during design/manufacturing. + 1 trip every 2 mo for 2 people for LN2 tanks/distributionduring design/manufacturing. + 1 trip every 2 mo for Nitrogen Generation during design/manufacturing. - Schedule impact: +14 mo over current schedule. That includes: + +9 mo of ramp up time. + +2 mo for installation units 1-3. + +3 mo for commissioning units 1-3. Alternate Plan B: - Cost impact: +$21,356kover Nitrogen System updated ICE (May-2022). Includes additional labor (12 FTEs) for 113,152 hr and the following travel: + 1 trip/mo for 3 people for recycle compressors manufacturer during design/manufacturing. + 1 trip/mo for 3 people for rliquefiers manufacturer during design/manufacturing. + 1 trip every 2 mo for 2 people for LN2 tanks/distributionduring design/manufacturing. + 1 trip every 2 mo for Nitrogen Generation during design/manufacturing. - Schedule impact:+20 mo over current schedule. That includes: + +9 mo of ramp up time. + +6 mo of engineering. + +2 mo for installation units 1-3. + +3 mo for commissioning units 1-3. Details in attached documentation. | 3 - Solid estimate | ​Phase 2 Proposals are not executable (price exceeds fair and reasonable value, failure to reach agreement on T&Cs). | Updated Independent Cost Estimate (in progress) and submitted updated version to DOE. Negotiate agreeable T&C with vendors. Negotiate price reductions with vendors. |  | DocDB-25867 | 1 (VL) | 3 (H) | 3 (H) | 2 (Medium) | 10894.6667 | 11.33 | 544.7 | 0.5665 | 2023-07-06 08:45 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-025 | LBNF / DUNE | [PM] Delay to start of Installation | If the BSI and FDC concurrent schedules cannot be resolved, following the EXC AUP and BSI must proceed before FDC can begin underground work at SURF, then the cryostat and detector installation will be delayed.​ | Threat | Technical Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2022-08-01 | 2024-05-01 | ​When agreement regarding the precise work sequence is reached with FSCF-EXC and FSCF-BSI and their relevant subcontractors and implemented into the Project schedule. | 50% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 2-point - flat range | 1 |  | 3 | ​start of warm structure installation | ​To complete BSI in the N Cavern requires three months. | 2 - Reasonable estimate |  | FDC and FSCF-BSI/FSCF-EXC teams have developed a proposal to advance the FSCF-BSI work in the N Cavern by 3 months​ (FSCFBSI_1004). |  |  | 4 (H) | 0 (N) | 1 (L) | 2 (Medium) | 0 | 2 | 0 | 1 | 2023-02-01 14:38 | Jill Dornfeld | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-034 | LBNF / DUNE | [FD2-PDS] Additional on-project labor required during installation | If the contributed labor during detector construction installation is insufficient, then additional resources would be required otherwise the detector construction and installation would be delayed or performed poorly, which in turn could lead to late delivery or a sub-performant detector, reducing the chance that the key performance parameters of the project are met. | Threat | Management Risk | YES | Peter Shanahan | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-10-01 | 2028-09-30 | ​​​If detector construction and installation are completed with sufficient costed technical labor to meet baseline schedule, then this risk can be retired. | 30% | 0 (N) - negligible technical impact | 2-point - flat range | 100 |  | 500 | 1-point - single value |  | 1 |  | Risk hook: 13124.Z401458 --> RT-131-FDC-FD2-034 --> 13124.Z401460​​ | ​The risk probability assumes that each institution goes through a comparative review every 3 years and that a fraction of the grant proposals are not approved. (1) Probability is based on past experience materialization of uncosted effort. (2) Cost impact is estimate of adding 0.5 FTE technical costed effort at low end and 4 FTE technical costed effort at high end to installation activities (current baseline estimates 2 FTE of technical effort). (3) Schedule impacts is inefficiency estimate to onboard new technical labor. | 2 - Reasonable estimate | In the current plan a fraction of the consortium labor resources during construction are provided by scientific labor at participating US institutions and a fraction of the labor resources for installation are provided either by international partners or by scientists, postdocs, and graduate students at no cost to the project. If these resources are not available at the time of FD2 detector construction and installation there would be a problem that would need to be addressed by either accepting a delay in the installation or by reducing the quality control activities, or by adding labor supported by the project. | Estimates of the resources required during the construction and installation activities will be updated based on lessons learned from the detector construction and installation for module 0 at NP02. Efforts will continue to incorporate additional partners (both from US and international institutions) in the consortium and in particular in planning for the installation activities, to ensure that sufficient contributed resources will be available first during construction and later at the time of installation. Memoranda of understanding will be put in place between the consortium and the participating institution to detail the expected level of contributed effort available during the detector construction and during the installation process.​ | If at the time of the production readiness reviews it will become clear that the scientific effort required during detector construction is insufficient, a baseline change request will be made to increase the labor resources required during the detector construction. Similarly, if a few months ahead of the beginning of installation the risk is realized, a baseline change request will be made to increase the labor resources supported by the DOE project required for installation. This needs to be done at the latest a few months ahead of the beginning of installation to allow for the recruiting and the training of the new personnel. |  | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 300 | 1 | 90 | 0.3 | 2024-01-13 13:00 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-059 | LBNF / DUNE | [FD2-CRP] Insufficient contributed labor for the installation of bottom CRP in FD2 | ​If the contributed / scientific labor needed during the installation of the bottom CRP is not sufficient to meet the requirements then the installation of the bottom CRPs may be delayed, with a consequence on the timeline for the completion of the FD2 key performance paramters | Threat | External Risk | YES | Matthew P. Worcester | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2027-10-01 | 2028-06-30 | ​This risk can be closed when sufficient contributed / scientific resources are identified within the CRP consortium and the DUNE collaboration to reach the level required to proceed with the installation plan | 30% | 0 (N) - negligible technical impact | 2-point - flat range | 25 |  | 75 | 2-point - flat range | 0.5 |  | 2.5 | Risk hook: 13143.50950 (SS) --> RT-131-FDC-FD2-059 -->13124.A367262X | We make the assumption that the contributed labor comes from institutions that see their grant renewed every 3 years and assume that one institution out of three may fail to get all the support they want from their funding agency (30% probability). We then estimate that additional personnel will have to be hired / trained (or most likely that some technicians from other groups will have to see their contracts extended) for one third of the uncosted labor durin installation (290h) plus two weeks of training (100h). This corresponds to a cost of $50k, and we apply a +/-50% variation on this number. We estimate the impact at the level of 2-10 weeks of delay (2 weeks in case we just need to retrain technicians that are already at SURF, 10 weeks in case we need to hire new personnel at the last minute)​ | 2 - Reasonable estimate | ​This risk is triggered by the lack of contributed labor for the installation process, which in turn could be caused by the fact that some groups do not see their base grant renewed. | ​This risk is being mitigated by trying to increase the number of institutions involved in the activities of the CRP consortium in the US, and encouraging them to participate in all the activities, which will also include the integration and installation activities at SURF. In addition MOUs will be put in place with the institutions in the CRP consortium, and the availability of the scientific / contributed labor for the installation activities at SURF will be monitored closely in the two years ahead of the installation, to ensure that possible problems are identified and addressed as early as possible, | ​If this risk is realized, the first response will be to see how much of the labor can be transferred to other members of the DUNE collaboration, including international partners that are already involved in the CRP consortium. If this is not sufficient some of the technicians hired to work in other areas could see their contracts extended to participate in the installation of the bottom CRPs that are one of the last elements to be installed. By monitoring closely the availability of the scientific / contributed labor it should be possible to plan ahead for the need to extend contracts / hire new people and avoid delays. |  | 3 (M) | 0 (N) | 1 (L) | 1 (Low) | 50 | 1.5 | 15 | 0.45 | 2024-01-13 12:59 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-291 | LBNF / DUNE | FD1 APA Delay in UK Production During Final Year | ​If there are delays in UK APA production then all DUNE US KPPs are threatened, overall project completion date is threatened, and start of physics program will be delayed. This risk accounts for delays realized before the start of installation work at SURF. | Threat | External Risk |  | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2026-01-05 | 2027-01-04 | All APAs are delivered to SURF | 20% | 0 (N) - negligible technical impact | 3-point - triangular | 110 | 220 | 440 | 3-point - triangular | 0.5 | 1 | 2 | ​13141.A1210 (beginning of APA installation - the decision whether to transfer the construction of some APAs to the US will be taken at that time) | ​The last 30 UK APAs, approximately 20% of their total production, will finish in the 6 months leading up to installation. The US could make up to 2 APAs to cover UK delays during this time. Any other mitigation would likely require sending funds to the UK. The 3-point impact function for the assumed schedule delay is equivalent to a need of production of 1, 2, and 4 APAs. Cost assumptions for APA production is $110 of labor with the UK assumed to provide all components. | 2 - Reasonable estimate | ​The UK schedule currently shows delay with respect to the needed installation dates. The UK is unable to have more than 4 winders, unable to increase production rates.​ Any foreseeable increase in production efficiency (estimated max 10%) will not likely be able to compensate the observed delays in production once maintenance and unforeseen downtime is taken into account.​ | ​The risk is most effectively mitigated by producing an adequate number of APAs at a US institution. The US will have two production sites which are both scheduled to finish production in sufficient time to wind additional APAs before the end of installation. If more APAs are needed than can be produced at US institutions, funds will have to be sent to the UK to speed up production there as they have more available APA winders. | ​If the risk is realized prior to April 2026, we can transfer the production of a number of APAs to the US, using UK components. If the risk is realized late in 2026 the only solution is to take the delay in the installation.​ |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 256.6667 | 1.17 | 51.3 | 0.234 | 2023-01-23 16:36 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-071 | LBNF / DUNE | [FD2-BDE] FD2 CE damage to the FEMBs / cold cables during or after CRP installation at SURF | ​​If the FEMBs or the cold cables are damaged during or after installation of the CRPs inside the cryostat then it will be necessary to replace the damaged parts, repeat the quality control process in the cavern, and if the damage takes place after the installation of the CRPs inside the cryostat it may be necessary to take one (or more CRPs) out of the cryostat. As a consequence there could be a schedule delay in the detector installation. | Threat | Technical Risk | YES | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-01-10 | 2028-08-18 | ​This risk will be closed when the cryostat for FD2 is closed and the LAr filling starts, because at that point it will no longer be possible to access the FEMBs and the cables and replaced them. | 5% | 1 (L) - somewhat substandard | 2-point - flat range | 25 |  | 70 | 2-point - flat range | 0.25 |  | 1 | Risk hook: 13124.9.6.1 --> RT-131-FDC-FD2-071 --> 13124.9.8.1​ | ​This risk catches two possible issues: one is the damage to the FEMBs on the CRP inside the cryostat and the second one is damage to the 25m cables. If FEMB(s) needs to be replaced on a CRP already installed inside the cryostat, it may require uninstalling and moving multiple CRPs to replace the FEMBs. If cables on the vertical cable tray if damaged, it's impractical to re-run a new set of cables given that the Field Cage, Top CRP, and cathode are in the way. We'll need to re-route the spare cables to replace the damaged cables. The expectation is that if it takes more than one month to perform the operation, we will likely live with the problem. The cost impact is mostly to cover the paid technicians, and additional travel support for the onsite installation crew for the delay. | 2 - Reasonable estimate | ​The risk is realized when there is a damage to either the FEMBs or the cables or both when performing the integration and installation activities. Examples of the risk realization: damage to the cable connector on the FEMB, cable not properly seated in the connector, damage to the cable during the routing or through the cryostat penetration, cable not properly seated on the CE flange. | ​Multiple actions have already been taken to reduce the occurrence of this risk. The connection between the signal cables and the FEMB has been redesigned to make it more robust and tests are planned to confirm the validity of the design. Multiple tests are planned to validate the cable routine strategy. Patch panels are incorporated on the CRPs to simplify the cable connections to the CRPs. ESD protections will be put in place to minimize the probability of such damage. Frequent testing of the electronic chain is planned at SURF to ensure that any problem is detected at the earliest possible stage, such that it can be fixed with minimal cost/schedule impact. Tests of the full readout chain for each CRP are part of the installation strategy. We also plan to include additional spare signal and power cables in the cable bundles. | ​​If the risk is realized then FEMBs or cables may have to be replaced. Depending on the issue, CRP(s) may need to be moved to have access to the FEMB or spare cables. If needed, we can recuperate parts of the delays incurred by having additional personnel participating in the integration and installation activities.​ |  | 1 (VL) | 0 (N) | 0 (N) | 1 (Low) | 47.5 | 0.63 | 2.4 | 0.0315 | 2024-01-13 12:59 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-292 | LBNF / DUNE | [DAQ] DAQ: Data writing performance insufficient | ​If the baseline dataflow storage systems cannot write data at the required rate, more performant systems will need to be purchased, which will have a higher cost. | Threat | Technical Risk |  | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2025-07-14 | 2025-08-14 | ​Data-writing tests show that the required data-writing speed can be achieved with baseline-design storage servers. | 20% | 0 (N) - negligible technical impact | 3-point - triangular | 100 | 200 | 350 | 1-point - single value |  | 0 |  | ​13122.A366573 | ​Probability is a rough estimate based on prior experience. Cost impactis based on quote of $65K for a SSD-based storage server, which is $25K more than the baseline design cost. Cor cost, assume a three-point impact for between 2(min), 4(most likely) and 7 (all) upgraded servers per FD (which is then x2 for both FD1 and FD2). | 2 - Reasonable estimate |  | ​Perform early testing of candidate storage systems and software for data-writing, and include time for development and optimization of software-writing capabilities. Have assessments of data-writing capabilities be included in planned reviews (Final Design Review, Production Readiness Review). | Perform early re-testing of upgraded server systems to ensure that disk-writing rate can be achieved, which should happen alongside general integration testing to not extend schedule. |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 216.6667 | 0 | 43.3 | 0 | 2023-02-01 09:10 | Jill Dornfeld | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-063 | LBNF / DUNE | [I&I] Component re-work required during FD2 installation | ​If a top CRP module needs to be removed and repaired after cabling in the cryostat then the support structure must be uncabled, removed, and new CRP installed. The installation needs to then be repeated. | Threat | Technical Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft | 2027-05-12 | 2027-08-12 | ​Completion of the T_CRP installation and noise verificaiton test. | 30% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 1-point - single value |  | 0.75 |  | ​13143.50590 Final Verification Cryostat low noise environment Test | ​If a top CRP of cathode module needs to be removed and replaced after cabling then it will require 16 shifts (8 calendar days) to remove and replace the super structure with modules. This is twice the estimate for the intitial installation. There are 16 CRP support structures so 30% corresponds to a probability of ~2% per superstructure installaiton. This refelects a relatively low probability which has many oportunities to occur. | 1 - Rough guess |  | ​Module-0 prototype installation. |  |  | 3 (M) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0.75 | 0 | 0.225 | 2023-05-09 09:54 | Jill Dornfeld | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-062 | LBNF / DUNE | [FD2] installation labor peaks cause schedule delay | ​If the required manpower exceeds the available power in a week then the schedule must be extended. | Threat | Management Risk |  | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft | 2027-04-13 | 2028-02-21 | ​Completion of FD2 detector installation | 100% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 2-point - flat range | 2 |  | 3 | Start of CRP installation​ 13143.50170 Cleanup Step 1 13143.50600 Cathode survey and Cleanup SS installation 13143.50910 Complete Install Field Cage Super Module 23/24 - West End wall 13143.51140 Installation B_CRP Row 20 | ​The person power at the far site is limited by the staff based on the hiring plan. The schedule has variations in required manpower that are not completely leveled and some unexpected loss in staff is expected of the installation period. Unlike FD1 where schedule overruns can be compensated with Friday Saturday overtime with 6-day weeks on FD2 schedule overruns will cause schedule delays. The fluctuations in manpower in the schedule are typically a small fraction of the total manpower so delays of one week periods would be likely if there are manpower shortages that cannot be addressed by replanning the daily activities. The delays would likely be realized a the ends of the cryostat top, Step1 and Step 2. Possible delays in Step 3 are covered by the risk of delaying row 20. ​ | 1 - Rough guess |  |  |  |  | 5 (VH) | 0 (N) | 1 (L) | 2 (Medium) | 0 | 2.5 | 0 | 2.5 | 2023-01-31 15:06 | Jill Dornfeld | Item | org/ocoo/ippm/Lists/Risk Register
RU-131-FDC-PM-021 | LBNF / DUNE | [PM] [CD3a] Anomalous inflation impact on the FDC CD-3a costs | If the inflation between Spring 2022 and Spring 2023 is larger than the currently assumed escalation costs, the funding for the CD-3a scope of the FDC subproject sill not be sufficient for covering all the costs. This would lead to a delay in the producement of the long lead items, negating the advantages of the CD-3a request, which in the long term could cause additional costs and delays in the achievement of the KPPs​ | Uncertainty | External Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved | 2023-04-01 | 2024-03-31 | ​This risk can be closed once all the CD-3a procurements have been completed | 100% | 0 (N) - negligible technical impact | 3-point - triangular | -118 | 0 | 217 | 1-point - single value |  | 0 |  | Risk hook: 13122.A48260 --> RU-131-FDC-PM-021 --> 13122.01.02.CD23aNEW This risk should be used only for a CD-3a specific risk MC. In case the risk MC is run over the entire schedule, this risk should be excluded to avoid double counting.​ ​​​​For the moment this risk hook is not implemented in MC. It will be implemented only if we rerun the CD-3a risk MC.​ | The cost impact is estimated using the OPSS study of inflation that assumes that M&S expenditures may increase between 2.2 and 5.3% between FY2022 and FY2023, and that labor rates may increase between 3 and 6.7%. Our base cost assumes increases of 3.3% for M&S and 4.3% for labor, and the fluctuations around those values correspond to the range of -$118 and +$217k. | - Not yet defined - |  | ​There are few mitigations that can be put in place, like trying to place the orders at an optimal time | The only risk response if the costs are higher than planned is to pay more. We cannot delay the purchases in the hope that prices will go down​ |  | 5 (VH) | 1 (L) | 0 (N) | 2 (Medium) | 33 | 0 | 33 | 0 | 2023-05-16 04:27 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-293 | LBNF / DUNE | [FD1] Component re-work required during FD1 installation | ​If problems are discoverd during installation to detector components then delays may occur in the detector installation process. | Threat | Technical Risk |  | Janet E. Bishop | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​Detector install complete | 30% | 0 (N) - negligible technical impact | 1-point - single value |  |  |  | 3-point - triangular | 0 | 0.75 | 1.5 | ​Detector install |  | - Not yet defined - |  |  |  |  | 3 (M) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0.75 | 0 | 0.225 | 2023-05-09 09:54 | Jill Dornfeld | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-225 | LBNF / DUNE | [FD1-HV] Damage to the resistive Kapton film on the CPA - need for additional spares | If the resistive surfaces of the CPA are damaged beyond that covered by the spares, then there will be a need for additional material affecting the cost and schedule. | Threat | Technical Risk | YES | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-10-04 | 2027-04-20 | ​The risk can be retired after the CPAs are installed. | 10% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 22 | 2-point - flat range | 0 |  | 3 | Risk hook: 13122.A129730MS450 --> RT-131-FDC-FD-225 --> 13122.A13337 | Replacement of the resistive panels is non-US. Depending on when damage occurred, it could have no schedule impact (before CPA assembly), or up to 3 months (2 month replacement fabrication, 1 month reassembly). Reassembly labor cost is 22k for 10% of CPAs. ​ | 1 - Rough guess | ​CPAs are damaged in number beyond that of the spares. | ​Careful handling, and crate design. Experience with mechanical mock-ups and ProtoDUNE. |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 11 | 1.5 | 1.1 | 0.15 | 2024-01-13 12:57 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-247 | LBNF / DUNE | [FD1-CE] Need additional ASICs or FEMB test stands to speed up production | ​If the ASIC or FEMB construction starts too late, the TPC electronics components may not be available in time for integration with the APAs, delaying the detector installation and therefore affecting the achievement of the threshold and objective KPPs | Threat | Management Risk | YES | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-10-01 | 2026-08-31 | ​This risk can be closed when it becomes clear that having 2 test sites for each ASIC flavor and 5 test sites for the FEMBs is sufficient to meet the FD1 and FD2 production deadlines and have the TPC electronics components available in time for installation on the APAs at SURF | 20% | 0 (N) - negligible technical impact | 3-point - triangular | 140 | 280 | 420 | 1-point - single value |  | 0 |  | Risk hook: ​13122.2004.132.340 --> RT-131-FDC-FD-247 --> 13122.2004.132.350, 360, 370, 380, 390 (need all 5 successors) | ​We assume the cost of equipping one additional ASIC or FEMB test site at $140k per site, and we estimate the support throughout the production at $140k per site. The minimal assumption is that we encounter 50% of the total cost, the maximum is that we encounter 150% of the total cost. | 2 - Reasonable estimate | ​This risk would be realized if there are major delays with the beginning of the production, caused either by external reasons (limited funding for the detector construction because the funding is used for other purposes) or because there are delays in the preparation of the test stands and/or the training of the personnel. | ​Ensure that test stands are ready in a timely fashion and that they are exercised with pre-production components. | ​​If it becomes clear that there is going to be a need of compressing the production schedule, including the QC step, consider first increasing the number of shifts at the existing facilities, and plan for additional facilities only as a last resort. If it becomes clear that additional test sites are needed, start by setting them up using spare components for test stands, and then fabricate more components as needed to recover the spares. Train personnel as early as possible to ensure that the additional test stands become operational as quickly as possible. |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 280 | 0 | 56 | 0 | 2024-01-13 12:57 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-022 | LBNF / DUNE | [PM] [CD3a] Additional top down risk for CD-3a scope of FDC suproject | ​If there are any exceptional cost increases affecting the CD-3a scope that are not covered by the estimate uncertainty or by the risks covering inflation fluctuations arising from supply chain issues caused by the COVID pandemic or by the war in Ukraine, we may not be able to make all the procurements needed in time and we would have to wait for the CD-3 ESAAB, leading to a delay in the project execution. | Threat | External Risk |  | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Obsolete | 4 - approved | 2023-04-03 | 2024-03-31 | ​This risk can be closed when all the procurements covered in the CD-3a scope are complete | 50% | 0 (N) - negligible technical impact | 2-point - flat range | 990 |  | 1979 | 1-point - single value |  | 0 |  | Risk hook: 13122.A48260 --> RU-131-FDC-PM-021 --> 13122.01.02.CD23aNEW This risk should be used only for a CD-3a specific risk MC. In case the risk MC is run over the entire schedule, this risk should be excluded to avoid double counting.​ ​​For the moment this risk hook is not implemented in MC. It will be implemented only if we rerun the CD-3a risk MC. | ​We assume a cost increase between 10% and 20% of the total M&S expenditures planned as part of the CD-3a scope (after taking into account the FY22 to FY23 planned escalation rate the total M&S expenditures in the CD-3a scope amount to $9,896k and the 10% and 20% are $990k and $1979k) | 1 - Rough guess | ​This risk could take place if there is a resurgence of the COVID pandemic that further disrupts the supply chain. The risk can be similarly triggered by an extension of the war in Ukraine | ​The early procurement via CD-3a is already a risk mitigation in itself.​ As soon as we have the spending authorization we will try to place the orders in order to minimize the occurrence of this risk. |  |  | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 1484.5 | 0 | 742.3 | 0 | 2023-05-16 04:27 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-301 | LBNF / DUNE | [DAQ] FD1 SURF infrastructure stability impacts DAQ uptime | ​If the rooms and barracks housing DAQ equipment at SURF do not have sufficient performance or stability in cooling, power, and air quality, then this may affect the uptime of DAQ servers and cause a slowdown in integration work. | Threat | Technical Risk | YES | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-09-01 | 2028-03-01 | ​Integration testing with the full DAQ at SURF is complete | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 0 | 1 | 3 | Risk hook: 13122.A455318 --> RT-131-FDC-FD-301 -->13122.A366415 | ​Assuming stability issues create problems at 25% level for uptime, leading to needing 25% more time for integration work. No additional cost, as integration work cannot be done. | 1 - Rough guess | ​During integration testing with the full DAQ at SURF, instabilities in infrastructure cause a delay in being able to perform those activities. | ​Communicate DAQ services requirements clearly, including those that affect stability. Develop a plan for operations support to monitor stability issues and communicate as required. Plan integration testing activities such that some instability will not cause a complete halt in work. | ​Replan activities as needed to try to work around instabilities. Promptly communication problems during integration testing. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 1.33 | 0 | 0.133 | 2024-01-13 12:55 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-027 | LBNF / DUNE | [FDC] SURF underground access suspension due to weather | ​If underground access at SURF is restricted due to weather (snow, high winds, etc), then no work will occur underground and delays will be incurred. | Threat | External Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft | 2024-08-01 | 2030-12-31 | ​all FDC work complete | 100% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 3-point - triangular | 0.1 | 0.25 | 0.5 | finish of warm #1 finish of cold #2 finish of detector #1 finish of detector #2 finish of filling #1 | ​based on weather delays experienced during FSCF-EXC (CY2019 through CY2022) | 1 - Rough guess |  | ​ |  |  | 5 (VH) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0.28 | 0 | 0.28 | 2023-02-14 09:35 | Mohammed Elrafih | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-255 | LBNF / DUNE | [I&I] Delay in the availability of Slow Controls | ​If a dedicated team for the development and support of slow controls is not identified, then the integration and installation process at SURF will be delayed with an impact on the achievement of the KPPs | Threat | External Risk | NO | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2021-01-01 | 2026-10-15 | ​This risk can be closed when a fully operational slow control system is delivered and it has been demonstrated to operate according to the DUNE requirements. | 20% | 1 (L) - somewhat substandard | 2-point - flat range | 500 |  | 1000 | 1-point - single value |  | 0 |  | Risk hook: 13122.2004.161.260 --> RT-131-FDC-FI-255 --> 13122.2004.161.350​ | ​The cost impact is due to need to add resources to supplement integration and installation activities. | 1 - Rough guess | ​An appropriate team is not identified to take over the slow control project | ​A team of people should be identified to develop the slow control system for DUNE at the latest in 2024. The slow control system for ProtoDUNE may be supported by the CERN personnel and some of the software developed there may be used in DUNE, but there are scaling issues and possibly new hardware to be supported for DUNE. Early deployment of the slow control system at test sites and eventually at ProtoDUNE will also help mitigating the risk | ​If this risk is realized, personnel from the Fermilab projects control group should take over the responsibility for slow controls. |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 750 | 0 | 150 | 0 | 2024-01-13 11:13 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-001 | LBNF / DUNE | [I&I] Membrane Cryostat damaged during Detector Installation | If a detector component is dropped and damages the Membrane of the cryostat, then the membrane cryostat needs to be repaired | Threat | Technical Risk | YES | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-10-01 | 2028-06-30 | Detector install complete | 5% | 1 (L) - somewhat substandard | 3-point - triangular | 100 | 500 | 1000 | 2-point - flat range | 4 |  | 7 | Total probability should be equally split between the two risk hooks: 1) 13141.A81150MS --> RT-131-FDC-FI-001-A --> 13141.A2580MS 2) 13141.A85150 --> RT-131-FDC-FI-001-B --> 13143.A2580MS10 The risks FD-209-A and FD-209-B are uncorrelated | Once cryostat is damaged, cryostat manufacturer will need to be contracted to repair. DOE might have to pay for this contractor to complete the work. The cost impact is a rough guess based on the cost of the cold cryostat. FNAL procurement estimates it will take 3 months to process a contract of this value. Assume the process can be accelerated to 2mo. Assumed it will take around 1 to 2 months to repair any damage and one to three months to mobilize and aquire any required materials.​ | 1 - Rough guess | Mishandling of components, human error | Detailed installation procedures, detailed assembly testing performed in advance, false floor and temporary protection installed​. Minimize number of loose parts which can be dropped. Tools will be tethered. | ​Hire contractor to repair the damage |  | 1 (VL) | 1 (L) | 2 (M) | 1 (Low) | 533.3333 | 5.5 | 26.7 | 0.275 | 2024-01-13 12:31 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-307 | LBNF / DUNE | [FD1-HV] Field case profiles do not need alodine coating | ​Current plan includes the coating of the FC profiles. If ProtoDUNE-VD demonstrate no need for the coating, there will be cost saving to CERN, and early delivery of the profiles. | Opportunity | External Risk |  | Bo Yu | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft | 2024-01-01 | 2024-10-01 | ​FD1 FC profiles have been shipped to SURF. | 80% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | -2 |  | ​13122.A13226 (Ship FD1 FC profiles to SURF - CERN)​ | FC profile production is CERN scope so no US cost impact. Skipping the alodine coating step may speed up delivery of the FC profiles by 2 months. | 2 - Reasonable estimate | ​ProtoDUNE-VD shows NO need for the conductive coating on FC profiles | perform additional tests to evaluate the need for the coating | ​Skip the alodine coating step in FC profile fabrication process. |  | 5 (VH) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | -2 | 0 | -1.6 | 2023-02-01 15:06 | Jill Dornfeld | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-002 | LBNF / DUNE | [I&I] Detector failure during cooldown | If there is a significant failure of the detector components during cooling then the detector will need to be re-opened for repair​ | Threat | Technical Risk | YES | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2028-03-01 | 2029-12-31 | ​After cooldown of both FD1 and FD2 is complete | 5% | 1 (L) - somewhat substandard | 1-point - single value |  | 2500 |  | 3-point - triangular | 9 | 10 | 11 | Risk hook: a) 131123.04.04.03.17 --> RT-131-FDC-FI-002-A --> 131123.04.02.276MS b) 131123.04.04.04.47 --> RT-131-FDC-FI-002-B --> 131123.04.02.278MS​ (FF relationship) Split the probability in two, assign half to the first risk hook (purge and cooldown of FD1 ) and half to the second risk hook (purge and cooldown of FD2) | Time estiimate as follows: warm and inject breathable air into the cryostate (3mo) - open TCO 1mo, enter through the man holes and make repairs of accessible equipment 1-3mo, close TCO 1 mo, Purge and cool down 3mo. Cost estimate is 2M for opening and closing the TCO and 250k to re-establish a temporary cleanroom and provide access equipment. If a failure occures requiring repair it is likely in the HV system whoch would not require removing detector components. Probability estimate based on not experiencing this issue at previous LAr prototypes. | 2 - Reasonable estimate | ​Component not operating as expected during cooldown | Cold testing of all components before installation and continuous monitoring after installation | ​Evaluate impact on detector performance, determine if repair needed. If needed, wait for air to become breathable, enter cryostat and repair components. |  | 1 (VL) | 2 (M) | 2 (M) | 1 (Low) | 2500 | 10 | 125 | 0.5 | 2024-01-13 12:31 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-304 | LBNF / DUNE | [DAQ] FD2 Availability of DAQ personnel on site at SURF | ​​If not enough DAQ personnel are available on site at SURF during installation, there could be delays in these activities, which would then have an impact on the achievement of the KPPs​ | Threat |  |  | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 4 - approved |  |  | ​​This risk can be closed when the FD2 DAQ components used during installation have been installed and all the firmware/software servers have been commissioned. | 20% | 0 (?) - Not yet defined | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 1.25 | ​13122.A454725 | ​The total estimated time for installation is expected to be 3 months. If up to 40% of effort is not available, that will lead to a delay of 5 weeks. | 1 - Rough guess | ​If not enough DAQ personnel are available to assist in FD2 DAQ installation actiities, there will be a delay in the completion of the work. | ​Tools should be put in place to allow for remote access to the DAQ systems and for collaborative work between personnel working at SURF in the cavern and DAQ experts that are either in Europe or in other US locations. DAQ experts should be trained in such a way that there isn't a single person with a particular expertise that can help solve problems that are encountered during the integration and installation activities at SURF. This includes putting in place succession plans for DAQ experts. ​Involve the Fermilab visa office to address any issues related to visa problems. | ​​If this problem is caused by lack of travel funds, the DUNE project should consider providing travel support. If the problem is due to visa issues, try to get help from the Fermilab visa office. If the problem is caused by personnel leaving, identify and train a replacement. |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0.63 | 0 | 0.126 | 2023-02-01 10:33 | Jill Dornfeld | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-298 | LBNF / DUNE | [DAQ] Loss of expert DAQ personnel | ​If there is a loss of DAQ expert personnel without a suitable immedaite backup, then it will require time to identify and train up a new expert.​ | Threat | Management Risk |  | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 0 - obsolete | 2026-01-01 | 2026-12-31 | ​The risk can be closed once installation and integration activities at SURF are complete. | 20% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 0 | 1 | 3 | Risk hook: 13122.A451940 --> RT-131-FDC-FD-298 --> 13122.A455018 ​ | ​Assume that identifying/replacing an immediate replacement for a DAQ expert on critical activities may take up to a month, with some likelihood that additional shuffling of activities will lead to a longer (3 month) delay. | 1 - Rough guess | ​Unexpected / unplanned for loss of a critical DAQ expert. | ​Train a pool of experts and critical personnel in such a way that the loss of a particular person will not require significant time to identify and train new personnel. Document critical tasks to minimize time for training new people. | ​Identify people to perform critical expert tasks that have most impact on minimizing changes to cost and schedule. Replan activities as needed to avoid future delays. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 1.33 | 0 | 0.266 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-299 | LBNF / DUNE | [DAQ] Delivery of FD1 DAQ components are delayed due to supply chain or manufacturing issues | ​If there are significant supply chain or manufacturing issues, particularly for computing/electronics components, there can be a delay in the deliver of FD1 DAQ components. | Threat | External Risk |  | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​All FD1 DAQ components have been delivered. | 10% | 0 (?) - Not yet defined | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 3 | ​13122.A368947, 13122.A366573 | ​Most DAQ components are commodity servers or devices, and so expect that a delay may be of up to 3 months. | - Not yet defined - | ​In the procurement process, we are informed of a delay in the availability of DAQ components. | ​Initiate procurements with enough lead-time to mitigate risk that DAQ server delivery is on the critical path. | ​Evaluate if a delay in DAQ installation activities will cause further delays: if so, replan DAQ insallation activities to try to minimize any downstream delays. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 1.5 | 0 | 0.15 | 2023-02-01 10:02 | Jill Dornfeld | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-300 | LBNF / DUNE | [DAQ] Delivery of FD2 DAQ components are delayed due to supply chain or manufacturing issues | ​If there are significant supply chain or manufacturing issues, particularly for computing/electronics components, there can be a delay in the deliver of FD2 DAQ components. | Threat |  |  | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved |  |  | ​All FD2 DAQ components have been delivered. | 10% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 1-point - single value | 0 |  | 3 | ​13122.A366865 | ​Most DAQ components are commodity servers or devices, and so expect that a delay may be of up to 3 months. | - Not yet defined - | ​In the procurement process, we are informed of a delay in the availability of DAQ components. | ​Initiate procurements with enough lead-time to mitigate risk that DAQ server delivery is on the critical path. | ​Evaluate if a delay in DAQ installation activities will cause further delays: if so, replan DAQ insallation activities to try to minimize any downstream delays. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 0 | 0 | 0 | 2023-02-01 10:03 | Jill Dornfeld | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-004 | LBNF / DUNE | [I&I] Underground Occupancy limit not enough to execute work as planned | ​If the project is unable to increase the allocation of underground occupancy to the Integration team, then the installation activities will take longer to perform. | Threat | Management Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-10-01 | 2028-06-30 | ​SDSD increases underground occupancy capacity with SURF to 250 | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 0 | 3 | 6 | Risk hook: 13141.A2580MS --> RT-131-FDC-FI-004 --> 13141.A3340 | ​Current resource planning for Integration fits within 175 FTE. SDSTA is planning to increase total underground headcount to 250. It will take longer to execute the installation activities if this increase is not achieved. | 1 - Rough guess |  | ​Joint coordination team to manage risks in partnership with SDSTA. Conversations about additional refuge space underground have been ongoing to increase total headcount. As of 19 December 2023, underground headground at the 4850-ft is increased to 194 personnel. The increase to 250 persons is anticipated in Q1 CY2024. | ​Accept longer installation time |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 3 | 0 | 0.3 | 2024-01-13 12:38 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-028 | LBNF / DUNE | [I&I] Fire inside the cryostat during installation | ​Electrical and powered components on the detector and installation equipment could overheat and cause burning. | Threat | Technical Risk | YES | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-09-01 | 2028-06-30 | ​Closure of the TCO of the two cryostat | 1% | 2 (M) - significantly substandard | 2-point - flat range | 500 |  | 5000 | 2-point - flat range | 1 |  | 12 | Probability should be equally split between two risk hooks: 1) 13141.A1210 --> RT-131-FDC-FI-028-A --> 13141.A1220 2) 13143.50070 --> RT-131-FDC-FI-028-B --> 13143.50080 Risks FI-028-A and FI-028-B are uncorrelated | ​Installation of the detector in the cryostat is a temporary operation and there will not be a permanent fire suppression system inside the cryostat. The cryostat will likely be classified as a confined space and a fire of any size might pose a serious danger to personnel and equipment. Injury could be sustained by workers. Damage to detector can occur. Smoke film on stainless steel would necessitate a re-cleaning inside the cryostat. | 1 - Rough guess |  | ​Polyurethane foam insulation is fire retardent. No large source of combustible materials in cryostat. Combustibles going to be used in the cryostat are controlled as well as in the cavern in general. Any welding will require a burn permit. Need to interlock electrical power to high sensitivity smoke detector (HSSD). | ​Repair any damage and clean equipment​ |  | 1 (VL) | 2 (M) | 2 (M) | 1 (Low) | 2750 | 6.5 | 27.5 | 0.065 | 2024-01-13 12:37 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-108 | LBNF / DUNE | [I&I] Customs delays | ​If insufficient interagency and international regulatory coordination has occurred, then items moved between countries may be delayed or subject to additional costs. | Threat | Management Risk | YES | Michael D Pfaff | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-04-01 | 2027-12-31 | ​all international items are delivered to SDWF | 30% | 0 (N) - negligible technical impact | 3-point - triangular | 100 | 500 | 1000 | 3-point - triangular | 1 | 2 | 3 | Risk hook: 13141.A3621MS --> RT-131-FDC-FI-108 --> 13141.A80000​ | Estimate based on storage fee of $200/day per container. FDC has 1500 containers total. Estimate assumes midpoint of 600 storage days per year, considering that some shipments will be comprised of multiple containers which will incur storage fees at a higher rate. Does not include customs duties. Custom fees are included in the budget. Schedule delay considers existing FDC guidance to have material at the warehouse 3 months prior to installation. None of the shipments to ProtoDUNE had delays beyond three months. | 1 - Rough guess |  | Having freight forwarder. Far Site Logistics manager to prepared shipping manual to help team prepare shipments. Plan, through using bills of lading, to minimize delays. FDC guidance is to have material at the warehouse 3 months prior to installation | Pay storage fees |  | 3 (M) | 1 (L) | 1 (L) | 1 (Low) | 533.3333 | 2 | 160 | 0.6 | 2024-01-13 12:36 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-306 | LBNF / DUNE | [DAQ] FD2 TDE and Timing System integration not fully demonstrated | ​If the integration of the timing system and TDE for FD2 are not fully demonstrated at VD Module 0, integration will be done for the first time at SURF and be at risk of additional cost and effort. | Threat |  |  | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Rejected | 1 - draft |  |  | ​The DUNE Timing system has been successfully integrated with FD2 TDE during testing at ProtoDUNE-II VD. | 10% | 0 (?) - Not yet defined | 1-point - single value |  |  |  | 2-point - flat range | 0 |  | 2 | ​13122.A366839 | ​Integration time is expected to take 2 months at ProtoDUNE-VD, and this work will then need to be done as part of timing integration at SURF. | - Not yet defined - | ​The FD2 TDE system is not fully integrated with the DUNE timing system during testing at ProtoDUNE-II VD. | ​Prioritize integration of the FD2 TDE with the DUNE Timing system at ProtoDUNE VD Module 0. | ​Replan integration activities to be performed at SURF to minimize schedule delays. |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 1 | 0 | 0.1 | 2023-02-01 10:36 | Jill Dornfeld | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-115 | LBNF / DUNE | [I&I] Complications with internal supply chains and logistics | ​If material flow and logistics are complicated beyond plan then Cryostat/Detector installation schedule is impacted. | Threat | Management Risk | YES | Michael D Pfaff | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2025-05-01 | 2028-06-30 | ​all items are delivered to SURF | 30% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 0.5 | 1 | 3 | Risk hook: 13141.A80320 --> RT-131-FDC-FI-115 --> 13141.A82000​ | Extrapolating from ProtoDUNE experience, recovering from missing equipment or shipping delays cost approx 1-3 months during that installation period. Also includes misplaced material/equipment and inattentive handoffs. | 1 - Rough guess | ​Shipping complications | Plan for buffer storage to mitigate delays (warehouse). Receive materials in warehouse well before they are required for installation. Robust planning between installation and logistics teams. Shipping manual & logistics plans to all consortia. Inventory control and tracking system. Utilize trucking service. Also planning to leverage hardware database to support tracking. |  |  | 3 (M) | 0 (N) | 1 (L) | 1 (Low) | 0 | 1.5 | 0 | 0.45 | 2024-01-13 12:35 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-286 | LBNF / DUNE | [I&I] Delay in the beginning of APA integration and installation | ​If the installation of the TPC electronics cryostat penetrations is delayed then the overall integration and installation of the APAs is also delayed, resulting in an overall delay of the FD1 installation (including achieving the FD1 KPPs) and some standing army costs. | Threat | Management Risk | YES | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-08-01 | 2027-03-31 | ​This risk can be closed when the APA integration and installation process for FD1 starts. The risk could also be retired when the contractor for the installation of the cold membrane provides us with a detailed schedule that allows us to refine our plans for the installation of the TPC electronics cryostat penetrations. | 20% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 200 | 2-point - flat range | 0 |  | 3 | Risk hook: 13141.A2580MS (SS) ---> RT-131-FDC-FI-286 ---> 13141.A3340 | ​The worse case scenario is that we cannot work on the installation of the cryostat penetrations for the TPC electronics until after the primary membrane has been welded, the cryostat has been cleaned, and the false flooring inside the cryostat has been installed. This represents the maximum of 3 months. The cost estimate includes the cost-of-living/travel for the personnel coming from universities and laboratories to SURF. The cost of the standing army for the technicians employed by the TPC electronics consortium is calculated from the schedule delay. | 1 - Rough guess | ​We cannot make a detailed prediction for the beginning of the installation of the TPC electronics penetrations, given that we do not have information from the contractor responsible for the installation of the cold cryostat structure (insulating foam and primary membrane). We have made some assumptions in the schedule and we need to take into account the risk that we may not be able to start the work of the installation of the TPC electronics penetrations at our planned date. The trigger of this risk would be a delay in the installation, caused by the conflict between our schedule and the schedule of the constractor. | ​We need to investigate different scenarios where we change the installation and testing sequence for the components on the top of the cryostat, in such a way that we can start the installation of the cryostat penetrations as late as possible, while completing the test of the readout of the warm interface electronics crates and keeping sufficient float prior to the beginning of the integration and installation of APAs. | ​If this risk is realized, the only thing that can be done to minimize the delay in the overall FD1 integration and installation schedule is to increase the personpower at SURF working on the TPC electronics, in such a way that different operations can be performed in parallel and that the overall schedule impact for achieving the FD1 KPP is minimized. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 100 | 1.5 | 20 | 0.3 | 2024-01-13 12:35 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD-290 | LBNF / DUNE | US Assembles Additional APAs Due to Insufficient Production Rate in UK | If the UK cannot produce APAs at a rate sufficient to meet the installation schedule then the US may have to assemble more APAs from UK provided components | Threat |  |  | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2026-01-01 | 2027-07-01 | ​This risk can be closed once the UK production rate can be reliably predicted to meet the installation schedule. | 10% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | 300 | 600 | 3-point - triangular | 0 | 4.5 | 9 | Risk hook: 13122.02.A139278 --> RT-131-FDC-FD-290 --> 13122.02.A139980 ​​​​ | ​Each APA produced at the University of Chicago facility costs approximately $150,000 in labor. The most likely cost and schedule impact then has an additional 2 APAs assembled at the University of Chicago and a maximum of 4 APAs | 2 - Reasonable estimate | ​The UK production rate at the end of 2025 appears insufficient to complete the required number of APAs in time for installation. | ​This risk is mitigated by the UK project increasing efficiency and production capacity to stay on schedule. A fifth winder was recently added to the Daresbury assembly site.​ | ​A small number of APAs are assembled at the University of Chicago using components provided by the UK. |  | 2 (L) | 1 (L) | 2 (M) | 2 (Medium) | 300 | 4.5 | 30 | 0.45 | 2023-05-10 15:41 | Jill Dornfeld | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-008 | LBNF / DUNE | [PM] Extended U.S. Congressional Continuing Resolution after CD-2 | ​IF there's an extended Congressional continuing resolution in FY24 after the ESAAB approval of the CD-3b portion of the project, some of the CD-3b activities will have to delayed to FY25 with a corresponding cost increase due to escalation. | Threat | Management Risk | NO | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-04-01 | 2024-12-31 | This risk can be changed to cover the rest of the project scope once there is more clarity on the FY24 budget. At that time, this risk will have to be changed to cover the remainder of the work for FY25 and later. | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 2300 |  | 1-point - single value |  | 0 |  | Risk hook: 13122.01.02.244MS --> RT-131-FDC-PM-008 --> 13122.01.02.255MS | ​This schedule estimate is based on the fact that the amount of the funding profile will not change after baselining the project since DOE commits to a project after CD-3* and tries very hard not to change the profile. We are assuming that the execution of the CD-3b scope will be partially delayed in case of a year long continuing resolution for FY24, which would lead to a cost increase of $2.3M. This number is obtained assuming that the 131.FDC.04 scope can proceed with the funds that are available, while the 131.FDC.02. 131.FDC.03, and 131.FDC.05 scope will be delayed to FY25. We did not include in this calculation the downstream impact on all other schedule activities. That impact will be estimated at a later date for the full CD-2/3 approval. That work will be delayed until after we know what is the final budget for FY24. | 2 - Reasonable estimate | ​Congressional continuing resolution | ​​Already have 3 months CR planned into schedule and major awards in January. Work with HEP to be clear about funding needed at beginning of each year to possibly front-load DOE Financial Plan for the project annually. Understand how to incrementally fund large procurements | ​​use cost contingency to keep critical path activities on track |  | 4 (H) | 2 (M) | 0 (N) | 3 (High) | 2300 | 0 | 1150 | 0 | 2023-12-12 07:57 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD1-001 | LBNF / DUNE | [FD1 APA] Broken wires point to changes in assembly process or choice of materials | ​If investigation of broken wires suggest a change in the production assembly process or requirement of new material then those changes would need validation, which entails delays in the APA production and installation | Threat | External Risk |  | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2023-02-02 | 2024-09-01 | ​Cold box tests are complete and show no issues with production. | 5% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 1 | 3 | 6 | Risk hook: 13122.D1152 --> RT-131-FDC-FD1-001 --> 13122.D1162​ | ​The schedule delay accounts for the time necessary to implement a new process and test it. | 2 - Reasonable estimate | Observation of an anomalous rate of broken wire during APA construction. | ​The assembly process has passed a production readiness review and vetted with prototypes.​ | Identify the root cause for the wire breakage. If it is caused by the wire quality replace the wire. If it caused by the aseembly procedures, modify them. A new qualification of the assembly is then required. |  | 1 (VL) | 0 (N) | 1 (L) | 1 (Low) | 0 | 3.33 | 0 | 0.1665 | 2023-07-06 10:09 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-287 | LBNF / DUNE | [I&I] Delay in the beginning of CRP installation | ​ If the installation of the bottom drift electronics cryostat penetrations is delayed then the overall integration and installation of the photon detector and CRPs s is also delayed, resulting in an overall delay of the FD2 installation (including achieving the FD2 KPPs) and some standing army costs. | Threat | Management Risk | YES | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2027-09-01 | 2028-04-30 | ​ ​This risk can be closed when the CRP integration and installation process for FD2 starts. The risk could also be retired when the contractor for the installation of the cold membrane provides us with a detailed schedule that allows us to refine our plans for the installation of the bottom drift electronics cryostat penetrations. | 20% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 200 | 2-point - flat range | 0 |  | 3 | ​Risk hook: 13143.50070 --> RT-131-FDC-FI-287 --> 13143.50080 | ​ ​The worse case scenario is that we cannot work on the installation of the cryostat penetrations for the bottom drift electronics until after the primary membrane has been welded, the cryostat has been cleaned, and the false flooring inside the cryostat has been installed. This represents the maximum of 3 months. The cost estimate includes the cost-of-living/travel for the personnel coming from universities and laboratories to SURF. The cost of the standing army for the technicians employed by the bottom drift​​ electronics consortium is calculated from the schedule delay.​ | 1 - Rough guess | ​ ​We cannot make a detailed prediction for the beginning of the installation of the bottom drift electronics penetrations, given that we do not have information from the contractor responsible for the installation of the cold cryostat structure (insulating foam and primary membrane). We have made some assumptions in the schedule and we need to take into account the risk that we may not be able to start the work of the installation of the bottom drigt electronics penetrations at our planned date. The trigger of this risk would be a delay in the installation, caused by the conflict between our schedule and the schedule of the constractor | ​ ​We need to investigate different scenarios where we change the installation and testing sequence for the components on the top of the cryostat, in such a way that we can start the installation of the cryostat penetrations as late as possible, while completing the test of the readout of the warm interface electronics crates and keeping sufficient float prior to the beginning of the integration and installation of CRPs. ​ | ​ ​If this risk is realized, the only thing that can be done to minimize the delay in the overall FD2 integration and installation schedule is to increase the personpower at SURF working on the bottom drift electronics, in such a way that different operations can be performed in parallel and that the overall schedule impact for achieving the FD2 KPP is minimized.​ |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 100 | 1.5 | 20 | 0.3 | 2024-01-13 12:34 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-004 | LBNF / DUNE | [PM] Codes or standards change resulting in scope increases FS | ​​If new safety/environmental codes and standards are introduced over the life of the multi-year facility, then changes in design may be necessary that increase the scope. With increased scope, the cost and schedule will be increased. | Threat | External Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2025-01-01 | 2028-06-30 | ​​Complete work at the Far Site | 5% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 2950 | 2-point - flat range | 0 |  | 2 | Risk hook: 13141.A80220 ---> RT-131-FDC-PM-004 --> 13141.A81000 | ​​Assume 0.5% impact on FD1C cost of 590M = 2950k. Assume modest impact on design time, mainly for infrastructure | 1 - Rough guess | ​Design codes and laws change during a long project, and sometimes these are imposed even when a faciltiy is almost through design or construction. | ​Be congnizant of FESHM and building code changes to understand impacts as early as possible. | ​​revise design to meet codes if required.​ |  | 1 (VL) | 2 (M) | 0 (N) | 1 (Low) | 1475 | 1 | 73.8 | 0.05 | 2024-01-13 12:43 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-006 | LBNF / DUNE | [PM] Ross skip hoist brakes failure | ​If the skip hoist brakes at Ross shaft fail, then the FDC scope in progress at the time will stop and follow on work on the critical path will be delayed, causing standing army and escalation impacts for that follow on work. This risk covers the FDC period after the completion of the BSI suproject (September 2025 to December 2028). Between the start of FDC work at SURF (October 2024 and August 2025) this risk is covered by risk RT-131-FSCF-BSI-006. | Threat | Management Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-08-01 | 2030-09-30 | ​​all FS project work complete | 30% | 0 (N) - negligible technical impact | 1-point - single value |  | 500 |  | 1-point - single value |  | 2 |  | Risk hook: 13141.A80220 --> RT-131-FDC-PM-006 --> 13141.A81000 | ​Since this risk is that the brakes fail to actuate in time to prevent crashing into the beams in the headframe and/or chairs at the 5000L, the cost is both for repair of the structures damaged as well as repalcement of the rope, which would potentially be over-stressed in this event. Follow up for the brakes is most likely adjustment and not​ actual repair. The impact is estimated at 2 months and $200k to repair damage in the headframe if the skip crashed into the crash beams, $100k to repair the chairs at the 5000L, and $200k to replace the ropes. It is not recommended to replace the skip brakes, since the probability of a failure is low and the cost of addressing a failure is lower than the cost of installing new brakes. This risk is tied to work scopes that would use the skips and cryostat. The probability of this risk being realized is taken to be proportioal to the probability that the risk RT-131-FSCF-BSI-006 is realized, based on the relative duration of the time periods where the risks are active. | 2 - Reasonable estimate | ​A failure of the braking system is likely to come in the form of a conveyance stopping too slowly in an emergency event. Since the skip hoist is used only for material moves, the result of this could be damage to equipment. | ​​Replace existing brakes with modern braking system described in Risk Supplement, but not recommended for this risk at this time. Note that sufficient redundancy exists in the hoist systems to prevent a free-falling skip situation.​ |  |  | 3 (M) | 1 (L) | 0 (N) | 1 (Low) | 500 | 2 | 150 | 0.6 | 2024-01-13 12:43 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-112 | LBNF / DUNE | [PM] SURF underground headcount limit requires additional infrastructure | ​If the SURF underground headcount restrictions hinder efficiency, then a double-decker cage will be needed to expand personnel movement capability | Threat | Management Risk |  | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Closed - Retired | 4 - approved | 2024-08-01 | 2028-10-01 | This risk can be closed when all underground detector is complete, as those phases represent the highest personnel and material loads.​ | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 650 |  | 3-point - triangular | 2 | 6 | 12 | The risk hook should be a predecessor to 13141.A3340 (Install End Wall 1 Detector #1) ​ | ​Preliminary estimates for fabrication of a new double-decker cage are $500k. The single-point cost impact also includes an estimate for the design cost and labor for installation. The schedule impact accounts for the time for design, fabrication and installation, with the range referencing when the risk occurs during the installation phase. | 1 - Rough guess | ​Staffing scheduling projections exceed available underground heardcount limit due to egress restrictions and availability (including Yates shaft as secondary egress). | Instalation work occurs in phases, with each phase optimized as much as possible, with significant attention to the underground headcount restrictions. SDSTA has indicated an expansion of the refuge chamber, allowing for increased underground headcount. | ​If the risk occurs, the design for the double-decker cage should be initiated as soon as possible.​ |  | 4 (H) | 1 (L) | 2 (M) | 3 (High) | 650 | 6.67 | 325 | 3.335 | 2023-04-18 14:22 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-007 | LBNF / DUNE | [PM] Ross skip drum cracks require repair | ​​If the Ross skip drum cracks require repair, then the ​FDC work in progress at the time while the drum is repaired, as well as follow on critical path activities will be delayed, causing additional standing army cost and escalation to activiities on critical path. ​ This risk covers the FDC period after the completion of the BSI suproject (September 2025 to December 2027). Between the start of FDC work at SURF (October 2024 and August 2025) this risk is covered by risk RT-131-FSCF-BSI-007 | Threat | Management Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-08-01 | 2030-09-30 | ​​all FS Project work complete​ | 15% | 0 (N) - negligible technical impact | 1-point - single value |  | 687 |  | 1-point - single value |  | 1.5 |  | ​Risk hook: 13141.A80220 --> RT-131-FDC-PM-007 --> 13141.A81000 | ​A proposal has been received by SURF to repair the skip drum cracks for $687k using a metal stitching technique. The discovery of propagating cracks upon routine inspection would result in the hoist being shut down to perform the same repairs as recommended for mitigation. This would have a similar cost, and may prevent excavation for up to 6 weeks if all cracks were repaired. Some subset of the cracks could be addressed instead, so this impact would be a maximum. This risk impacts work scope that uses the skips and therefore it is active during the installation of the cryostats and portions of the detectors. The probability of this risk being realized is taken to be proportioal to the probability that the risk RT-131-FSCF-BSI-007 is realized, based on the relative duration of the time periods where the risks are active. | 2 - Reasonable estimate | ​The Ross skip hoist drum (where the wire rope is wound) was the first of its kind installed in the world. There is speculation that the rods used to tension the drum and keep it round were not properly torqued when installed, which may have contributed to a number of cracks propagating throughout the drum. | ​​monitoring and inspection to ensure if crack propagation increases, risk can be re-assessed and repairs made if required. The drum has cracks that are regularly monitored. Holes have been drilled at the ends of the cracks to reduce the risk of continued propagation, but there remains a risk that the higher demand for LBNF rock removal will result in a failure at one of these crack locations. Based on a low probability of failure, and a modest impact, it is recommended to accept this risk. | ​​​Repair means stitch welding existing cracks.​ |  | 2 (L) | 1 (L) | 0 (N) | 1 (Low) | 687 | 1.5 | 103.1 | 0.225 | 2024-01-13 12:43 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-014 | LBNF / DUNE | [PM] Detrimental Changes to the Overall DOE funding profile before CD-2 Baselining | IF DOE changes the overall project funding profile (not just one year's funding) before CD-2, THEN the FDC SP could be delayed since funding won't be availble to proceed as planned​​ | Threat | Management Risk | NO | Christopher J. Mossey | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-08-01 | 2024-06-30 | ​This risk should be retired once DOE approves a baseline for the FDC subproject | 15% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 3 | Risk hook: 13141.A80010 (SS) --> RT-131-FDC-PM-014 --> 13141.A80030 | There is a large range of possible changes to funding profile that would delay the project. Assess this as a schedule impact, since the funding delay directly affects the project schedule and the burn rate calculated from this. Probability is lower than for NSCFB & ND since sequencing driving funding use is for FDC to complete first. The project has had several funding profile adjustments which have delayed ​project actitivies in the past, most recently in 2021 with the Reference Funding Profile. | 2 - Reasonable estimate | DOE may need to act in response to overall program funding changes, changes in priority, delays in other projects, politicial situations | ​Be alert to how to replan work quickly. Have backup plans ready, develop alternate scenarios. Use contingency if necessary and possible to keep critical path items on track. Be sure priorities are clear among project and collaboration leadership. | Identify critical path activities and respond to those first​. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 1.5 | 0 | 0.225 | 2023-12-12 07:51 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-011 | LBNF / DUNE | [PM] General Security at SURF | ​If someone intent on harm is able to access critical infrastructure such as the hoist or electrical supply and harm critical systems, then access to the underground could be affected and the project delayed. This risk covers the FDC period after the completion of the BSI suproject (September 2025 to December 2028). Between the start of FDC work at SURF (October 2024 and August 2025) this risk is covered by risk RT-131-FSCF-BSI-011 | Threat | Management Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2025-09-01 | 2028-12-31 | completion of FS work scope | 4% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 1000 | 2-point - flat range | 0 |  | 6 | Risk hook: a) 13141.A80170 and 13141.A80180 --> RT-131-FDC-PM-011-A -->13141.A80190, 13141.A80200, and 13141.A80360 b) 13141.A82280 --> RT-131-FDC-PM-011-B --> 13141.A82290 In the PRA MC model, there is a single risk with the total probability as above. This risk has two line item impacts that are fully correlated:hook A for North cavern and hook B for South cavern.Each hook experiences the full schedule impact (see above). These two delays do not add up as the North and South caverns' work is largely de-coupled. The total cost impact above is assigned to risk hook A (the earlier one). | ​​Assume impairment of shaft infrastructure would require replacement of major components. It would likely take time to assess the situation, procure parts, make repairs -- estimate 6 months delay and a cost of $1M. The probability of this risk being realized is taken to be proportional to the probability that the risk RT-131-FSCF-BSI-011 is realized, based on the relative duration of the time periods where the risks are active. | 1 - Rough guess | ​​People intent on harm could be disgruntled employees or members of the public. They would have to be able to get unauthorized access to the systems. | ​​Robust security systems such as gate checks, building security systems, and controls on who can access equipment. HR processes to ensure discharged employees cannot re-access the site. These are captured in the project's updated and approved Security Vulnerability Assessment Report. Fermilab Security and Emergency Management Division uses DOE Safeguards and Security funding to support a SD-based Facility Security Officer. | ​assess problems, make plan, repair damage​ |  | 1 (VL) | 1 (L) | 1 (L) | 1 (Low) | 500 | 3 | 20 | 0.12 | 2024-01-13 12:41 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-125 | LBNF / DUNE | [PM] Lack of Agreement on international codes/standards affects partner design work | ​If there is no agreement on use of international codes and standards for partner components, then partners could delay starting design or the designs could be difficult to assess for operations in the U.S. This affects mostly electrical work. | Threat | External Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-10-01 | 2028-06-30 | ​last delivery from int'l partners, end of project. Agreement on cryostat testing protocol | 15% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 0 | 0.5 | 6 | Risk hook: 13141.A2580MS --> RT-131-FDC-PM-125 --> 13141.A3340 | In 2017, Fermilab international codes and standards committee established an equivalency process to evaluate discrepencies between US codes and Non-US codes (FESHM 2110). Outstanding issues remain on electrical, structural, mechanical, and MSHA/OSHA governance at SURF. Duration estimates time to resolve issues when equipment has arrived. | 1 - Rough guess | ​​​ | ​Use code equivalencies and international agreements to detail process for design and acceptance of non-US components. Proximity cryogenic systems being spec'd to accommodate US and European standards. Cryostats were prototyped at CERN and processes have been extrapolated to Fermilab standards. Detectors: using design reviews to evaluate compliance to codes/standards applicable to the project Establishment of the integration project office / compliance office to resolve issues ahead of execution. |  |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 2.17 | 0 | 0.3255 | 2024-01-13 12:40 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-131 | LBNF / DUNE | [PM] Non-US Workers Visa Delays | ​If workers from outside the U.S. are not able to get and maintain work permits, then progress on non-DOE partner contribution work such as the cryostats, detector and cryogenics could be delayed. | Threat | External Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-02-05 | 2030-12-31 | ​End of project. | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 1 |  | 3 | Risk hook: 13141.A80220 --> RT-131-FDC-PM-131 --> 13141.A81000​ | ​European foreign nationals entering the US can stay for 90 days without a visa if they are fromspecific countries identified by the U.S. Dept of Stateand meet specific requirements. Fermilab utilizes J-1 visas to host & sponsor foreign specialized workers (J-1 specialist = 1 year visa, repeatable). Workers may not be able to be brought in by partners in a timely manner. Also, if the work takes longer than expected, the visa may not be able to be extended. Estimate there's ~ 10% chance something will go wrong with a visa that will most likely take a month to straighten out. | 1 - Rough guess | ​Foreign nationals are not able to get visas to work in the US or be part of the visa waiver program in the timeframe necessary to meet the project schedule, or may not be able to get visas to work in the US at all because of their Country of Origin. | The Project has engaged ​Fermilab's Global Services Department which has two visa experts on staff to support planning for the Project’s anticipated number of workers. The Project has provided timing and worker estimates (#) to the Visa Office which has worked with the Department of State to secure sufficient J-1 host/sponsor forms. Project management continues to work with non-DOE partners to assist with any visa issues and verify planning as early as possible. | Wait for workers to arrive. |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 2 | 0 | 0.2 | 2024-01-13 12:40 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-172 | LBNF / DUNE | [PM] Insufficient scientific personnel for the FD2 integration and installation | ​​If the institution participating in the FD2 consortia cannot recruit all the contributed scientific effort required during the integration and installation of the detector at SURF, the project may need to hire additional technicians, leading to both a cost increase (salaries) and a possible delay in the achievement of the KPPs (time required to hire the additional personnel). | Threat | Management Risk | YES | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2027-07-01 | 2028-12-31 | ​This risk can be closed at the end of the installation of FD2 | 30% | 0 (N) - negligible technical impact | 2-point - flat range | 300 |  | 750 | 2-point - flat range | 0 |  | 3 | ​Risk hook : 13143.50050 ---> RT-131-FDC-PM-172 ---> 13143.50070 | ​The probability of 30% assumes that one third of the research groups in the US go through the comparative reviews every year and are at risk of not getting their grant renewed. The cost impact assumes that between 3 and 5 additional technicians will be hired by the project at a cost of $150k per year (the upper limit represents 30% of the total scientific FTEs from US institutions). The schedule impact assumes that plans could be made ahead of the installation, but also that there could be problems with recruiting the personnel​ | 2 - Reasonable estimate | ​​This risk is triggered when some of the US group who are planning to participate in the installation activities fail to get their research grant renewed | ​ ​Several risk mitigations have been put in plance: a) conduct surveys of the available personpower (the last one was done in July 2025 in preparation of a NSG review) b) involve the collaboration to recruit additional personnel for these tasks c) inform the funding agencies of the institutions that have committed to the detector integration and installation work​ | ​Try again to recruit personnel from the collaboration, hire technicians​​ |  | 3 (M) | 1 (L) | 1 (L) | 1 (Low) | 525 | 1.5 | 157.5 | 0.45 | 2024-01-13 12:32 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-173 | LBNF / DUNE | [PM] International partners fail to provide personnel for FD1 and FD2 installation | ​If the international partners fail to provide the promised personnel for the integration and installation of FD1 and FD2 there will be a delay achieving the corresponding KPPs | Threat | External Risk | YES | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-07-01 | 2028-12-31 | ​Completion of the installation of FD1 and FD2 | 20% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 3 | ​Risk hooks (FD1 with 10% probability, FD2 with 20% probability) a) 13141.A2580MS (SS) ---> RT-131-FDC-PM-173-A ---> 13141.A3340 (FD1) b) 13143.50050 ---> RT-131-FDC-PM-173-B ---> 13143.50070 (FD2) | ​We assume that there is a 10% probability that the international partners will fail to provide some of the ~25 people promised for FD1 or some of the ~50 people promised for FD2. We assume that it will take between 0 and 3 months to address the problem. This is an international risk where the project is not responsible for the extra costs. The solution of this problem involves discussions with the INC and the RRB. | 1 - Rough guess | ​International partners fail to provide the required personnel | ​ ​Several risk mitigations have been put in plance: a) conduct surveys of the available personpower (the last one was done in July 2025 in preparation of a NSG review) b) involve the collaboration to recruit additional personnel for these tasks c) update the MOUs in 2025 including updates of the promised personpower​ | If this risk is realized the Collaboration, the RRB, and the INC will be involved in its solution, that is likely to require a scope transfer between the US and international partners which may even go beyond the FDC subproject. Since this would be a failure on the side of international partners, there will be no other consequences for the project, other than the schedule delay and its associated costs.​ |  | 2 (L) | 0 (N) | 1 (L) | 1 (Low) | 0 | 1.5 | 0 | 0.3 | 2024-01-13 12:32 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-181 | LBNF / DUNE | [PM] Loss of key personnel | ​If some key personnel is lost during either the detector construction or installation then the project will take some time to find an appropriate replacement which would cause delays in the achievement of the KPPs | Threat | Management Risk | YES | Marco Verzocchi | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-07-01 | 2029-03-31 | ​This risk can be closed at the end of the detector installation | 20% | 0 (N) - negligible technical impact | 3-point - triangular | 0 | 125 | 250 | 3-point - triangular | 0 | 1 | 4 | ​Risk hooks (share the probability equally between the two, the first one is FD1, the second one is FD2) a) 13141.A2580MS (SS) ---> RT-131-FDC-PM-181-A ---> 13141.A3340 b) 13143.50050 ---> RT-131-FDC-PM-181​​-B ---> 13143.50070 | ​The design of FD1 and FD2 is complete (all the FDRs have been completed) and therefore the project is less sensitive to the loss of key engineers. However the project remains sensitive to the unavailability of personnel for QC testing of the detector components, to the loss of experienced personnel for DAQ software and for firmware design in general, as well as for the loss of experienced personnel that can lead the integration and installation of the detectors. This risk is supposed to catch the cases where some key person leaves the project without providing sufficient warning to train their replacement and to have an appropriate overlap between the person leaving and the replacement. The probability of 20% is an estimate based on past experience from ProtoDUNE and other experiments. The cost impact is based on the assumption that there could be an overlap period where two people need to be paid for the work normally done by a single person. The estimate of the schedule impact is based on the experience of how long it takes to replace a person and train a newcomer. | 1 - Rough guess | ​This risk is triggered when some personnel leaves and there isn't a backup ready. | Several risk mitigations are being put in place a) identify key personnel and develop an appropriate succession strategy b) ensure that there are very few areas where we have single points of failure c) reach out to the collaboration to find additional personnel to cover areas of weakness​ | If the risk is realized, find a replacement and train them as quickly as possible using collaboration resources and resources from the national laboratories​ |  | 2 (L) | 1 (L) | 1 (L) | 1 (Low) | 125 | 1.67 | 25 | 0.334 | 2024-01-13 12:32 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-CR-159 | LBNF / DUNE | [CRYO] Partner-supplied items do not meet quality standards and are delayed | ​If the items manufactured under a partner's supervision do not meet acceptable quality standards then rework of the parts will be needed and the items will be delayed. | Threat | Technical Risk | YES | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-03-01 | 2028-08-31 | ​Items pass quality inspection before shipping. Items pass quality inspection upon arrivat at SURF and before installation. | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 0 | 0.5 | 1.5 | Risk hooks: 1) 131123.02.03.9530 --> RT-131-FDC-CR-159-A --> 13122.OBMS92690 2) 131123.02.03.9600 --> RT-131-FDC-CR-159-B --> 131123​.02.03.5005 The riosks CR-159-A and CR-159-B are uncorrelated | Rework of items ready to dispach will have high priority at the manufacturer. Assuming appropriate supervision during the preceding phases and given the size of the expected contributions, a couple of weeks is the most likely schedule impact. It will give enough time to procure off the shelf items, if needed, alter equipment, retest them, etc. No issues will have no impact, so the minimum would be 0. If the issues are severe or custom made items are needed for the repair, up to 6 weeks might be needed. So the maximum schedule impact is 1.5 mo. | 2 - Reasonable estimate | ​Lack of expertise from the partner during the QC process. Vendor not suitable for the scope of work. Scale of equipment too large for either the partner or the vendor to handle. | ​Verify acceptable QA plan. Verify credentials of partner and vendor for scope of work. Assist partner as needed with QC process of deliverables: this includes review of documents and participation in vendor's visits to witness performance and acceptance tests. Continue to develop equivalency for foreign codes and standards. |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0.67 | 0 | 0.067 | 2024-01-13 12:49 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-192 | LBNF / DUNE | [TDE] Unexpected noise in the top drift electronics during installation | ​If unexpected noise levels are observe during the installation of the top drift electronics and after the connection with the top CRPs, some additional grounding and shielding work may be necessary which will delay the achievement of the FD2 KPPs | Threat | Technical Risk | YES | Steve Kettell | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2027-07-01 | 2028-03-31 | This risk can be closed once the FD2 installation and initial checkour at room temperature are complete​ | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 0 |  | 2 | Risk hook:​ 13143.50250 ---> RT-131-FDC-FD2-192 ---> 13143.50270 | This estimate is based on past experience with both ProtoDUNE detectors and with the cold box tests that have also served as a mitigation for this risk. The schedule impact is based on past experience for the amount of time that it takes to solve grounding issues in large detectors. The cost impact is zero because this is an international risk​ | 1 - Rough guess | ​This risk is realized when in readout tests of the top drift electronics (either standalone or after connection to the CRP) a larger than expected level of noise is observed. | ​Several tests are performed in Cold Box and ProtoDune tests to assess, diagnose and attend to such issues. Additional care is being taken to ensure proper grounding and shielding of all electronics components. | ​​identify the grounding problems, additional filtering in the readout FPGS |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 1 | 0 | 0.1 | 2024-01-13 12:34 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-193 | LBNF / DUNE | [TDE] Damage to the front-end electronics during initial testing | ​If the TDE front-end electronics is damaged during initial testing of the detector, there will be a small delay due to the need of replacing the cards, which will delay the completion of the project | Threat | Technical Risk | YES | Steve Kettell | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2027-07-01 | 2028-12-31 | ​Completion of the warm checkout of the vertical drift detector | 1% | 0 (N) - negligible technical impact | 2-point - flat range | 0 |  | 0.5 | 1-point - single value |  | 0 |  | Risk hook:​ 13143.50250 ---> RT-131-FDC-FD2-193 ---> 13143.50270 | The probability of this risk being realized is based on past experience with the ProtoDUNE detectors and with cold box tests. The schedule delay corresponds to the time that is required to swap out the FE cards in the chimneys. The cost impact is zero because this is an international risk.​ | 1 - Rough guess | ​This risk is realized when one of the FE cards becomes unresponsive during the initial testing of the vertical drift detector | ​Design of suitable protection components on the FE card. Allow for replacement of cryogenci electronics via chimneys without contaminating LAr volume and the need to switch off the other cards in the same chimney or other chimneys. | ​Replaced the damaged cards |  | 1 (VL) | 0 (N) | 0 (N) | 0 (Negligible) | 0.25 | 0 | 0 | 0 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FD2-305 | LBNF / DUNE | [DAQ] FD2 SURF infrastructure stability impacts DAQ uptime | If the rooms and barracks housing FD2 DAQ equipment at SURF do not have sufficient performance or stability in cooling, power, and air quality, then this may affect the uptime of DAQ servers and cause a slowdown in integration work.er lifetime of DAQ servers and slowdown in integration work. | Threat | Technical Risk | YES | Wesley Robert Ketchum | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2027-10-01 | 2028-12-31 | ​Integration testing with the full DAQ at SURF is complete. | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 0 | 0.5 | 1.5 | Risk hook: 13122.A455628 --> RT-131-FDC-FD2-305 --> 13122.A366427 | ​Assuming stability issues create problems at 25% level for uptime, leading to needing 25% more time for integration work. No additional cost, as integration work cannot be done. | 1 - Rough guess | ​During integration testing with the full DAQ at SURF, instabilities in infrastructure cause a delay in being able to perform those activities. | ​Communicate DAQ services requirements clearly, including those that affect stability. Develop a plan for operations support to monitor stability issues and communicate as required. Plan integration testing activities such that some instability will not cause a complete halt in work. | ​Replan activities as needed to try to work around instabilities. Promptly communication problems during integration testing. |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0.67 | 0 | 0.067 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-008 | LBNF / DUNE | [I&I] Noise in the detector after row 1 is installed | ​IF the noise tests after detector#1 row 1 is installed indicate a noise source is present THEN a period of noise mediation will be required. | Threat | Technical Risk | YES | James Stewart | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-10-01 | 2028-06-30 | ​After detector slice 1 is installed and tested this risk is retired. | 25% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 1-point - single value |  | 1 |  | Risk hook: 13141.A1220 --> RT-131-FDC-FI-008 --> 13141.A1230 ​ | ​Typically in ProtoDUNE-SP the noise sources could be identified in a one month period. The estimate assumes the cost impact which is the standing army cost will be automatically evaluated through the risk process. | 1 - Rough guess | ​External/internal noise sources, grounding issues causing noise in the detector | ​Implementation of DUNE grounding and shielding plan. ProtoDUNE-SP and ProtoDUNE-SP-II FDR and PRR. The tests and ProtoDUNE and the design reviews will reduce this risk. However any small changes to the design could defeat the testing and experience shows that the collaboration is prone to many small changes. All instrumentation will be tested in ProtoDUNE-II. The residual risk is that some changes are made after ProtoDUNE-II that have unforeseen impacts.​ |  |  | 3 (M) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 1 | 0 | 0.25 | 2024-01-13 12:38 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-012 | LBNF / DUNE | [I&I] Parallel installation of Internal Cryogenics and DSS with membrane | ​IF the contract for the membrane installation does not permit the parallel installation of the DSS and internal cryogenics THEN additional schedule time will be needed to execute the activities serially.​ | Threat | Management Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-03-01 | 2026-09-30 | ​The risk will be closed when the Membrane installation contract is placed. | 15% | 0 (N) - negligible technical impact | 1-point - single value |  | 200 |  | 2-point - flat range | 0.5 |  | 1 | Risk hook: 13141.A84015 --> RT-131-FDC-FI-012 --> 13141.A84045​ | schedule impact is time needed to install the scaffolding. cost impact is cost of scaffold rental for ​3 months, which is a rough estimate of the time to install the det 1 internal cryogenics and DSS if this needs done after the cryostat work is complete.The probability is 15% as based on the protodune experience there is no known reason for this not to work, but there have been no discussion with the companies.​ | 1 - Rough guess |  | ​Negotiations with cold membrane subcontractor |  |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 200 | 0.75 | 30 | 0.1125 | 2024-01-13 12:38 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RU-131-FDC-CR-148 | LBNF / DUNE | [CRYO] Price of LAr is uncertain (#1, #2) | ​If the Argon demand continues to increase more than the Argon supply, the price of the LAr will continue to increase (#1, #2). | Uncertainty | External Risk | NO | David Montanari | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2025-08-01 | 2029-07-02 | ​Award of contract for LAr supply. LAr supplied as in-kind contribution by an International partner from a place where LAr is abundant. | 100% | 0 (N) - negligible technical impact | 3-point - triangular | -2913 | 0 | 3072 | 1-point - single value |  | 0 |  | Risk hooks both with P=100% (uncertainties): 1) 131123.04.02.46MS4 --> RU-131-FDC-CR-148-A --> 131123.03.25 2) 131123.04.02.75MS --> RU-131-FDC-CR-148-B --> 131123.03.40 Risks CR-148-A and CR-148-B are CORRELATED. See "Explanation of Estimate" field for cost split details. | The report from Intelligas Consulting on LAr supply uses a 3.5%/year price increase. Assuming a 3-4% range, the impacts are (until the end of the fill): Min impact = 3% increaseLikely impact = 3.5% increase (baseline LAr escalation in P6) Max impact = 4% increase. The possibility that the yearly increase is only 3% is captured as a negative impact (saving): -1,364k for #1 and -$1,549k for #2 for a total MIN = -$2,913k (correlated for # and #2). The possibility that the yearly increase is 4% is captured as a cost increase: +1,417k for #1 and $1,655 for #2 for a total MAX = -$3,072k (correlated for # and #2). The amount for purge and cool down has been updated in P6 as well. No additional risk uncertainty has been added, since it is within the estimate uncertainty. | 3 - Solid estimate | The status of the steel industry in the US drives this risk. In general, if the economy is going well, there is high demand of LAr, and therefore less available for a once in a lifetime customer like LBNF/DUNE. | ​Continue to monitor the LAr production and its supply/demand balance. Continue to engage with John Campbell and the industry to maintain our estimates up-to-date. |  | Detailed calcs for cost impact in BOE Report. | 5 (VH) | 2 (M) | 0 (N) | 3 (High) | 53 | 0 | 53 | 0 | 2024-01-13 13:05 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RU-131-FDC-FD-157 | LBNF / DUNE | [FD1-APA] Transportation cost fluctuations for APA shipping | ​If the costs for transporting APAs fluctuates, then the cost of shipping them will be impacted | Uncertainty | External Risk | NO | Brian J. Rebel | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2026-07-01 | 2027-08-30 | ​All APAs have been shipped to SURF | 100% | 0 (N) - negligible technical impact | 3-point - triangular | -74 | 0 | 149 | 1-point - single value |  | 0 |  | Risk hook: 13122.OBMS92045​--> RU-131-FDC-FD-157 --> 13122.02.A139588​​ | ​Each shipment of APAs via long-haul truck is expected to cost $6600. There are 45 shipments in total for the project costing $297,000 at the current estimates. Transportation costs for large items are particularly volatile due to COVID. Given the current uncertainty we add a risk that the shipping costs may fluctuate between $5k and $10k per shipment (i.e. between 75% and 150% of the current best estimate) | 2 - Reasonable estimate |  | ​Monitor the market pricing. Explore options for discounts with larger shipments.​ |  |  | 5 (VH) | 0 (N) | 0 (N) | 0 (Negligible) | 25 | 0 | 25 | 0 | 2023-12-12 07:58 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-FI-100 | LBNF / DUNE | [I&I] Schedule Interfaces at SURF | ​If concurrent work for multiple parties during the Integration phase cannot be executed in an optimized way, or properly prioritized, then scheduling conflicts will occur, resulting in installation delays for cryostat, cryogenics and detector.​​ | Threat | Management Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-08-01 | 2028-06-30 | ​this risk will linger for the duration of the project's multi-party activities at SURF. | 50% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 2-point - flat range | 0.25 |  | 0.5 | Risk hooks: 1) 13141.A80010 (SS) --> RT-131-FDC-FI-100-A --> 13141.A80030 2) 13141.A80510 --> RT-131-FDC-FI-100-B --> 13141.A364832 3) 13141.04.02.36MS --> RT-131-FDC-FI-100-C --> 131123.02.04.70MS The three risks FI-100-A, FI-100-B, and FI-100-C are uncorrelated​ ​ | impacted activities are start of initial installations when things are still being figured out. High probability that something will go wrong at some point or conflicts will be missed in planning. | 1 - Rough guess | Multiple parties working underground to cosntruct and install LBNF and DUNE will be interfering with each other’s work because surface, underground space, and shaft availaibility are limited. Causes could include last minute delivery schedule changes, simlutaneous requests for material moves, inadequate communication of delivery schedules, unavailability of temp areas to park unexpected deliveries to work out issues. It's assumed that this may occur more than once in the life of the LBNF/DUNE underground construction and assembly work at SURF. | ​Perform a detailed geographical location-timeline schedule. Continue updating the logistics planning. The current draft of the logistics plan includes a Ross Shaft utilization estimate over the life of the integration phase of the project. This will need to keep being refined as load lists become more detailed and schedules become more granular. Use the analysis to plan the material move schedules and inform the installation schedule. implement project-wide common inventory management system to track items for delivery. Interactions with FSCF discussing lessons learned, including formal workshop post BSI contract awards |  |  | 4 (H) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0.38 | 0 | 0.19 | 2024-01-13 12:36 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RU-131-FDC-PM-099 | LBNF / DUNE | [PM] Future escalation rates are uncertain | ​The cost estimates in the Basis of Estimate (BoE) documents are expressed in terms of the base-year dollar when the estimate was made. For budgeting purposes [GAO-09-3SP, page 102], projected escalation rates are then applied to escalate the base-year dollars to then-year dollars and hence reflect the expected cost in the year in which it will be incurred. If actual inflation in future differs from the assumed escalation rates, then the project cost may increase or decrease. | Uncertainty | External Risk | NO | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-10-01 | 2032-09-30 | End of the project | 100% | 0 (N) - negligible technical impact | 3-point - triangular | -11282 | 0 | 19338 | 1-point - single value |  | 0 |  | We share the cost over the fiscal years to obtain the correct contingency need profile. The five risk impacts are 100% correlated such that the total min/likely/max range is fully sampled (note: correlations in time are already addressed in the escalation impact analysis -- see PPP document referenced below). FY25: 13122.01.02.244MS (SS relationship) --> RU-131-FDC-PM-099-B -->13122.01.02.255MS FY26: 13122.01.02.246MS (SS relationship) --> RU-131-FDC-PM-099-C --> 13122.01.02.256MS FY27: 13122.01.02.247MS (SS relationship) --> RU-131-FDC-PM-099-D --> 13122.01.02.257MS FY28: 13122.01.02.248MS (SS relationship) --> RU-131-FDC-PM-099-E --> 13122.01.02.258MS FY29: 13122.01.02.249MS (SS relationship) --> RU-131-FDC-PM-099-F --> 13122.01.02.259MS Cost impact:​​​ FY25: [-$2,609k, 0, +$3,244k] FY26: [-$2,875k, 0, +$4,723k] FY27: [-$2,930k, 0, +$5,595k] FY28: [-S2,070k, 0,​ +$4,232k] FY29: [ -$798k, 0, +$1,544k] | We follow Fermilab’s guidance on “Escalation Rate Projections and Risks for Fermilab Projects” (PPP-doc-2606).https://ppp-docdb.fnal.gov/cgi-bin/sso/ShowDocument?docid=2606 For non-civil construction M&S we use the Personal Consumption Expenditures (PCE) index from the Bureau of Economic Analysis of the Department of Commerce [PCE-INDEX]. For labor, the US Bureau of Labor Statistics (BLS) Employment Cost Indexes (ECI) for “colleges, universities and professional schools” is used. Forecasts of PCE rates are obtained from the Federal Reserve’s quarterly Monetary Policy Reports to Congress. These forecasts allow for many economic indicators, the impacts of the Covid-19 pandemic, the war in Ukraine, and expectations for future monetary policy actions. The labor escalation forecasts are determined from the PCE forecasts plus the historical difference between the PCE and BLS ECI rates. The minimum, likely and maximum risk escalation risk impacts are computed by rolling up the budgeted cost (as of 8 June 2023) in Cobra under three scenarios: MIN / AVE / MAX escalation rates from PPP-doc-2606. Subtracting the AVE cost (as is used by default in Cobra) from the MIN and MAX scenarios, yields the range of cost impacts: Min impact = -12,752k$ and Max impact = 21,09k$. | 2 - Reasonable estimate |  | ​​Monitor actual escalation annually and update project plan accordingly. | ​​If the cost impacts are acceptable the risk response is to use contingency to cover the increased costs. For extreme inflation rate changes that cannot be covered by contingency, work with the agencies to address the issue. If need be, descope options (that have already been identified) may need to be exercised to ensure the overall project cost remains within the agency guidance. | Escalation Rate Projections and Risks for Fermilab Projects” (PPP-doc-2606) | 5 (VH) | 3 (H) | 0 (N) | 3 (High) | 2685.3333 | 0 | 2685.3 | 0 | 2024-01-09 08:25 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RT-131-FDC-PM-002 | LBNF / DUNE | [PM] Union Work Stoppage Delays Project at Far Site | ​If work stoppages occur on FS contracts with union labor, then the subsequent contract activities could be delayed, as well as the follow on project scope such as FS Cryo, FD, FSI. Then the overall project critical path may be delayed for the period equal to the work stoppage, increasing the standing army cost and increasing escalation on the delayed activiites. This risk covers the FDC period after the completion of the BSI suproject (September 2025 to December 2028). Between the start of FDC work at SURF (October 2024 and August 2025) this risk is covered by risk RT-131-FSCF-BSI-001 | Threat | Management Risk | YES | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2024-08-01 | 2028-06-30 | ​FD2 Complete | 10% | 0 (N) - negligible technical impact | 1-point - single value |  | 0 |  | 3-point - triangular | 0 | 0.25 | 0.5 | Risk hook: 13141.A80010 (SS) --> RT-131-FDC-PM-002 --> 13141.A80030​​ | ​Based on past experience: When a work stoppage occurred on the NuMI Tunnels and Halls Project, no work was performed by the excavation contractor for ~ one week. The Fermilab Meson Roof Repair project was delayed when the non-union contractor was challenged by union officials and it took 2 weeks to sort how to satisfy the union. Any critical path delays have associated increases in level of effort work and associated costs. Based on past experience, assume 2 weeks as max, one week as most likely, and 0 as min. The probability of this risk being realized is taken to be proportioal to the probability that the risk RT-131-FSCF-BSI-001 is realized, based on the relative duration of the time periods where the risks are active. We then divide that risk by a factor 2 to account for the fact that a significant fraction of the workforce during the I&I period will be employed by Fermilab which has better working conditions relative to contractors. | 1 - Rough guess | ​The cryo installation, and detector installation will utilize some combination of union contractors, non-union contractors, and laboratory/university technicians. The union contractors may either strike themselves, or may stop work to not cross the picket line of another union on strike. This has occurred at Fermilab, and caused delays of several days, even up to a week. Much of the installation work is on the critical path. | ​​Create good communications with union officials | ​​Establish means to provi​​​de alternate access during union work stoppages to keep other workers going.​ |  | 2 (L) | 0 (N) | 0 (N) | 0 (Negligible) | 0 | 0.25 | 0 | 0.025 | 2024-01-13 12:42 | Jolie R Macier | Item | org/ocoo/ippm/Lists/Risk Register
RU-131-FDC-PM-114 | LBNF / DUNE | [PM] Offsite Indirect Rates uncertainty | Fermilab has agreed to have a special CSS rate for offsite work at SURF starting in FY25, but this rate is not going to be set until Summer of 2024. For the moment we are assuming that the SURF offsite CSS rate is between 70% and 90% of the onsite rate. This uncertainty represents the fluctation of this rate. The cost impact includes both BUDGET and CONTG and therefore it is the direct impact to the TPC of the project. | Uncertainty | Management Risk | NO | Jolie R Macier | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2023-10-01 | 2030-12-31 | all use of SD-based labor is complete​ | 100% | 0 (N) - negligible technical impact | 3-point - triangular | -2667 | 0 | 2621 | 1-point - single value |  | 0 |  | Risk hook: 13122.01.02.244MS --> RU-131-FDC-PM-114 -->13122.01.02.255MS​ | We do not have an estimate of the CSS rates from FY25 to the end of the project for work performed at SURF. We will be assuming for the moment that the CSS overhead will be reduced to be 80% of the level for work done onsite at Fermilab, and allow for a fluctuation between 70% and 90%. The total impact is in the range [-$2.667M,+$2,621M] distributed as follows FY25: [-$433k, +$426k] FY26: [-$676k, +$665k] FY27: [-$777k, +$763k] FY28: [-$629k, +$618k] FY29: [-$136k, +$133k] FY30: [-$17k, +$17k] | 2 - Reasonable estimate | ​A strategic change is implemented that adjusts the offsite indirect rate for labor resources. | ​Continue to interact with Fermilab Financial Division. Shift to subcontracted labor rather than FNAL staff labor. | ​Additional cost is added to the project. | FNAL Labor rates | 5 (VH) | 2 (M) | 0 (N) | 3 (High) | -15.3333 | 0 | -15.3 | 0 | 2023-12-12 07:56 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register
RU-131-FDC-PM-215 | LBNF / DUNE | [PM] Fluctuations in exchange rates cause variations of the costs of detector components | ​If the relative exchange rate of the USD relative to other currencies fluctuates too much, the cost of some detector components procured from US resellers may increase/decrease too much relative to the baseline cost, with variations that exceed the cost uncertainty (that is some case is limited as quotes already exist for those components). This could result in a significant variation of the construction cost. | Uncertainty | External Risk | NO | Cheng-Ju Stephen Lin | 131.FDC - Far Detectors + FS Cryogenic Infrastructure | Open | 4 - approved | 2019-09-01 | 2025-10-31 | ​This risk will be closed at the completion of all the procurements of the components required for the detector construction, that are likely to be fabricated outside the US. | 100% | 0 (N) - negligible technical impact | 2-point - flat range | -1500 |  | 1500 | 1-point - single value |  | 0 |  | Risk hook: 13122.2004.133.330 --> RU-131-FDC-PM-215 --> 13122.2004.133.390 | ​We have identified $3.7M of FD1 components (printed circuit boards and discrete components for the FEMBs, WIBs, and PTCs), cold cables, and power supplies that are likely to be purchased from US vendors but fabricated outside of the US. We assume that if the exchange rate of the USD relative to that of the country where the items are fabricated (China in most cases, Germany for the power supplies) changes too much, this will be reflected in a variation of the cost of the components. We not that ASICs do not contribute to this risk, since the payment takes is done in USD. ​We have identified $3.7M of FD2 components (printed circuit boards and discrete components), cold cables, and power supplies that are likely to be subject to currency fluctuation uncertainties. We assume a maximum rate fluctuation of -20% to +20% with uniform probability. | 2 - Reasonable estimate | This risk is realized if there is a significant variation of the exchange rate of the USD relative to some foreign currencies.​ | ​Unfortunately there is not much that can be done to protect against this risk, other than trying to profit from favorable exchange rates whenever possible. | ​Unfortunately there is not much that can be done to protect against this risk, other than trying to profit from favorable exchange rates whenever possible.​ |  | 5 (VH) | 2 (M) | 0 (N) | 3 (High) | 0 | 0 | 0 | 0 | 2023-12-12 07:51 | Lucas Taylor | Item | org/ocoo/ippm/Lists/Risk Register