## Slide 1: LBNF/DUNE-US FSCF-EXC and BSI Risks
16 January 2023

## Slide 2
EXC Subproject

## Slide 3: EXC Risk Register – Open Risks
RI-ID | Title | Probability | Cost Impact | Schedule Impact | P * Impact (k$) | P * Impact (months)
RT-131-FSCF-EXC-237 | Cranes for North Caverns arrive late to EXC Subproject and Impact FDC Subproject | 55.00% | 100 -- 300 k$ | 0 -- 0.5 -- 2 months | 110 | 0.5
RT-131-FSCF-EXC-011 | FS Unavailability of SURF or FRA supplied systems & spaces at SURF-high prob,low imp (EXC) | 33.00% | 0 -- 3300 -- 6600 k$ | 0 -- 0.5 -- 1 months | 1,089 | 0.2
RT-131-FSCF-EXC-013 | Yates shaft unavailable for emergency egress | 5.00% | 3300 -- 19800 -- 39600 k$ | 0.5 -- 3 -- 6 months | 1,045 | 0.2
RT-131-FSCF-EXC-234 | Ross Brow Excavation Delays | 15.00% | 850 k$ | 1 months | 128 | 0.2
RT-131-FSCF-EXC-232 | EXC subcontract completion delayed due to shaft constraints | 5.00% | 250 -- 750 k$ | 1 -- 3 months | 25 | 0.1
RT-131-FSCF-EXC-006 | FS SURF infrastructure projects impact LBNF/DUNE project (EXC) | 25.00% | 0 -- 1500 k$ | 0 -- 0.5 months | 188 | 0.1
RT-131-FSCF-EXC-101 | Adverse conditions in far site underground excavations - High Prob Low Impact | 5.00% | 50 -- 1000 k$ | 0 -- 1 months | 26 | 0.0
RT-131-FSCF-EXC-007 | FS Ross skip hoist brakes failure (EXC) | 1.00% | 13700 k$ | 2 months | 137 | 0.0
RT-131-FSCF-EXC-004 | FS ESH Incident Stops Work Temporarily (EXC) | 5.00% | 250 -- 900 -- 1800 k$ | 0.25 -- 0.5 months | 49 | 0.0
RT-131-FSCF-EXC-008 | FS Ross skip drum cracks require repair (EXC) | 1.00% | 10587 k$ | 1.5 months | 106 | 0.0
RT-131-FSCF-EXC-001 | Adverse conditions in far site underground excavations - Low Prob High Impact | 2.00% | 0 -- 1750 k$ | 0 -- 0.25 months | 18 | 0.0
RT-131-FSCF-EXC-010 | FS General Security at SURF (EXC) | 1.00% | 0 -- 500 k$ | 0 -- 0.25 months | 3 | 0.0
RT-131-FSCF-EXC-002 | FSCF EXC construction activities impact neighboring communities with Dust and Noise | 15.00% | 750 -- 1250 k$ | 0 months | 150 | 0.0
RT-131-FSCF-EXC-231 | Ross shaft logistic interference EXC/BSI/Cryostat #1 delays FSCF contractors (EXC) | 15.00% | 500 -- 3000 k$ | 0 months | 263 | 0.0
131.FSCF.EXC – Far Site Conventional Facilities
Retired Risks 31
Open Risks 14 More than half of these Open Risk will be retired in March 2024, with the remainder of them being retired in June 2024.
EXC Risks to BSI
Notes: The MC Analysis is based on a 90% CL according to FRA Lab Procedures
The Total Contingency Need is made up of three parts: Estimate Uncertainty and Risk Contingency and Top Down Contingency, so in our case, we have a Total Contingency Need of $88M which equates to a Contingency Need of 34% on ETC.
  ETC = $260M
  Contingency = $88M ($33M EUC) + $36M (Risk) + $19M (Top Down)

## Slide 4: Summary EXC Contract Changes as of 17 November 2023
Category | Cost Impact1,2 |  | Schedule Impact1
Code/Standard Changes | $5,073,000 |  | 0 day
Design Related Changes | $5,894,000 |  | 0 day
Differing Site Conditions | $3,301,000 |  | 23 day
RHS Performance3 | $17,105,000 |  | 0 day
Access/Infrastructure Related | $12,733,000 |  | 72.25 days
COVID-19 | $185,000 |  | 0 day
Weather | $963,000 |  | 4.5 days
Other | $66,000 |  | 0 days
Total | $45,321,000 |  | 99.75 Days
Note 1: Changes to date for cost (10.4%) and schedule (5.3% of original duration) have been dominated by unavailability of FRA or SURF supplied equipment (shafts and hoists). There are pending issues (including RHS performance and labor stacking due to resequencing) that are under review and could potentially extend the completion date to mid-August 2024.
Note 2: Cost impacts include both approved and pending changes to date.
Note 3: RHS = Rock Handling System
Chart: 
| Code/Standard Change | Design Change | Differing Conditions | RHS Performance | Existing Facility Failure | Covid-19 | Weather | Other
Total | 5072563 | 5894017 | 3301073 | 17105483 | 12733364 | 185264 | 963483 | 66079

## Slide 5: Access/Infrastructure Related Costs and Delays – 1 of 6
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | DATE OF IMPACT | TIME IMPACT
006 | Bird’s Nest Ore Hoist | The South Skip cable had a bird nest incident. Rope had to be cut and re-socketed in the field | $976,946 | 4/7/2021 - 4/19/2021 | 0
009 | Ross Shaft Shutdown 7/9/21 | Ross shaft shutdown by SDSTA for 5 shifts (malfunction of hoist controls) | $308,248 | 7/9/2021 - 7/11/2021 | 2.5
011 | Trolley Drift MLC Bay | Yates Shaft was shutdown by SDSTA due to shaft instability (need additional room for construction equipment) | $47,378 |  | 0
012 | Yates Shutdown 6/29/21 thru 12/16/21 | Yates was shutdown by SDSTA due to shaft instability; TMI was required to resequence the work to avoid total stoppage | $1,717,430 | 6/29/2021 - 12/16/2021 | 21
013 | Ross Shaft Shutdown 8/2/21 thru 8/3/21 | Ross Shaft was shutdown by SDSTA due to sheave wheels bearing being changed on the skips | $217,386 | 8/2/2021 - 8/3/2021 | 1.5
019 | Ross Shaft Power Outage 9/21/21 thru 9/22/21 | All work was suspended underground due to no power on the 4850L and 5000L | $33,327 | 9/21/21 - 9/22/21 | 0
034 | East Drift Resequencing | Critical path work had to be re-sequenced due to Yates Shaft Shutdown (no access from the east end of cavern) | $580,129 | 6/29/2021 - 12/16/2021 | 7
040 | Mine Evacuation and Ross Shutdown | Fire on 1700L and slack rope event on the cage hoist rope | $45,122 | 3/9/2022 - 3/15/2022 | 0
041 | Ross Shaft Power Outage on 4/25 and 4/26/22 | No power to Ross Headframe | $114,200 | 4/25/2022 - 4/26/2022 | 0
044 | Ross Shaft Power Outage on 7/19/22 | No power to Ross Headframe | $92,628 | 7/19/2022 - 7/20/2022 | 0

## Slide 6: Access/Infrastructure Related Costs and Delays – 2 of 6
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | DATE OF IMPACT | TIME IMPACT
045 | Ross Brow Shotcrete Material | Ross Brow excavation was rescheduled due to Yates Shutdown June 29 – December 16, 2021 | $45,969 | 6/29/2021 - 12/16/2021 | 0
046 | Ventilation Reduction on 7/4/22 thru 7/5/22 | SDSTA Oro Hondo Fan Shutdown (limited work to one cavern heading) | $34,495 | 7/4/2022 - 7/5/2022 | 0
049 | Ross Shaft Interruption on 7/30/22 | Power outage at Ross Shaft (no work underground) | $2,236,300 | 7/30/2022 - 8/11/2022 | 0
050 | Mine Evacuation on 3/9/22 and Ross Shaft Shutdown on 3/15/22– Indirect Costs | Fire on 1700L and slack rope event on cage hoist rope | $30,519 | 3/9/2022 - 3/15/2022 | 0.5
051 | Ross Shaft Power Outage 4/25/22 thru 4/26/22 – Indirect Costs | No power to Ross Headframe | $61,279 | 4/25/2022 - 4/26/2022 | 1
053 | Ross Shaft Power Outage on 7/19/22 – Indirect Costs | No power to Ross Headframe | $32,526 | 7/19/2022 - 7/20/2022 | 0.5
054 | Ross Shaft Interruption on 7/30/22 | Power outage at Ross Shaft (no work underground) (NOTE: outage was caused by failure of LBNF installed component; however, duration was significantly extended due to reliance of SDSTA infrastructure on this circuit. | $704,721 | 7/30/2022 - 8/11/2022 | 18.5
055 | Ventilation Reduction on 10/18/22 | Oro Hondo Fan Shutdown by SDSTA for upgrading works (limited work to one cavern heading) | $41,833 | 10/18/2022 - 10/18/2022 | 0

## Slide 7: Access/Infrastructure Related Costs and Delays – 3 of 6
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | DATE OF IMPACT | TIME IMPACT
057 | Ross Cage Incident 11/7 Direct Costs | SDSTA suspended the underground work due to Ross Cage Incident | $30,043 | 11/7/2022 - 11/7/2022 | 0
058 | Ross Cage Incident 11/7 Indirect Costs | SDSTA suspended the underground work due to Ross Cage Incident | $29,015 | 11/7/2022 - 11/7/2022 | 0.5
059 | Ventilation Reduction 12/6/22 Direct | SDSTA restricted the underground ventilation due to an electrical maintenance outage for the Oro Hondo Fan | $77,521 | 12/6/2022 - 12/6/2022 | 0
064 | 2.5 Day Ventilation Shutdown 1/18/23 Direct Costs | SDSTA shut down the Oro Hondo Fan, which restricted underground construction work | $411,815 | 1/18/2023 - 1/20/2023 | 0
068 | 2.5 Day Ventilation Shutdown 1/18/23 Indirect Costs | SDSTA shut down the Oro Hondo Fan, which restricted underground construction work | $144,729 | 1/18/2023 - 1/20/2023 | 2.5
075 | Ventilation Reduction 2/21/23 Direct | SDSTA restricted the underground ventilation to prevent the Yates Shaft from freezing during extreme winter cold temperatures | $69,318 | 2/21/2023 - 2/24/2023 | 0
077 | UG Shutdown 3/31/23 Direct Costs | The Subcontractor was restricted from executing underground construction work during the SDSTA Planned Maintenance Shutdown | $237,248 | 3/31/2023 - 4/1/2023 | 0
078 | UG Shutdown 3/31/23 Indirect Costs | The Subcontractor was restricted from executing underground construction work during the SDSTA Planned Maintenance Shutdown | $86,838 | 3/31/2023 - 4/1/2023 | 1.5

## Slide 8: Access/Infrastructure Related Costs and Delays – 4 of 6
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | DATE OF IMPACT | TIME IMPACT
092 | Ventilation Reduction 12/6/22 Indirect | SDSTA restricted the underground ventilation due to an electrical maintenance outage for the Oro Hondo Fan | $25,324 | 12/6/2022 - 12/6/2022 | 0.5
094 | Fan Outage 5/24 Direct | Oro Hondo ventilation fan outage. 6am – 11am. | $44,422 | 5/24/2022 - 5/24/2022 | 0
097 | Fan Outage 5/24 Indirect | Oro Hondo ventilation fan outage. 6am – 11am. | $27,425 | 5/24/2022 - 5/24/2022 | 0.5
099 | Oro Hondo Fan Outage 6/6 Direct | Oro Hondo ventilation fan outage. | $805,148 | 6/6/2023 - 6/11/2023 | 0
100 | Oro Hondo Fan Outage 6/6 Indirect | Oro Hondo ventilation fan outage. | $280,469 | 6/6/2023 - 6/11/2023 | 5
101 | Oro Hondo Fan Outage 6/23 Direct | Oro Hondo ventilation fan outage. 6pm to 10pm | $39,552 | 6/23/2023 - 6/23/2023 | 0
102 | Oro Hondo Fan Outage 6/23 Indirect | Oro Hondo ventilation fan outage. 6pm to 10pm | $14,023 | 6/23/2023 - 6/23/2023 | 0.25
103 | Ventilation - Hoist Issue 6/13 Direct | Ross Shaft Cage issue. 0.5 shift lost. | $35,761 | 6/13/2023 - 6/13/2023 | 0
104 | Ventilation - Hoist Issue 6/13 Indirect | Ross Shaft Cage issue. 0.5 shift lost. | $14,023 | 6/13/2023 - 6/13/2023 | 0.25

## Slide 9: Access/Infrastructure Related Costs and Delays – 5 of 6
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | DATE OF IMPACT | TIME IMPACT
105 | Ventilation Interruption 7/3 Direct | Ventilation failed for 3 hours. | $40,386 | 7/3/2023 - 7/3/2023 | 0
106 | Ventilation Interruption 7/3 Indirect | Ventilation failed for 3 hours. | $13,979 | 7/3/2023 - 7/3/2023 | 0.25
117 | Power Outage 8/30 Direct | Power outage for relocation of utilities. 8:15am to 12:15pm | $50,849 | 8/30/2023 - 8/30/2023 | 0
118 | Power Outage 8/30 Indirect | Power outage for relocation of utilities. 8:15am to 12:15pm | $27,845 | 8/30/2023 - 8/30/2023 | 0.5
119 | Ventilation Issue 8/21 Direct | Alarm closed Yates Roll up door creating reduction in ventilation. 6pm to 11pm. | $2,875 | 8/21/2023 - 8/21/2023 | 0
123 | Power Outage 9/25-30 Direct | Loss of Power to underground from Ross substation due to damaged junction box. | $896,140 | 9/25/2023 - 9/30/2023 | 0
124 | Power Outage 9/25-30 Indirect | Loss of Power to underground from Ross substation due to damaged junction box. | $306,901 | 9/25/2023 - 9/30/2023 | 5.5
125 | Water Supply Shortage 10/5-13 Direct | Oct 5th & 6th water loss over 5-6hrs. Oct 10th water loss 7.5hrs. Oct 11-13 continued with water supply issues. Total delay 1 day. | $157,128 | 10/5/2023 - 10/13/2023 | 0
126 | Water Supply Shortage 10/5-13 Indirect | Oct 5th & 6th water loss over 5-6hrs. Oct 10th water loss 7.5hrs. Oct 11-13 continued with water supply issues. Total delay 1 day. | $55,722 | 10/5/2023 - 10/13/2023 | 1

## Slide 10: Access/Infrastructure Related Costs and Delays – 6 of 6
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | DATE OF IMPACT | TIME IMPACT
127 | Ross Cage Slack Rope Incident 10/14-18 Direct | Ross Cage slack rope incident | $824,396 | 10/14/2023 - 10/18/2023 | 0
128 | Ross Cage Slack Rope Incident 10/14-18 Indirect | Ross Cage slack rope incident | $278,610 | 10/14/2023 - 10/18/2023 | 5
131 | Power Outage 11/6/2023 - Direct | Power outage to replace cable connections in the shaft. 3 shift outage. | $255,269 | 11/6/2023 - 11/7/2023 | 0
132 | Power Outage 11/6/2023 - Indirect | Power outage to replace cable connections in the shaft. 3 shift outage. | $83,754 | 11/6/2023 - 11/7/2023 | 1.5
 |  | TOTAL IMPACT | $12.7M |  | 72.25 Days

## Slide 11: Weather
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | TIME IMPACT
060 | 4.5 Weather Days 2022 Direct | Excavation Subcontractor is entitled to compensation when weather delays exceed seven calendar days in a year. | $707,160 | 0
067 | 4.5 Weather Days 2022 Indirect | Excavation Subcontractor is entitled to compensation when weather delays exceed seven calendar days in a year. | $256,323 | 4.5
 |  | TOTAL IMPACT | $963,483 | 4.5 Days

## Slide 12
BSI Subproject

## Slide 13: BSI Risk Register
RI-ID | Title | Probability | Cost Impact | Schedule Impact | P * Impact (k$) | P * Impact (months)
RT-131-FSCF-BSI-001 | FS Union Work Stoppage Delays Project at Far Site (BSI) | 5.00% | 0 | 0--0.25--0.5 months | 0 | 0.0
RT-131-FSCF-BSI-002 | FS ESH Incident Stops Work Temporarily (BSI) | 10.00% | 0 -- 100 -- 1000 k$ | 0.5 -- 1 -- 6 months | 37 | 0.3
RT-131-FSCF-BSI-003 | FS Codes or standards change resulting in scope increases FS (BSI) | 10.00% | 0 -- 550 k$ | 0 -- 2 months | 28 | 0.1
RT-131-FSCF-BSI-004 | Far Site construction activities impact neighboring communities (BSI) | 10.00% | 0 -- 250 k$ | 0 -- 1 months | 13 | 0.1
RT-131-FSCF-BSI-005 | FS SURF infrastructure projects impact LBNF/DUNE project (BSI) | 50.00% | 0 -- 1000 k$ | 0 -- 0.5 -- 1 months | 250 | 0.3
RT-131-FSCF-BSI-006 | FS Ross skip hoist brakes failure (BSI) | 10.00% | 500 k$ | 2 months | 50 | 0.2
RT-131-FSCF-BSI-007 | FS Ross skip drum cracks require repair (BSI) | 5.00% | 687 k$ | 1.5 months | 34 | 0.1
RT-131-FSCF-BSI-008 | Old timber at Far Site combusts spontaneously (BSI) | 1.00% | 0 -- 100 -- 1000 k$ | 2 -- 4 -- 6 months | 4 | 0.0
RT-131-FSCF-BSI-009 | Delays obtaining AHJ or Other Regulatory Approvals | 10.00% | 25 -- 100 -- 500 k$ | 0 -- 3 months | 21 | 0.2
RT-131-FSCF-BSI-010 | Specialized construction labor is unavailable | 15.00% | 1000 -- 5000 k$ | 0 -- 1 months | 450 | 0.1
RT-131-FSCF-BSI-011 | FS General Security at SURF (BSI) | 1.00% | 0 -- 1000 k$ | 0 -- 6 months | 5 | 0.0
RT-131-FSCF-BSI-012 | FS Unavailability of SURF or FRA supplied systems & spaces at SURF-high prob,low imp (BSI) | 50.00% | 0 -- 250 -- 1500 k$ | 0 -- 0.25 -- 1.5 months | 292 | 0.3
RT-131-FSCF-BSI-013 | Cryogenics or FD changes impact layout/design of Far Site facilities (BSI) | 10.00% | 250 -- 3000 -- 5000 k$ | 0 -- 1 months | 275 | 0.1
RT-131-FSCF-BSI-015 | Oro Hondo shaft ventilation path is blocked (BSI) | 1.00% | 0 -- 50000 k$ | 0 -- 24 months | 250 | 0.1
RT-131-FSCF-BSI-016 | Water inundation to underground spaces at Far Site (BSI) | 5.00% | 0--200 k$ | 0--0.1 months | 5 | 0.0
RT-131-FSCF-BSI-018 | Ross shaft logistic interference EXC/BSI/Cryostat #1 delays FSCF contractors (BSI) | 25.00% | 500 -- 3000 k$ | 1 -- 3 months | 438 | 0.5
RT-131-FSCF-BSI-019 | BSI Long Lead Delays | 15.00% | 0 -- 500 k$ | 0 -- 1 months | 38 | 0.1
RT-131-FSCF-BSI-020 | Escalation/Market uncertainty exceeds plans | 50.00% | 4500 -- 9000 k$ | 0 months | 3,375 | 0.0
RT-131-FSCF-BSI-021 | FS Unavailability of SURF or FRA supplied systems & spaces at SURF-low prob,high imp (BSI) | 5.00% | 1500 -- 6000 k$ | 1.5 -- 6 months | 188 | 0.2
RT-131-FSCF-BSI-022 | Shaft Piping Contracted Outside SDSTA | 25.00% | 0 -- 300 k$ | 1 -- 6 months | 38 | 0.9
RT-131-FSCF-BSI-024 | Yates Shaft Interruption resulting in delays to BSI Construction | 5.00% | 0 -- 250 k$ | 0 -- 0.25 months | 6 | 0.0
RT-131-FSCF-BSI-025 | General Logistics/Subcontractor Productivity Delays | 25.00% | 0 k$ | 0 -- 1.8 -- 3.6 months | 0 | 0.5
RT-131-FSCF-BSI-026 | Commissioning Delays | 25.00% | 0 k$ | 0.5 -- 1 -- 3 months | 0 | 0.4
RT-131-FSCF-BSI-027 | Weather delays exceed budget | 20.00% | 0 -- 125 -- 250 k$ | 0 -- 0.125 -- 0.25 months | 25 | 0.0
RT-131-FSCF-BSI-216 | Extended review and consent periods on FSCF BSI bid trade packages | 15.00% | 0 -- 1000 -- 4000 k$ | 0 -- 1 -- 4 months | 250 | 0.3
RT-131-FSCF-BSI-226 | Far Site BSI Facilities as-built conditions are not as anticipated | 20.00% | 50 -- 1000 k$ | 0 -- 1 months | 105 | 0.1

## Slide 14: FS ESH Incident Stops Work Temporarily (BSI)
Only assumed 10% probability of a serious enough incident to stop the project
Assumed 2 weeks to 6 months based on lab experience
Most likely event is not injury, but equipment damage – like the cage drop incident

## Slide 15: Far Site construction activities impact neighboring communities (BSI)
Most likely issue for BSI (or FDC) is trucking
Assume up to a month based on “shut down” imposed by city for dust issues
10% likelihood. We’ve already heard concerns about trucking on Mill street from the community

## Slide 16: SDSTA Infrastructure related risks
FS Ross skip hoist brakes failure (BSI)
FS Ross skip drum cracks require repair (BSI)
Old timber at Far Site combusts spontaneously (BSI)
FS Unavailability of SURF or FRA supplied systems & spaces at SURF-high prob,low imp (BSI)
FS Unavailability of SURF or FRA supplied systems & spaces at SURF-low prob,high imp (BSI)
Oro Hondo shaft ventilation path is blocked (BSI)
Water inundation to underground spaces at Far Site (BSI)
Yates Shaft Interruption resulting in delays to BSI Construction
Average Delay for EXC: 18 days/yr (36 shifts)

## Slide 17: Logistics Related Delays
Ross shaft logistic interference EXC/BSI/Cryostat #1 delays FSCF contractors (BSI)
General Logistics/Subcontractor Productivity Delays
  Note that logistics and productivity are very related – if a contractor gets pushed to a different cage down or up, they lose productive hours.
FS SURF infrastructure projects impact LBNF/DUNE project (BSI)
  Impact of SURF expansion project not well understood.
  One known impact is 18 people on day shift, which is essentially a full cage
  Several slung loads of equipment down and up must be fit into the schedule
Logistic delays during EXC have been minimal, but shaft sharing was much more limited than it will be during BSI/FDC

## Slide 18: Weather delays exceed budget
KAJV contract includes 7 weather days/year – we don’t get charged unless we exceed that.
Average 2019-2023 is 8.4 shifts/yr (4.2 days), but we had 22.8 shifts (11.4 days) in 2022. The average is also skewed by COVID delays in 2020 during the worst time of year
Most frequently delays in March, April, and October, but our longest delays were in December 2022 (9.5 shifts and 4 shifts in the same month).

## Slide 19: Commissioning Delays
There’s a lot of commissioning that has to simulate loads since FDC won’t be operational when BSI completes. This will require a lot of coordination with FDC

## Slide 20: Cryogenics or FD changes impact layout/design of Far Site facilities (BSI)
Recent changes in electrical loads for LN system are expected to result in a 4-6 month delay in procurement of the transformers feeding that equipment.
  We’ve got float on this, but it illustrates the impact of changes at this late date.
There seems to still be uncertainty on a number of items:
  Power demand for Equipment on FDC mezzanines
  Fire suppression for FDC installation
  Networking (where to run fiber, WAPs, etc)
  Bridges and stairs (FDC scope, but has some influence on things like lighting

## Slide 21
EXC Subproject Back-Up Slides

## Slide 22: Code / Standard Change
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | TIME IMPACT
008 | ACGIH Impacts | Changes to Air Quality Standards | $1,231,902 | 0
032 | Sanitary Services | Request TMI to provide underground sanitary services | $103,894 | 0
035 | Ventilation Variance Part 1 | Assess and design new ventilation system to meet new variance requirements | $267,023 | 0
048 | Ventilation Variance Part 2 | Additional ventilation equipment required to meet new variance requirements | $3,348,717 | 0
066 | EA Audit Actions | Contract changes following EA audit | $27,456 | 0
122 | CT Bolt Abandonment | Means of securing of abandoned CT bolts | $93,571 | 0
 |  | TOTAL IMPACT | $5.07M | 0 Days

## Slide 23: Design Related Changes – 1 of 2
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | TIME IMPACT
005 | Design Changes | Design changes to spray chamber | $95,483 | 0
010 | Design Changes | Design changes to spray chamber | $435,649 | 0
015 | Design Changes | Various | $75,165 | 0
023 | Monorail Support Bolts | Additional bolts for monorail required | $87,467 | 0
026 | WWF Continuity Tester | Design change to testing of WWF | $11,115 | 0
037 | Back alteration for ATC | Modification of shotcrete surface to enable testing equipment to pull test bolts | $58,441 | 0
047 | Ross Brow Crane | Additional works for TMI to erect crane at Ross Brow | $408,806 | 0
061 | Bulletins 8 & 9 Instrumentation | Design change associated with Multi-point Borehole Extensometers | $48,382 | 0
070 | Fiber Line, Network Switches & WiFi | Install fiber line, network switches and Wi-Fi for NO2 Monitors | $35,498 | 0
071 | SDSTA Rail Rehab | Additional scope of work associated with replacing deteriorating rail at the 4-Winze Wye | $56,733 | 0
072 | Test Blast Niche Concrete | Additional scope of work to provide concrete slab at the Test Blast Niche located in the South Access Drift | $9,525 | 0

## Slide 24: Design Related Changes – 2 of 2
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | TIME IMPACT
079 | Bridge Abutment Design Change | A design modification was made to the cavern bridge abutments | $6,781 | 0
080 | Ross Brow Design Changes | Bulletin 9 added the following scope of work to the excavation of the Ross Brow: Drainage Bore Holes, Concrete Ore Pass Wall and Station Rail Modifications | $1,025,913 | 0
086 | Bulletin 10 Ross Back Door | Excavation as rear of shaft to provide secondary access / egress if front of cage exit is compromised during Ross Brow excavation | $369,202 | 0
087 | Ross Brow Crane | FRA required TMI to purchase and install Crane for Ross station | $169,817 | 0
089 | Monorail Beam Tolerances | Placeholder. Differences between steel standards | $3,000,000 | 0
 |  | TOTAL IMPACT | $5.9M | 0 Days

## Slide 25: Differing Site Conditions - 1 of 2
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | TIME IMPACT
014 | Ore Pass Plug | 4850-31 dump area encountered a larger Ore Pass than was predicted in the original scope of work. TMI had to seal of the larger opening above their waste dump for safety reasons | $681,424 | 0
017 | Grizzly Changes | 4850-31 dump area encountered a larger Ore Pass than was predicted in the original scope of work. TMI had to install a larger grizzly. | $301,982 | 0
020 | Victaulic Pipe Drain | Drain hole intercepted during excavation on 4850-05. Pipeline needed to be added to divert the water to invert. | $48,074 | 0
043 | Oro Hondo Ventilation Shaft | Bulkhead wall needed to be removed to create larger opening on 3650L | $58,132 | 0
083 | DSC Cracked Shotcrete | Subcontractor was required to add more rock bolts to remedy the issue | $62,855 | 0
084 | DSC Replace Mezzanine bolts 2 & 4 | Replacement of mezzanine anchor bolts due to adverse ground | $46,160 | 0
085 | DSC Pilar 4850-33/16 Indirect | Indirect costs and time impacts for repair to pillar | $208,397 | 4
091 | DSC 4850-16-33 Rib Rehab Direct | Repair to pillar due to differing ground conditions | $193,938 | 0

## Slide 26: Differing Site Conditions - 2 of 2
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | TIME IMPACT
093 | DSC Cracked Shotcrete E Pillar 4850-37-17 | Repair to pillar due to differing ground conditions | $39,239 | 0
096 | DSC 4850-16-33 NW Pillar Rehab Phase 2 - Indirect | Indirect costs and time impacts for repair to pillar | $1,218,031 | 21
108 | 4850-37 N Rib Reinf Change | Additional ground support | $102,516 | 0
109 | 4850-37/17 Add'l Mezz Anchors | Additional ground support | $38,574 | 0
112 | 4850-37 N Rib Reinf Change Indirect | Indirect costs and time impacts for additional ground support | $113,392 | 2
120 | DSC 4850-37 W Endwall Bolt Spacing | Additional ground support | $5,876 | 0
121 | DSC 4850-37 South Abutment Add'l Mezz Brackets | Additional support for bridge abutment due to differing ground conditions | $182,483 | 0
 |  | TOTAL IMPACT | $3.30M | 23 Days

## Slide 27: Rock Handling System (RHS) Performance – 1 of 2
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | TIME IMPACT
004 | RHS Commissioning | Provide commissioning support | $129,970 | 0
016 | RHS Blow Piping Labor 3Q-4Q21 | TMI required to employ more labor to blowpipe the Ore Bins and 5000L | $227,762 | 0
021 | Chute Vibrators | Improvements to RHS at crusher chute area | $51,133 | 0
022 | Rock Plows | Improvements to conveyor | $18,659 | 0
028 | Dust Control Additive | TMI needed to add dust control additive to conveyor belt to reduce dust at the Open Cut | $471,423 | 0
030 | Double Handling of Muck | Due to stoppage of conveyor belt at the Open Cut due to the dust issues at the park and into public areas | $169,202 | 0
031 | RHS Restocking | TMI required to purchase addition RHS spare parts | $6,578 | 0
038 | RHS Blow Piping Labor 4Q21-2Q22 | TMI required to employ more labor to blowpipe Ore Bins and 5000L | $427,408 | 0
039 | HPU and Diverter Gates | TMI required to purchase addition RHS spare parts | $71,388 | 0
062 | RHS Blow Piping Labor 1Q-4Q23 | Additional labor required to move plugged muck using a blow pipe | $1,418,165 | 0
063 | RHS Blow Piping Labor 3Q-4Q22 | Additional labor required to move plugged muck using a blow pipe | $174,722 | 0

## Slide 28: Rock Handling System (RHS) Performance – 2 of 2
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | TIME IMPACT
065 | Skip Loader Modifications | Rock Handling System modifications to improve field production | $11,954 | 0
069 | Bin Rail Torn Belt Repair | Damaged conveyor belt due to deteriorating infrastructure in the Ore Pass | $23,476 | 0
073 | Extended Services |  | $629,618 | 0
074 | Skip Calibration Support | Purchased rock quarry material for payload calibration | $7,885 | 0
076 | Muck Re-handling | Double handling of muck due to limitations with the RHS | $22,168 | 0
088 | RHS Rock Plows | Additional of rock plows to improve RHS. Not in original design. | $16,219 | 0
110 | WAD Rehabilitation | Replace WAD invert after being used as muck storage. | $1,099,451 | 0
111 | Muck Re-handling 2Q2023 | Double handling of muck due to skipping performance not meeting contract requirements. | $24,677 | 0
113 | Concrete Protection | Protecting concrete in CUC as equipment needs to be stored due to Yates shaft delays and resequencing of works | $103,625 | 0
115 | Resequencing | TMI claim for trade stacking and RHS performance. | $12,000,000 | 0
 |  | TOTAL IMPACT | $17.1M | 0 Days

## Slide 29
Other
PCO NO. | TITLE | DESCRIPTION | COST IMPACT | TIME IMPACT
082 | RRB Site Visit 3/30/2023 | Subcontractor instructed to light cavern for RRB Site Tour | $2,479 | 0
090 | Camera Installation | Install camera into 4850-09 to monitoring mucking activities. | $43,203 | 0
107 | VIP Visits Aug 2023 Directs | Preparation for politician VIP visit. | $20,397 | 0
 |  | TOTAL IMPACT | $66,079 | 0 Days