## Slide 1
PRR Preparation for Cathode
Fabien Cavalier, Mar 5th 2024
Reason of the PRR:
Launch of call for tenders for cathode frames and resistive meshes
Long tendering process (4-5 months)
Long production time (> 1 year after ordering)
Scope of the review:
For the production of the ½ cathode frames (with final transport boxes) in the industry (~600 k€)
For the production of the resistive meshes in the industry (~350 k€)
Out of the scope:
Cathode suspension system (TAD, LAD, ropes)
Electrical connection
Assembly at IJCLab
Installation at SURF
Call for tenders in preparation with CNRS purchase office:
Specific technical terms and conditions (STTC) document almost written (in French)
Target date for call: week 18 (end of April) => final versions one week before

## Slide 2
Systems Engineering/Mechanical Engineering:
Integrated models : OK
Final fabrication drawings : almost done, foreseen for the end of the week
Approved installation plan : non applicable
Electrical Engineering: non applicable
Compliance Office:
Documentation of electrical and mechanical safety reviews: Document for Module-0 available. Need to check with CO if the minor modifications impact the structural behavior and imply a new version
Engineering codes and standards to be applied in the manufacturing process: in STTC
Welder qualification requirements and specification of qualified weld procedure: non applicable
Commercial vendor QC requirements including: in STTC
  Certified material test reports
  Certificates of compliance.
  General test/inspection reports.
Plans for critical handling of components: in STTC
Status of requested information for PRR

## Slide 3
Technical Coordination:
Production Schedule: in STTC
Shipping plan and schedule: in STTC (up to IJCLab)
Plan for resources (facilities, infrastructure, and workforce): To be done (describe space available at IJCLab for reception and associated manpower for control and reception)
Plans for component procurement including procurement specifications: in STTC
Delineation of responsibilities and required signoffs for each stage of shipping process: in STTC
Review Office:
Responses to previous review recommendations: To be done
Final testing and performance results from prototyping activities: To be done (describe activities in ColdBox + Module-0). Presented at Collab Meeting
Description of design changes occurring after the Final Design Review: To be done (Removal of glue for final assembly at SURF, reduction of the numbers of crossribs, additional holes for PDS). Presented at Collab Meeting
Project ES&H:
Production facility safety plans: non applicable
Hazard analyses for the production and manufacturing processes: non applicable

## Slide 4
Project Quality Assurance:
Detailed manufacturing procedures: in STTC
Shipping, handling, and storage requirements: in STTC
QC Plan including in STTC
  Applicable specifications, drawings, and procedures.
  List of components to be inspected and tested.
  Codes and standards to be incorporated in the tests to be performed.
  Description of all inspections and tests to be performed during manufacturing.
  Locations where tests will be performed.
  Descriptions of technical requirements being verified by each inspection and test.
Manufacturing traveller documents incorporating in STTC
  In-process and final inspection steps.
  Acceptance criteria at each step.
Plan for documentation of non-conforming items evaluated as acceptable for use. In STTC
Documentation of assigned responsibilities for who signs-off on each step in the QC process. In STTC

## Slide 5
Conclusion
All information available
Few documents to be written:
  Mainly the one for Review Office
  English version of STTC to be done (existing one in French)
  Eventually new version for Compliance Office
PRR on week 14 (April 2nd-5th) will be perfect for our timing => all documents given on March 25th