## Slide 1: LBNF Primary Vacuum and Magnet Installation Kevin Duel (L4), Ty Funk, Rob Ridgway, Parth Gandhi, Monika Sadowski, Jason Morin, Scott Oplt, Eric Pirtle, Dirk Hurd, Freddie Roman, Matthew Volante, James Williams, Dan Vrbos
Primary Vacuum
  Final Design Review held this past Wednesday (1/17)
  Work continues on vacuum layout/installation drawings
    Plan to release component drawings after receiving FDR report
  Kicker ceramic beam tube alternate coating testing continues
    Outgassing tests in queue at NWA
    12” long tube samples on their way to vendor for coating
  Dipole magnet beam tube installation demo performed in December
Magnet Installation
  MI enclosure corrector stand engineering note review in progress
  PBE quad stands and MI quad and dipole stands engineering notes reviewed and approved
  PBE dipole stand and multiwire stand design/drafting and engineering note review in progress
  Preparing for Final Design Review in mid-February 2024
Kicker beam tube coating resistance measurement
12” samples for coating
Dipole beam tube installation demo