## Slide 1
FAST / IOTA Shutdown 2023-2024
Enclosure STATUS: ODH-0 & Supervised Access
ES&H: -South gate of cave (P™). LL OSC Mode (too) active
IPI: -Cable pull on hold (2 wks left)(Heliax, VAC)
  -All Girders & RFQ set. Stands in. Most optics in place
  -6” coax installation in progress (w/ Rick Z)
  -600A Disconnect installed
Cryo: -Working on cryo system: repairs, testing, LN2 #45 (@5K Q3)
ISD: -Lights changed™, “Everything OK alarm” (P™), ICW (Q2), -ESB HVAC (Q3), fdr #35 HV PM (May 2024)
Water: -GN2 Back-up system ready. Chiller waiting on contractor
— Contact FAST RunCo with any work or access requests —

## Slide 2: ISD/CFM Report on NML Status
HiBay LEDs: “in Procurement™” to issue PO (materials are onsite)
LED upgrade: (Exterior and Non-HiBay Interior) RFQ to contractors
Gravel for ESB south door (R&G) (Spring?)
Emergency Generator:
  New heater repair scheduled™ for Jan 24th (2024???)
  Procurement™ dropped the ball with the contractor
ESB HVAC install – still waiting on contract submittal (P™)(Spring?)