## Slide 1: LBNF - Beamline – Target Complex
Horns
  Continued work on drawings of inner and outer conductors of Horns B & C.
  Friction Stir Welding vendor verification continues
    SDSMT is to rework weld
    Negotiating with PNNL to do samples
    German vendor samples x-ray and found acceptable (QA./QC)
  Started assembly of Prototype hangers
  Flipping fixture tested safely and successfully

## Slide 2: LBNF - Beamline – Target Complex
Horns Power Supply
  Many procurements occurring for the full power supply for the Horns Test Stand at MI-8.
    Components are arriving
  Electrical work continues at MI-8 to support Test stand power supply and water-cooling system.
Water Systems
  RAW system designs continue
  Finished drawings of Horn Test Stand water- cooling system
Test Stand
  Preparing to grout in place

## Slide 3: LBNF - Beamline – Target Complex
Stripline
  FEA modeling of stripline
  Modeling and drafting has begun on final design of stripline tee segments
Remote Handling
  Check of designed lifting fixture being appropriate for possible change of COG for Horn A Module with Stripline Block and Target Utility Block