## All Recommendations & Pre-Start
IRR 1b Report Recommentdations
Type | Document/Topic | Number |  | Recommendation | Assigned to | Resolution | Status | Comments
Recommendation | Credited Controls | Pre-Start #1 | Pre-Start | Label all Credited Contorls in the tunnels and work areas prior to beginning operations | Maddie/Jeremy + Help
|  |  |  | - Booster | Salah | complete | Done with exception, 24 penitrations blocked by equipment.
|  |  |  | - 8 GeV | Marty | will be complete pre-start (post-ASE signing)
|  |  |  | - BNB | Jason | complete | done see elog entry for pictures | https://www-bd.fnal.gov/Elog/?orEntryId=254412
|  |  |  | - MI/RR | Marty | will be complete pre-start (post-ASE signing)
|  |  |  | - NuMI | Phil | complete | 1 remains to be done when access is possible | identified and plan in place to begin addressing tomorrow (labels in hand) 2/28; accessible (4 of 5) completed, Target hall shield pile will be labeled at the 1st opportunity (2/29)
Recommendations | ASE | Pre-Start #2 | Pre-Start | Ensure that the ASE Accelerator Operating Pramater Credited Control value(s) accurately reflect the MCI analysis summarized in the SAD
|  |  |  | - Booster | Salah | complete | Done
|  |  |  | - 8 GeV | Marty | complete | done
|  |  |  | - BNB | Jason | complete | Done | I did confirm with Joel that the CC chimpunk currently has a 1 mrem setting (it has a 2.5 mrem CC limit).
|  |  |  | - MI/RR | Marty | complete | done
|  |  |  | - NuMI | Phil | complete | done
Recommendation | MCI | Pre-Start #3 | Pre-Start | Complete MCI analysis for each segment prior to beginning operations
|  |  |  | - Booster | Lionel | complete | sent to SRSO
|  |  |  | - 8 GeV | Marty | complete | done
|  |  |  | - BNB | Jason | complete | Done
|  |  |  | - MI/RR | Marty | complete | done
|  |  |  | - NuMI | Phil | complete | done
Recommendation | SAD | Post-Start #1 | Post-Start | Ensure SAD Chapters accurately document soil activation hazard, or discuss why it is not applicable
|  |  |  | - Booster | Salah |  | Done
|  |  |  | - 8 GeV | Marty
|  |  |  | - BNB | Jason | I consider Post-Start #1 to be done, but I have not recieved feedback on the acceptability of the text. | Done
|  |  |  | - MI/RR | Marty
|  |  |  | - NuMI | Phil | addressed similarly to BNB per Mary's suggestion (2/23) | done
Recommendation | SAD | Post-Start #2 | Post-Start | Clarify how the MCI parameters are presented/discussed in the SAD Chapters. | Matt/Mary
Recommendation | SAD | Post-Start #3 | Post-Start | Discuss NuMI remote handling activities as a unique Non-Accelerator Specific Hazard (NASH) within the NuMI SAD Chapter rather than referring to the common NASH Risk Matrix table (within SAD Appendix C). | Marty | I added more discussion and pointed to the activation discussion as well (phil 2/23) | done
Recommendation | SAD | Post-Start #4 | Post-Start | Rectify identified typos and suggested wording edits.
|  |  |  | - Booster | Salah |  | Done
|  |  |  | - 8 GeV | Marty
|  |  |  | - BNB | Jason | I consider Post-Start#4 to be done, but I have not recieved feedback on the acceptability of my corrections. | Done
|  |  |  | - MI/RR | Marty
|  |  |  | - NuMI | Phil | addressed all but 2 myself and passed 2 up the chain as I was unable to fix them; they appear to be fixed to the best of my ability to check them (8.2.1.6 and page 43) 2/23 | done
Opportunity for Improvement | SAD | OFI #1 |  | Consider limiting discussions within the SAD Chapters to that segment and only the immediately upstream and downstream segments. |  | addressed for NuMI (phil 2/24)
Opportunity for Improvement | MCI, SAD, presentations | OFI #2 |  | Ensure numbers in the calculations are accurate (considering rounding and significant figures).
Opportunity for Improvement | SAD, presentations | OFI #3 |  | Clarify that LOTO procedures are to be reviewed and updated annually, not ALL procedures.
Noteworthy Practices |  | NP #1 |  | The use of AI to locate the source of beam loss or a drift in the beam position should be very helpful in hot spots before a team provides a rad survey, and could be useful targeting and prioritizing maintenance activities.
Noteworthy Practices |  | NP #2 |  | Fermilab has developed training for staff that will screen proposed actions and as-found conditions for potential USIs. This is a good start, and a way to integrate the USI process in work planning activities.
LIST OF TYPOS TO GO WITH POST-START #4
Booster SAD
o RPP is an acronym used on page 26 (27/45) without being defined in the list, but in the text. | [6 empty] | Done
o 4.2.1.10 Contamination on page 26 (27/45) should be “Justify” paragraph for consistency | [6 empty] | Done
o 4.2.2.1 Beryllium on page 28 (29/45) please use Absorber, instead of dump, to ensure consistency of the area mentioned | [6 empty] | Done
o 4.2.3 On page 28 (29/45) not sure why this sentence is there “Unusual hazards are present in the form of flammable hydrogen gas used in the source.” | [6 empty] | Done
o 4.2.4.1 Stored Energy Exposure incomplete sentence and too many capitalizations “Their Standard Operating procedures to mitigate this hazard. | [6 empty] | Done
o 4.2.4.3 Page 30 (31/45) missing break line between paragraphs for consistency | [6 empty] | Done
o 4.2.8.1 Fringe Fields suggested re-word “Should such a system be added, the provisions of the FESHM will be implemented.” to “Should such a system be added, provisions from FESHM will be implemented.” and … “Fields are nominally only hazardous to people who have heart pacemakers.” to “ Fields are nominally hazardous to people who only have pacemakers.” | [6 empty] | Done
o 4.2.10.1 Life Safety Egress on page 33 (34/45) “one gate at the magnet drop staging area” please remove “drop”. Fermilab doesn’t drop anything. You can replace with hatch if the author would like. | [6 empty] | Done
o 4.2.11 Environmental These three sections are clearly copy paste. Suggest the phrase match the hazard both in noun and preposition. Such as “Work in Booster…” be replaced with “Operations around Booster…” for soil or “Operations in Booster…” for Air. | [6 empty] | Done
o 4.3.1.1. Missing space between 8Gev on page 35 (36/45) in 1.c | [6 empty] | Done
o 4.4.2.1.1 bottom of page 37 (38/45) Incomplete sentence “ All existing shielding is a credited.” | [6 empty] | Done
o 4.4.2.2.1 Radiation Safety Interlock System on page 38 (39/45) “one gate at the magnet drop staging area” please remove “drop”. Fermilab doesn’t drop anything. You can replace with hatch if the author would like. | [6 empty] | Done
o On page 39 (40/45) please label the image and also the paragraph “ The Booster has a chipmunk detector located at the end of the 400 MeV chute that monitors radiation levels while Booster is open to access. This chipmunk will inhibit Linac beam should an unacceptable level be detected in the Booster.” Is this a Linac credited control/defense in depth then? It should be noted in this chapter which segment this chipmunk is associated with clearly. One could also say the same about the 400 MeV chute. | [6 empty] | Done
o 4.4.3.2 Is there a “ AD ES&H Department”? If not this should be removed or renamed appropriately. | [6 empty] | Done
o 4.4.3.3. Accelerator Operating Parameter On page 41 (42/45) Please remove “For an hour” | [6 empty] | Done
8 GeV SAD
o 5.1.3 Is it 24.5 feet of dirt or e.f.d.? There is some buried steel above the enclosure near the roads. | [6 empty] | Done
o 5.1.4 Location Page 17 (18/39) there is an extra “the” in the text suggested reword “ The 8 GeV Beamline enclosure is located in the southwest of the Booster” | [6 empty] | Done
o 5.1.5 Page 18 (19/39) suggested 2nd sentence rewrite “Since this beamline connects the Booster to the Booster Neutrino Beamline, along with MI/RR, the responsibilities for the operation of the beamline are often shared to optimize the operation of this beamline.”
o 5.2.1.2 Residual Activation (including 7Be) superscript not subscript | [6 empty] | Done
o 5.2.1.4 Surface Water Activation page 23 (24/39) missing a word in the sentence “Activation of the ‘components’ (?) along the rest of the beamline is orders of magnitude lower in comparison.” | [6 empty] | Done
o 5.2.7.2 Compressed gas there is an extra comma between “nitrogen, and argon” | [6 empty] | Done
o 5.2.8.1 For Magnetic Fringe Fields are there not Ion pumps such as those located in Booster? | [6 empty] | This paragraph is correct as written
o 5.2.9.4 Ergonomics Suggested rewrite “ Both office and technical work in service buildings and the 8-GeV Line areas, respectfully, may involve sitting or standing for long periods of time, repetitive motion, cramped conditions, and other ergonomic concerns.” It sounds as if there is office work in an enclosure… | [6 empty] | Done
o 5.3.1 Remove “ which is the Main Injector Segment” confusing | [6 empty] | Done
o 5.3.1.1 page 32 (33/39) suggested rewrite “Conservatively, radioactive doses fall off like 1/r, where r is the distance to the mitigated source.” to “Applying a conservative dose reduction of 1/r, where r is the distance to the mitigated source.” and remove the extra line break after the paragraph. | [6 empty] | Done
o 5.4.1.1.1 Permanent Shielding Including Labyrinths page 32 (33/39) place a space between number and units “500mrem/hr” | [6 empty] | Done
o There is two references/sentences that state the minimum efd which are different numbers. It would be good to have clarity or one number when the sentences say “Topographical surveys of the 8-GeV Line segment enclosures and berm conclude that there is a minimum of 21.6 Equivalent Feet of dirt (e.f.d.) shielding between the interior surface of the enclosure walls and the surface of the berm.” versus “As mentioned above, the 8-GeV Line enclosures have minimum of 24.5 e.f.d.” | [6 empty] | Done
o 5.4.1.2.1 Radiation Safety Interlock System Page 34 (35/39) extra space between B:LAM and power supply. | [6 empty] | Done
o 5.5.1.2 & 5.5.1.3 pages 36 & 37 (pages 37-38/39) through the paragraphs are not “justified” they are aligned left. Please adjust accordingly.
o 5.5.1.2.2 Machine Protection Controls on page 38 (37/39) the TLG acronym is used without reference. Suggest to place it in the reference a few bullet points above.
o 5.5.1.3.2 Procedures page 37 (38/39) There is an Error! Reference source not found. Please correct.
BNB SAD
o Revision History should the most recent revision be at the top?
o 6.1.3 On page 16 (17/50) Beam Pipe doesn’t need to be capitalized. MI should be MI-8 or 8 GeV line.
o 6.1.7 Suggested page break to ensure Table 1 is on one page instead of broken apart.
o 6.2.1.2 Residual Activation Page 22 last paragraph and as prescribed in “the” FRCM
o 6.2.1.6 Air Activation Page 28 (29/50) MUX is used without an acronym listing.
o 6.2.1.8 Soil Activation Page 29 (30/50) I am unsure how PPE limits body exposure to activated material and contamination via soil activation? This maybe better suited for contamination 6.2.1.10 or radioactive waste 6.2.1.9
o 6.2.1.11 Beryllium-7 Page 31 (32/50) Has conflicting messages between the paragraph and sentence. Should clean this up with a single message.
o 6.2.3 Flammables and Combustibles Page 33 (34/50) suggested rewrite “BNB has combustible hazards in the form of combustible materials. It does not have flammable hazards or materials.“
o 6.2.11 Environmental page 37 (38/50) These three sections are clearly copy paste. Suggest the phrase match the hazard both in noun and preposition. Such as “Work in BnB…” be replaced with “Operations at BNB…” for soil or “Operations for BnB…” for Air.
o 6.4.1.2.1 Radiation Safety Interlock System On page 42 (43/50), the phrase “Shielding is adequate to limit potential MCI radiation doses…except…”. Please use the word Passive shielding, so there is no mistake.
o 6.5 Summary of Defense in Depth Controls Please use Page breaks to get the tables on their own page and not break them up
MI/RR SAD
o On page 1 (2/43) SAD Chapter Review there are some odd lines on the document signage areas… | [6 empty] | Done
o Revision History should the most recent revision be at the top? | [6 empty] | Done
o Extra line break between 7.1.3 and 7.1.4 | [6 empty] | Doen
o 7.1.4 the text should be “justify” with consistent line spacing in the paragraph.
o 7.2.1 Radiological Hazards page 18 (19/43) What is an Orc gate? | [6 empty] | Paragraph is correct as written
o 7.2.1.3 Groundwater Activation 1st paragraph is conflicting phrases. Please make this more clear. | [6 empty] | Done
o 7.2.1.4 Surface Water Activation 1st paragraph is conflicting phrases. Please make this more clear. | [6 empty] | Done
o 7.2.1.11 Beryllium 7 page 23 (24/43) the 7 in 7Be should be superscript. | [6 empty] | Done
o 7.4.1.1.2 Movable Shielding page 32 (33/43) is it the P1 (A1) or P(A)150 line? | [6 empty] | Done
o 7.4.1.1.3 Penetration Shielding Suggest to modify the tables page 32 through 36 (33 through 37/43) to get them onto whole/single pages. Looks like the tables can be wider and shorter.
o 7.4.2 Sections there are a few extra line breaks in the document | [6 empty] | Done
o 7.4.2.3 Accelerator Operating Parameters page 38 (39/43) looks to have different font | [6 empty] | Done
o 7.5.1.2 Active Defense-in-Depth Engineering Controls Table 3 looks to have bold Chipmunks in the table | [6 empty] | Done
o 7.5.1.2.1 Machine Protection Controls Page 40 (39/43) please use units at the end of the 1st paragraph. | [6 empty] | Done
o I highly suggest to remove the “bolding” of the last bullet point. “Limits the accident incident…” | [6 empty] | Done
o 7.5.1.3.1 Training page 40 41/43) has an extra space 1st paragraph | [6 empty] | Done
NuMI SAD
o On page 2 (3/44) SAD Chapter Review it’s the External Beam Delivery Department not Beams
o 8.1.4 Location Should state ” The NuMI segment is located on the Fermilab site in Batavia, IL.”
o 8.1.6 Operating Modes Page 20 (21/44) doesn’t need MI protons.
o 8.2.1.6 Air Activation page 24 (25/43) There is an Error! Reference source not found. Please correct.
o 8.2.3.2 Flammable Materials page 28 (29/43) Is the dilution with Argon (Ar) or Air?
o 8.2.10 Access & Egress page 32 (33/44) the two sentences “Access is controlled by various key systems. The building is restricted.” Should have more details. Such as “Access in areas and buildings are restricted and controlled by various key systems.”
o 8.2.11.3 Hazard to Soil is N/A. page 34 (35/44) I highly doubt that for the beamline in the upstream section. I could be wrong though.
o 8.3.1.1 Radiological Hazard page 34 (35/44) the 1st paragraph should be “justify” not align left.
o 8.4.1 Credited Engineered Controls on page 35 (36/45) there is a copy paste error “III-8.1.1.1” in there
o 8.4.1.1.1 Permanent Shielding Including Labyrinths on page 36 there is a paragraph that says “Clarifying the “to MI-8 tunnel” entry as there was no previous discussion of this, the NuMI beamline passes under the MI-8 beamline. This is the transverse shielding from the NuMI enclosure to the MI-8 enclosure.” I believe the beam is no longer primary and its secondary particles along with if a facility worker or co-located worker is in the MI-8 tunnel there is no need to include this as a hazard given that worker (and collocated worker) is standing in the source of beam for NuMI. I find this paragraph and subsequent entry in Table 3 very confusing.
o 8.4.1.1.3 Penetration Shielding page 38 (39/44) should have a little more text in the paragraph such as “ …must be in place for beam operations”
o 8.4.1.2.1 Radiation Safety Interlock System page 39 (40/44) the chipmunk trip setting is set for 5 rem/hr as shown in Table 5. It is wise to reduce this number to protect for CFR 835 purposes or at least get away from the 420.2D limit.
o 8.4.2 Credited Administrative Controls page 40 (41/44) has the word “impact” twice in the opening paragraph. This seems redundant and rewording is suggested. “All NuMI Beam Line operations with potential to impact the safety of employees, researchers, or members of the public or to adversely impact to the environment are performed using approved laboratory, division or department procedures.”
o Page 42 (43/44) seems to have an extra page break, up to the author to remove or keep.

## PreStart Status for FSO
IRR 1b Report Recommentdations
Type | Document/Topic | Number |  | Recommendation | Assigned to | Resolution
Recommendation | Credited Controls | Pre-Start #1 | Pre-Start | Label all Credited Contorls in the tunnels and work areas prior to beginning operations | Maddie/Jeremy + Help
|  |  |  | - Booster | Salah | complete
|  |  |  | - 8 GeV | Marty | will be complete pre-start (post-ASE signing)
|  |  |  | - BNB | Jason | complete
|  |  |  | - MI/RR | Marty | will be complete pre-start (post-ASE signing)
|  |  |  | - NuMI | Phil | complete
Recommendations | ASE | Pre-Start #2 | Pre-Start | Ensure that the ASE Accelerator Operating Pramater Credited Control value(s) accurately reflect the MCI analysis summarized in the SAD
|  |  |  | - Booster | Salah | complete
|  |  |  | - 8 GeV | Marty | complete
|  |  |  | - BNB | Jason | complete
|  |  |  | - MI/RR | Marty | complete
|  |  |  | - NuMI | Phil | complete
Recommendation | MCI | Pre-Start #3 | Pre-Start | Complete MCI analysis for each segment prior to beginning operations
|  |  |  | - Booster | Lionel | complete
|  |  |  | - 8 GeV | Marty | complete
|  |  |  | - BNB | Jason | complete
|  |  |  | - MI/RR | Marty | complete
|  |  |  | - NuMI | Phil | complete