## Slide 1: Main Injector Reconfiguration (During Civil Construction)
Rework for LBNF Extraction Channel Installation

## Slide 2: ISO View of Main Injector and Primary Beamline Enclosure
Dipole
Magnets
Target
Complex
(LBNF-20)
Primary Beam Service Building
(LBNF-5)
Primary
Beamline
Enclosure
Major
Vehicle
Access
Fermilab
Main Injector
Tunnel
Extraction
Enclosure
Egress
MI-10 Alcove

## Slide 3: Main Injector Rework
Current Configuration
(pending Construction onset)
After Construction
Construction Barriers
Q-104
Q-104

## Slide 4: Main Injector With Extraction Channel

## Slide 5: Preparing The Main Injector Tunnel For Component Removal
What magnets are being removed:
  MI from Q631- Q108 (8Q’s & 6 D’s)
  RR from Q104- Q108 (8 magnets)
What devices are being relocated or removed (R):
  MI 8 Gev Injection Lambertson (R)
  MI Injection kickers (R)
  SQA852 Quad (R)
  LCW Headers and Secondary Manifolds
  Main Injector Bus
  Multiwire
  IPMS
  SEY experiment
Schedule:
  Removal: Jan ‘27 –Mar ‘27
  Civil Tie in: Mar’27 – May ‘28
  Reinstall: May ‘28 – Dec ‘28
Cables:
  Back Pull: ~215 cable ~ 32K ft
  New installation: 400-500 cables ~200k ft
  Cable tray will be left in place during construction work.

## Slide 6: Main Injector/Extraction enclosure
MI Beam Direction

## Slide 8: Elevation View Showing Beam Pipe Through MI Wall
1’x1’ Rectangular Pipe

## Slide 9: Geotechnical
Extraction Enclosure excavation and support of existing MI-14