## Slide 1
FD1 Status & Plans
Eric James
FD1 Technical Board Meeting
February 14, 2024

## Slide 2: Big Picture
2024 promises to be another busy year
Commission and operate ProtoDUNE-II detector in NP04
Ramp-up APA production and cold-test 4-6 modules in NP04 cold box.
Conduct Production Readiness Reviews and initiate production of remaining FD1 components

## Slide 3: ProtoDUNE-II (NP04)
NP04 cryostat is sealed
Filippo will give a short update on current status
Ramp-up to operations over next two months
Anticipating appointment of ProtoDUNE Run Coordinator at today’s DUNE Executive Board Meeting (posted file describes responsibilities)

## Slide 4: APA Production
Anticipate approval of new management structure at today’s Executive Board Meeting
The lead engineers and scientists at the factories will form an APA Production Board to manage the module construction activities
APA consortium will continue to have responsibility for post-construction activities (APA testing at CERN, APA reception at Fermilab/Ash River, and APA installation at SURF) as well as for producing the deliverables associated with these activities

## Slide 5: APA Production (Current Status)
Expect four winders to be operational at Daresbury within the next week or so
Chicago has successfully completed the winding of the x-layer on their first APA
Daresbury has identified sixteen suitable technician candidates and is currently in the process of onboarding them
Still working to understand the cause of two wire breakages on one of the two APAs currently under construction at Daresbury

## Slide 6: Upcoming LBNC/NSG Meetings
LBNC Meeting: Feb 26-28
NSG Meeting: Mar 27-28
Far Detectors are not the focus of either of these meetings
Technical Coordinators will be asked to give short (20-30 minute) status updates on FD1 and FD2 at both meetings
Request 2-3 slides from each consortium summarizing progress over last 6-12 months

## Slide 7: Production Readiness Reviews
Need to push forward with these on short time scale to ensure that construction activities can be started on schedule
More information about this topic in subsequent presentation