## Slide 1: Muon Campus Operation Report
Jim Morgan
Friday 09:00 Operations Meeting
February 9, 2024

## Slide 2: Muon Campus status
KPS5A PFL Repair
Intentional Accelerator
Standby Period
MC-1 Controlled Access
Study – Alternative M5 optics
G-2 Trolley Run
<------------Week Days -------------------
Study – M1-M3 Optics
Working on recommendations from SAD/ASE Review
  ARR scheduled for Next month
ESS1 Electrostatic Septum at A0 Clean Room
  Metal objects found in septum were 86% Aluminum and 13% silver
  Threaded holes in aluminum frame show clear signs of galling
Preparations for Electrostatic Septa installation
  Mechanical techs installed new compact vacuum pipe in Q203
Waiting to remove blocks from D40 Hatch for incoming and outgoing magnets
  8Q24 with rad hardened water lines at AP-50, ready to be lowered into tunnel
  Forklift and rad hard 8Q24 will be lowered into tunnel for installation
  Existing 8Q24 and four NSA sextupoles that had water leaks go to TD
Investigating source of chronic D50 ceiling tunnel ceiling leak
  ICW valved out to AP-50 as a test, tunnel leak remained the same

## Slide 3: Q206 rad hard water line modifications
Q206 modified rad-hard manifold
Q301 standard rad-hard manifold
Notch where M4 Line pipe goes

## Slide 4: D50 tunnel ceiling leak
Domestic water lines
Location of ceiling leak
Chilled water lines
Industrial Cold Water Lines
Ring Enclosure
NuMI

## Slide 5: Examples of metal galling compared with ESS1 pieces
From Wikipedia entry on galling
Caused by adhesion of contacting surfaces
Metal pieces found in ESS1

## Slide 6: Galled threads in aluminum frame of ESS1 and fastener

## Slide 7: ESS1 end view, location of galled threads in frame

## Slide 8: Upcoming work
ESS1 component replacement and assembly will continue at the A0 Clean Room
  Could optimistically be ready for tunnel installation in mid-March (end of February in last week’s report)
  Installation, leak-check and vacuum pump-down would follow
  If delayed, vacuum spool will be installed in Delivery Ring
ARR Preparations
Q205 magnet swap and special vacuum pipe replacement
  Waiting on parts to be machined for Q205 vacuum pipe
  Opening of D40 Hatch has been delayed until parts are in hand
Q203 location ready to for ESS1 installation
  Still some missing stand parts that should arrive soon
D50 tunnel water leak continues unabated
  Valving out CW and ICW to AP-50 didn’t reduce leak or sump activity
  No longer need ICW valved out for test, considering next move