## Slide 1
Dean (Chip) Edstrom
02/09/2024
IOTA Proton Injector Update

## Slide 2: Points of Contact
There are lots of activities with more than one (valid & incompatible) opinions on how things should be done…
Overall Cable Pull – Chip Edstrom
  Questions on cable list/labels/types/destinations/problems
  Relying upon Jamie primarily as Electrician/contract liaison
Overall Beamline Component Installation – Sasha Romanov
  Questions on beamline stand/components
Overall Support Department Liaison – Jinhao Ruan
  Questions on support for Mechanical/Electrical/RF
Overall Commissioning – Chip Edstrom
  RGD Registration, ORC, etc…
  Source Commissioning / Characterization

## Slide 3: Electrical Status
Cable Pull Nearly Complete…
    T&M update: WebReq 55913
    RG58 / Safety / Fiber pulls remain
    120 / 208 VAC beamline power
    Routing cables along beamline
      ¼” Heliax & CAT5/6 (✔)
      8-Pair (✔)
      10-Cond & Motors
    Safety Panel Installation (✔)
    Lydon is back starting yesterday…
      Please limit interactions
HLRF 600A Disconnect: Incorrect Kirk Key

## Slide 4: Commissioning Status
ORC Review for Full Source Operation
  Source Ready™ for Operation, but…
    HV Power Supply failure
    Filament supply scaling questions
  RGD Registration
    Still waiting on FSO approval
    Hydrogen iTrack issue resolved
  ES&H Monitoring Plan
    RCT presence for initial turn-on / for any increase in max voltage
    Passive monitoring (badges in-place)

## Slide 5: Next Steps
Beamline Component Installation (Dave Franck / Sasha R)
  RFQ Placement (✔) / Anchoring (✔) / Alignment
  LEBT Stand Placement (✔) / Anchoring (✔)
  Quadrupole Installation (✔) / Rough Alignment (✔)
  Multifunction Magnets Installation (✔) / Rough Alignment
  MEBT Allison Scanner & Other beamline components
Cable Routing / Termination
  500MCM into a box to be mounted to the cable tray (Daniel)
  8-Pair Magnet (✔) / Turbo Breakouts (✔) (Chip)
  Heliax (✔) (Brian Fellenz / Bogie) in progress
    BPMs (will need to be phase-matched)
  1 5/8” Buncher RF Heliax (✔)
  6” RFQ Waveguide Installation (Rick & FAST Ops) in progress
Dress / Fill Penetration

## Slide 6: 6” RFQ Waveguide
  Progress!

## Slide 7: Support Departments
EE Support
  CDC Contactor Progress…
RF Support
  Ding Sun
Mechanical Support
  Steve Wesseln… Currently working on PIP2
Instrumentation
  Bogie / Brian to assist with Heliax terminations, etc
  Brian Felenz assisting with racktops / signal manifolds / pigtails
  HLRF Fast Interlocks VME (Niral Patel / Steve Roccos)
Controls
  EPICS integration (Pierrick Hanlet)