## Slide 1
Marty Murphy
23 February 2024
0900 AD Scheduling Meeting

## Slide 2: Last Week This Week
Last Friday – Work planning for two jobs in MI and RR was on-going.
PESD verified the MI sextupole magnets can run air-cooled at operational RMS currents and 1.067 second duty cycle period. (this is over a week old, but I forgot to include it previously)
This week:
  Mostly in standby
  PESD and MSD worked to replace degraded cable for R:IP3180. This required a cable pull through the 30-straight section (near the HRA). The job was successful.
  Instrumentation repaired two broken multiwires in the MI8 line (814 and 840).
  F-Sector Magnet leak repair completed and the F-sector LCW system was returned to service Thursday afternoon.
  Ops searched and secured the MI on Wednesday evening. The machines are in stand-by.
  Working with ISD to replace damaged 60 HP pond pump wires between the MI40 MCC and the MI40 pond pump vault.

## Slide 3: Current Status
MI in controlled access.
Plan for Friday & Next Week
Submit paperwork to DOE for final authorization to operate early next week.
Switch on KRSS once folks are out of F-Sector.
Test P1, P2 and NuMI power supplies that have not yet been energized.
PESD swapped the horizontal sextupole power supply with the spare unit. SEXHPS needs to be energized.
Energize MI and RR longitudinal and transverse damper systems (MI and RF); this will happen next early week.