## Slide 1
Marty Murphy
01 March 2024
0900 AD Scheduling Meeting

## Slide 2: Last Week This Week
Last Friday: Controlled access wrapped, and Ops switched on at KRSS.
This week:
  Monday: MI/RR in standby.
  Tuesday ISD replaced a dead sump pump at 823B.
    PESD studies and measurements were done with mixed success.
    MI ramp was held off due to Fast Bypass Loop issues but, was fixed by end of the day.
    PESD identified an open load on the QT306 WA quad trim; needs access for further diagnosis. WPC in progress.
  Wednesday: Ops established MI, NuMI and P1-Line beamline PS ramps. MI30 mixing valve stopped regulating and was set manually to accommodate cooling.
  Thursday: Ramped MI, upstream NuMI power supplies for PESD.
    MI30 mixing valve was repaired; this required about 90 minutes of MI not ramping.
  Friday: MI & upstream NuMI supplies ramping. PESD measuring temp of new LAM61 cables.

## Slide 3: Current Status
MI on & ramping.
Plan for Friday & Next Week
Submit paperwork to DOE for final authorization to operate.
Turn off MI pond cooling and LCW pumps for ISD to pull new wires for 60 HP pump at MI40 – estimate 7-10 days. Likely start of Tuesday or Wednesday. This will turn of MI LCW.
Access MI to address QT306 open load indication.
Install Credited Control sticker/signage around the MI & 8-GeV.