## list_wt_names
https://edms.cern.ch/document/3067377
designer/engineer
engineering item | Pre-Swap "Submit PO" | Pre-Swap "need by" | Prelim. Need By | Supervisor | Engineer | Engineer Start work | priority | Comments
cold boxes | 2024-06-26 | 2024-07-01 | 2025-10-01 | Jack Fowler Marzio Nessi | Justin Freitag | 2023-03-01
SST Structure |  |  | 2024-07-01 | Dominique Duschesneau Olga Beltramello Marzio Nessi | Gianluigi Buccino Nick Joniak | 2023-12-01
CERN test steel structure |  |  | 2024-07-01 | Filippo Resnati | Nick Joniak | 2024-02-01
L beam insertion tool (airpads, support etc.) |  |  | 2024-06-01 | Olga Beltramello | Sanmitra Pingulkar Denis Diyakov | 2024-03-01
beam connections to cranes (beam rigging tooling) |  |  | 2024-04-01 | Syd Devries Marzio Nessi, Dimitar Mdladenov | Denis Diyakov | 2024-03-01
cold box pedestal |  |  | 2025-10-01 | Marzio Nessi, Justin Fritag | Saruultugs Batzorig | 2024-03-01
detector mezzanines |  |  | 2025-10-01 | Jack Fowler Marzio Nessi | Olga Beltramello Gianluigi Buccino Sanmitra Pingulkar | 2024-03-01
cryo mezzanines |  |  | 2026-02-01 | Jack Fowler Marzio Nessi | Olga Beltramello Gianluigi Buccino Sanmitra Pingulkar | 2024-03-01
Cryostat roof penetration new design proposal | 2024-10-14 | 2026-01-07 | 2025-07-01 | Marzio Nessi Louis Miralis Dimitar Mladenov | Dimitar Mladenov Louis Miralis Benoit Lacarelle | 2024-03-01
FD2 TCO access platform |  |  | 2024-12-01 | Olga Beltramello Jim Stewart | Saruultugs Batzorig Nick Joniak | 2024-04-01
FD2 wall cable trays |  |  | 2024-09-01 | Manhong Zhao Marzio nessi | Nick Joniak | 2024-04-01
FD1 permanent stairs |  |  | 2026-05-01 | Jack Fowler | Justin Freitag | 2024-05-01
FD2 permanent stairs |  |  | 2025-10-01 | Jack Fowler | Justin Freitag | 2024-05-01
FD1 access to cryostat - ladders etc | 2024-08-28 | 2025-06-24 | 2026-11-01 | Jim Stewart Marzio Nessi | Justin Freitag | 2024-05-01
FD2 access to cryostat - ladders etc | 2025-04-20 | 2026-04-15 | 2026-04-01 | Jim Stewart Marzio Nessi | Justin Freitag | 2024-05-01
Condensation prevention piping |  |  | 2025-02-01 | Marzio Nessi Filippo Resnati David Montanari | Adrian Parchet | 2024-07-01
Cryostat floor thermometry |  |  | 2025-02-01 | Marzio Nessi, Filippo Resnati David Montanari | Adrian Parchet | 2024-07-01
Machine Shop |  |  | 2025-02-01 | Bill Miller Jim Stewart | Justin Freitag | 2024-07-01
Laser level and 3 direction laser |  |  | 2025-02-01 | Jack Fowler Marzio Nessi | Mike Gemelli | 2024-07-01
Torque testing tool |  |  | 2025-02-01 | Mike Gemelli Marzio Nessi | Mike Gemelli | 2024-07-01
Lunch room |  |  | 2025-02-01 | Mike Pfaff | Bill Miller Jim Stewart | 2024-07-01
Temporary WIFI in cavern |  |  | 2025-02-01 | Marzio Nessi BSI | FNAL network | 2024-07-01
FD2 emergency exit path |  |  | 2025-02-01 | Jack Fowler Olga Beltramello | Jim Niehof | 2024-07-01
Cavern card readers and underground access |  |  | 2025-02-01 | Marzio Nessi BSI | BSI | 2024-07-01
Safety Signage including eggress |  |  | 2025-02-01 | Jack Fowler Olga Beltramello | Jim Niehof | 2024-07-01
Self rescuer cache top of cryostat |  |  | 2025-02-01 | Bill Miller Jim Stewart | Kyle Janford Jim Niehof | 2024-07-01
N-Cavern main bridge |  |  | 2026-06-01 | Olga Beltramello Jim Stewart Marzio Nessi | Justin Fritag Gianluigi Buccino Saruultugs Batzorig | 2024-08-01
Ground Monitor |  |  | 2025-01-01 | Terri Shaw | Linda Bagby | 2024-08-01
FD2 clean room (includes changing room) | 2025-11-04 | 2026-10-30 | 2026-04-01 | Bill Miller Jim Stewart | Nick Joniak | 2024-09-01
Leak testing |  |  | 2025-05-01 | Jim Stewart Filippo Resnati | Jim Stewart Filippo Resnati | 2024-10-01
Temporary power carts |  |  | 2025-02-01 | Jack Fowler | Mike Gemelli | 2024-10-01
Air compressors |  |  | 2025-02-01 | Mike Pfaff Filippo Resnati | Mike Pfaff Filippo Resnati | 2024-10-01
TCO beam FD2 | 2025-11-04 | 2026-10-30 | 2025-07-01 | Jim Stewart Bill Miller | Nick Joniak | 2024-11-01
FD1 clean room (not including roof + towers) | 2025-04-13 | 2026-04-08 | 2026-10-01 | Bill Miller Jim Stewart | Justin Freitag | 2024-12-01
FD1 TCO access platform |  |  | 2025-09-01 | Jack Fowler | Justin Freitag | 2024-12-01
FD2 DAQ Barracks structure |  |  | 2026-02-01 | Jack Fowler | Sanmitra Pingulkar | 2024-12-01
FD2 DAQ Barracks HVAC |  |  | 2026-02-01 | Jack Fowler | Sanmitra Pingulkar | 2024-12-01
Networking |  |  | 2026-05-01 | Jack Fowler | FNAL network | 2025-01-01
FD1 emergency exit path |  |  | 2025-08-01 | Jack Fowler Olga Beltramello | Jim Niehof | 2025-01-01
FD1/2 Electroncis Racks |  |  | 2025-12-01 | Jack Fowler | Terri Shaw Linda Bagby | 2025-02-01
FD2 DAQ Barracks fire suppression |  |  | 2026-05-01 | Marzio Nessi | Jim Niehof | 2025-03-01
UPS CUC |  |  | 2026-05-01 | Terri Shaw | New Lead EE | 2025-03-01
UPS Surface |  |  | 2026-05-01 | Terri Shaw | New Lead EE | 2025-03-01
Power CUC to S-Cavern |  |  | 2026-05-01 | Terri Shaw | New Lead EE | 2025-03-01
Power Barracks to det mezzanine |  |  | 2026-05-01 | Terri Shaw | New Lead EE | 2025-03-01
FD1 Cleanroom Bridge Crane | 2025-01-03 | 2026-01-28 | 2026-07-01 | Jack Fowler | Justin Freitag | 2025-03-01
FD1/2 DUNE Detector safety system |  |  | 2026-05-01 | Marzio Nessi Camillo Mariani | Camillo Mariani | 2025-03-01
FD1 top of the cryostat floor and hand rails | 2024-08-28 | 2025-06-24 | 2026-03-01 | Jack Fowler | Justin Freitag Kyle Janford | 2025-04-01
FD2 top of the cryostat floor and hand rails | 2025-04-20 | 2026-04-15 | 2026-03-01 | Jack Fowler | Justin Freitag Kyle Janford | 2025-04-01
FD1 cold cryostat protection floor |  |  | 2027-02-01 | Marzio Nessi Jim Stewart | Nick Joniak | 2025-05-01
FD2 cold cryostat protection floor |  |  | 2026-07-01 | Marzio Nessi Jim Stewart | Nick Joniak | 2025-05-01
FD1 Cleanroom Roof steel |  |  | 2026-10-01 | Olga Beltramello Bill Miller | Justin Freitag Saruultugs Batzorig | 2025-05-01
FD1 APA towers |  |  | 2026-10-01 | Jim Stewart | Kyle Zeug Saruultugs Batzorig | 2025-05-01
FD1/2 Ar purge lines |  |  | 2026-03-01 | Jim Stewart | Justin Freitag | 2025-05-01
FD1 and FD2 Cryostat roof cable trays |  |  | 2025-12-01 | Jim Stewart | Justin Freitag | 2025-06-01
Temporary TCO beam FD1 |  |  | 2026-03-01 | Jack Fowler | Nick Joniak | 2025-10-01
FD1 DSS |  |  | 2027-02-01 | Marzio Nessi Jack Fowler | Sanmitra Pingulkar | 2025-10-01
Cathode installation work platform |  |  | 2026-11-01 | Bill Miller Jim Stewart | Nick Joniak | 2026-01-01
Cold Box N2 system |  |  | 2027-02-01 | David Montanari | cryo team | 2025-10-01
AHU cryostat |  |  |  | Bill Miller | Justin Freitag
Cryostat roof railing beam clamps. |  |  |  | ? | ?
|  |  |  | 1 | Jack Fowler
|  |  |  | 2 | Sanmitra Pingulkar
|  |  |  | 3 | Nick Joniak
|  |  |  | 4 | Manhong Zhao
|  |  |  | 5 | Kyle Zeug
|  |  |  | 6 | Kyle Janford
|  |  |  | 7 | Charles Maupin
|  |  |  | 8 | Gianluigi Buccino
|  |  |  | 9 | Denis Diyakov
|  |  |  | 10 | Saruultugs Batzorig
|  |  |  | 11 | Adrian Parchet
|  |  |  | 12 | Benoit Lacarelle
|  |  |  | 13 | Rich Ruggerio
|  |  |  | 14 | John Scheblein
|  |  |  | 15 | New Lead EE
|  |  |  | 16 | Linda Bagby
|  |  |  | 17 | Terri Shaw
|  |  |  | 18 | Olga Beltramello
|  |  |  | 19 | Bill Miller
|  |  |  | 20 | Jim Stewart
|  |  |  | 21 | Marzio Nessi
|  |  |  | 22 | James Devinne
|  |  |  | 23 | Dimitar Mladenov
|  |  |  | 24 | Louis Miralis
|  |  |  | 25 | Alex Robin
|  |  |  | 26 | Syd Devries
|  |  |  | 27 | Justin Freitag
|  |  |  | 28 | Filippo Resnati
|  |  |  | 29 | Mike Pfaff
|  |  |  | 30 | David Montanari
|  |  |  | 31 | Mike Gemelli
|  |  |  | 32 | Camillo Mariani

## Sheet1
designer/engineer
engineering item | Pre-Swap "Submit PO" | Pre-Swap "need by" |  | Prelim. Need By | Supervisor | Engineer | Engineer Start work | priority | Comments
L beam insertion tool (airpads, support etc.) |  |  |  | 2024-06-01 | 18 | 2,9 | 2024-03-26
beam connections to cranes (beam rigging tooling) |  |  |  | 2024-04-01 | 26 | 3,9 | 2024-03-26
cold boxes | 2024-06-26 | 2024-07-01 |  | 2025-10-01 | 1,21 | 27 | 2024-03-26 |  | restart planning for this, now very urgent
cold box pedestal |  |  |  | 2025-10-01 | 27 | 10 | 2024-03-26 |  | Justin can feed the requirements to Saruultug
detector mezzzzanines |  |  |  | 2025-10-01 | 1,21 | 18,8,2 | 2024-03-26
cryo mezzanines |  |  |  | 2026-02-01 | 1,21 | 18,8,2 | 2024-03-26
Cryostat roof penetration new design proposal | 2024-10-14 | 2026-01-07 |  | 2025-07-01 | 21,24,23 | 23,24,12 | 2024-03-26 |  | rework eng. with CERN
N-Cavern main bridge |  |  |  | 2026-06-01 | 20,21 | 18,8 | 2024-08-01
FD1 permanent stairs |  |  |  | 2026-05-01 | 1 | 27 | 2024-05-01
FD2 permanent stairs |  |  |  | 2025-10-01 | 1 | 27 | 2024-05-01
FD1 access to cryostat - ladders etc | 2024-08-28 | 2025-06-24 |  | 2026-11-01 | 20,21 | 27 | 2024-05-01
FD2 access to cryostat - ladders etc | 2025-04-20 | 2026-04-15 |  | 2026-04-01 | 20,21 | 27 | 2024-05-01
FD1 clean room (not including roof + towers) | 2025-04-13 | 2026-04-08 |  | 2026-10-01 | 19,20 | 27 | 2024-12-01
FD2 clean room (includes changing room) | 2025-11-04 | 2026-10-30 |  | 2026-04-01 | 19,20 | 3 | 2024-09-01
Temporary TCO beam FD1 |  |  | Part of DSS | 2026-03-01 | 1 | 3 | 2025-10-01
TCO beam FD2 | 2025-11-04 | 2026-10-30 | Part of cleanroom | 2025-07-01 | 19 | 3 | 2024-11-01
FD1 TCO access platform |  |  |  | 2025-09-01 | 1 | 27 | 2024-12-01
FD2 TCO access platform |  |  |  | 2024-12-01 | 18,20 | 10,3 | 2024-04-01
FD1 cold cryostat protection floor |  |  |  | 2027-02-01 | 21,20 | 3 | 2025-05-01
FD2 cold cryostat protection floor |  |  |  | 2026-07-01 | 21,20 | 3 | 2025-05-01
FD1 top of the cryostat floor and hand rails | 2024-08-28 | 2025-06-24 |  | 2026-03-01 | 1 | 27,6 | 2025-04-01
FD2 top of the cryostat floor and hand rails | 2025-04-20 | 2026-04-15 |  | 2026-03-01 | 1 | 27,6 | 2025-04-01
FD1 Cleanroom Roof steel |  |  |  | 2026-10-01 | 18,19 | 27,10 | 2025-05-01
FD1 APA towers |  |  |  | 2026-10-01 | 20 | 5,10 | 2025-05-01
FD2 wall cable trays |  |  |  | 2024-09-01 | 4 | 3 | 2024-04-01
FD2 DAQ Barracks structure |  |  |  | 2026-02-01 | 1 | 2 | 2024-12-01
FD2 DAQ Barracks HVAC |  |  |  | 2026-02-01 | 1 | 2 | 2024-12-01
FD2 DAQ Barracks fire suppression |  |  |  | 2026-05-01 | 21 | ? | 2025-03-01 |  | to be clarified
UPS CUC |  |  |  | 2026-05-01 | 17 | 15 | 2025-03-01 |  | to be clarified
UPS Surface |  |  |  | 2026-05-01 | 17 | 15 | 2025-03-01 |  | to be clarified
Power CUC to S-Cavern |  |  |  | 2026-05-01 | 17 | 15 | 2025-03-01 |  | to be clarified
Power Barracks to det mezzanine |  |  |  | 2026-05-01 | 17 | 15 | 2025-03-01 |  | to be clarified
Ground Monitor |  |  |  | 2025-01-01 | 17 | 16 | 2024-08-01
FD1 Cleanroom Bridge Crane | 2025-01-03 | 2026-01-28 |  | 2026-07-01 | 1 | 27 | 2025-03-01
Cold Box N2 system | [8 empty] | to be clarified with D. Montanari
FD1 DSS |  |  |  | 2027-02-01 | 20,21,1 | 2 | 2025-10-01
CERN test steel structure |  |  |  | 2024-07-01 | 28 | 3 | 2024-02-01
SST Structure |  |  |  | 2024-07-01 | 21 | 8,3,18 | 2023-12-01
Cathode installation work platform |  |  |  | 2026-11-01 | 19,20 | 3 | 2026-01-01
AHU cryostat |  |  |  |  | 19 | 27
Condensation prevention piping |  |  |  | 2025-02-01 | 21,28,30 | 11 | 2024-07-01
Cryostat floor thermometry |  |  |  | 2025-02-01 | 21,28,30 | 11 | 2024-07-01
Machine Shop |  |  |  | 2025-02-01 | 19,20 | 27 | 2024-07-01 |  | need a relook at the layout
Leak testing |  |  |  | 2025-05-01 | 20,28 | 20,28 | 2024-10-01
Laser level and 3 direction |  |  |  | 2025-02-01 | 1,21 | 31 | 2024-07-01
Torque testing tool |  |  |  | 2025-02-01 | 31,21 | 31 | 2024-07-01
Temporary power carts |  |  |  | 2025-02-01 | 1 | 31 | 2024-10-01
Air compressors |  |  |  | 2025-02-01 | 29,28 | 29,28 | 2024-10-01
FD1 and FD2 Cryostat roof cable trays |  |  |  | 2025-12-01 | 20 | 27 | 2025-06-01
FD1/2 Electroncis Racks |  |  |  | 2025-12-01 | 1 | 17,16 | 2025-02-01
FD1/2 DUNE Detector safety system |  |  |  | 2026-05-01 | 21, 32 | 32 | 2025-03-01
FD1/2 Ar purge lines |  |  |  | 2026-03-01 | 20 | 27 | 2025-05-01
Lunch room |  |  |  | 2025-02-01 | 29 | 19,20 | 2024-07-01
Temporary WIFI in cavern |  |  |  | 2025-02-01 | 21 | TBD | 2024-07-01 |  | Marzio discuss with BSI
Networking |  |  |  | 2026-05-01 | 1 | TBD | 2025-01-01 |  | Jolie can identify who this is. Jolie has communicated with FNAL ITD
FD1 emergency exit path |  |  |  | 2025-08-01 | 1,18 | 29 | 2025-01-01 |  | ESH group
FD2 emergency exit path |  |  |  | 2025-02-01 | 1,18 | 29 | 2024-07-01 |  | ESH group
Cavern card readers and underground access |  |  |  | 2025-02-01 | 21 | 29 | 2024-07-01 |  | with BSI
Safety Signage including eggress |  |  |  | 2025-02-01 | 1,18 | 29 | 2024-07-01 |  | ESH group
Self rescuer cache top of cryostat |  |  |  | 2025-02-01 | 19,20 | 6 | 2024-07-01 |  | ESH group
Jack Fowler
Sanmitra Pingulkar
Nick Joniak
Manhong Zhao
Kyle Zeug
Kyle Janford
Charles Maupin
Gianluigi Buccino
Denis Diyakov
Saruultugs Batzorig
Adrian Parchet
Benoit Lacarelle
Rich Ruggerio
John Scheblein
New Lead EE
Linda Bagby
Terri Shaw
Olga Beltramello
Bill Miller
Jim Stewart
Marzio Nessi
James Devinne
Dimitar Mladenov
Louis Miralis
Alex Robin
Syd Devries
Justin Freitag
Filippo Resnati
Mike Pfaff
David Montanari
Mike Gemelli
Camillo Mariani