## Sheet1
SURF engineering meeting | week 16
day | M 15 | T 16 | W 17 | Th 18 | F 19
6:30 to 8:00 |  |  | visit underground
8:00 to 10:00 | material logistics executive summary + property transfer | cryo mezzanine + second floor | L-beam sled | FD2 instllation CERN tests | cryostat material lowering, shaft occupancy
10 :00 to 12:00 | detector mezzanine + inst | cryo mezzanine installation | Cryostat lowering tests | FD2 instllation CERN tests | Summary, work assignments
13 :00 to 15:00 | cold box | stairs + connecting platforms | Cryostat decking and railing | cryostat internal protection floor + internal cable trays | mech. Workshop material and layout
15 :00 to 17:00 | cold box assembly | external ladders / protego protection | TCO access structure, TCO beam FD1 and FD2 | pipes below cryostat floor, Cryo Penetrations
18:00 to 21:00 |  |  |  | common dinner
content for each item | requirements
structural engineering
compliance verification
3d models
2d production drawings
technical spec
installation procedure