## Slide 1
Kyle J. Hazelwood
PMG Meeting
2024-04-04
MI8 Beam Position Monitor AIP Update

## Slide 2: Introduction
2
Kyle J. Hazelwood | MI8 BPM AIP | PMG Meeting
The AIP will replace the electronics (crates, digitizers, etc) for the 8 GeV and BNB beamlines
AIP funding is $5M
Started Q2 FY24, ends Q3 FY27
Most R+D done for the PIP-II BPM system, the AIP will adapt that design to the beamlines
  More modern uTCA based system
  Replenishable VadaTech AMC digitizer cards
  Streamed readings
AIP BPM hardware will replace 8 GeV and BNB beamline electronics
  Existing VME system EOL
  Existing Echotek digitizer boards EOL, no useable spares
AIP will support additional readings, improved user experience
  New bunch by bunch measurement
  Modern user client and API
  Will help inform design choices for near future BPM and BLM upgrades in MI/RR
Organization
  Mary Convery – AD AIP Program Coordinator, AD Beam Division Director
  Robert Zwaska – Project Director, AD ACT Division Director
  Kyle Hazelwood – Project Manager, AD MI Department Head
  Craig Drennan – Project Engineer, AD INST Department Head
Existing 8 GeV BLM Crate

## Slide 3: Update
2
Kyle J. Hazelwood | MI8 BPM AIP | PMG Meeting
Project began mid January, baselined in March
Initial progress slow
  Personnel availability
Ongoing work
  Documentation
    Digital specifications near ready for review (digitizers, crates)
    Analog specifications ready for review (rear transition module)
    User requirements under development
    Timing module specifications started
    Digital product procurement testing procedures being developed
  Analog electronics
    Rear Transition Module (RTM) board being designed and laid out
Planned work for the quarter
  Begin procurement of prototype crate components
VadaTech AMC board