## Slide 1: MQXFA17 Overtemp excursion on NbTi splice And Proposed Recovery Options Updated 3/15/24
D. Cheng, for the AUP team
February 22, 2024

## Slide 2: Background
During the magnet splice operations two experienced technicians were assigned to make the second layer splice (“3/4” joint between Q1 and Q4)
When the operation was completed both technicians moved on to other tasks
  Assumed that the other would turn off the variac that was controlling the heater
Approximately ~10 min. passed before building occupants started smelling burning G11
The variac was then powered off, but the G11 around the splice block was blackened by that time
  No alarms or thermal protection were built into the splice tooling, since it was always supposed to be monitored for solder flow at ~200C, etc. when powered on
G11 discoloration was sanded/stoned for clean up, splice was packaged up as normal to stay stable while conditions were examined

## Slide 3: Background (2)
Splice joint setup

## Slide 4: Background (3)

## Slide 5: Preliminary Examination
Because no temperature monitoring was present the actual excursion was unknown
  Flux burns off ~380 C, so temperature must have exceeded this value
Some sample G11 ”burn tests” were performed
  One G11 pole key (bulk)
    solder melts @ 190C approx 1 min 30 sec
    Flux is gone @ 3 min 45 sec 380C
    Discoloration @approx 380C-410C
    Burnt G11 smell @ 410-415C
    Visibly G11 burnt @ 480C
    520c @6 min 30 sec
  One thinner piece (~1/8” plate)
    solder melts @ 190 1min 30sec
    Flux is gone @ 3 min 45 sec 380C
    ~400 C visibly discoloring @ 4 min, and delaminating
  Same clean up method Acetone and a wire brush after cool down
Preliminary conclusion from these tests is the the joint may be reached anywhere from 400C - 500C

## Slide 6: Preliminary Examination

## Slide 7: Additional Examination Possible?
Can the CLIQ lead be used to determine temperature excursion in the joint?
  Micrograph possible to compare with non-heated CLIQ lead?
This might be a NDE way to determine temperature excursion

## Slide 8: Update
Splice joint was measured; currently showing 60 µohm resistance across the joint

## Slide 9: Sectioning the NbTi splice joint
Each ~6 mm section will be cut in half
  This allows metallography and magnetization measurements to be performed on the same sample section
Two samples
  MQXFA17 overheated joint
  Mockup sample joint
CLIQ lead
NbTi Leads

## Slide 10: Proposed Replacement of NbTi Leads
Two options considered:
  Option 1: Replace NbTi lead in the splice box
    Will not require undoing of magnet preload
    Least invasive
    Dependent on the clearance of leads
    This is a more complicated design solution
  Option 2: Replace NbTi lead where it passes through the endplate
    More invasive: Will require undoing of magnet preload (half azimuthal, full axial unload)
    Fewer parts will need to be modified, but simple design

## Slide 11: Proposed Replacement of NbTi Leads
Option 1: Examined splice box clearances
There is not enough length available to splice a NbTi lead replacement to the Q4 lead

## Slide 12: Proposed Replacement of NbTi Leads
Option 2: Placing NbTi splice in the endplate
Clearances are such that the restraint guide can be machined to provide clearance for two new NbTi leads
New NbTi leads

## Slide 13: Option 2 Replacement of NbTi Leads
Option 2: Placing NbTi splice in the endplate
Cut Lead
Replacement Lead
New splice joint

## Slide 14: Option 2 Replacement of NbTi Leads
Option 2: Placing NbTi splice in the endplate
Can be performed for both Q1 and Q4 leads
May also need to modify lead support ramp

## Slide 15: Option 2 Replacement of NbTi Leads
Option 2: Placing NbTi splice in the endplate
115 mm splice joint (same as in normal joints) can be fit ~23 mm from the Coil theoretical end
May also need to modify lead support ramp

## Slide 16: Option 2 Replacement of NbTi Leads
Option 2: Placing NbTi splice in the endplate
VT locations can be provided
Existing VT pass-thrus can accommodate 2nd wire for monitoring these new splice joints
Extra VTA01b wires from coils (currently unused and bundled) can be utilized for this pair

## Slide 17: Option 2 Replacement of NbTi Leads
Summary of operations (off-normal) needed:
  Undo splice joints, remove splice box
  Unload magnet to half-azimuthal, no axial; remove LE endplate
  Cut NbTi leads of Q1 and Q4
  Modify/fabricate G11 restraint guides
  Add new NbTi leads
  Redo magnet preload to full axial, full-azimuthal
  Make up magnet splices, include extra VT wires for NbTi splice joint monitoring
Then the usual magnet EQC/connectorization prep to finish magnet will follow

## Slide 18: Recovery Update, 3/7/24
Magnetization and metallographic examination of the overheated NbTi strand appear to show no damage to current carrying ability
  Sintering of strands observed, and not very much solder was present
Recovering MQXFA17 to put back into service
  Tested with an overheated sample joint
    Mechanically separated the cut CLIQ lead from the existing joint
    Re-flowed more solder
  Replace the FVT voltage taps
  Complete connectorization and final finishing operations
  Perform SeqR and single EQC hipot coil-structure (Final EQC was already performed and passed prior to splice joint examination)

## Slide 19: Recovery Update, Tested Samples
Overheated sample joint to ~450C for ~5 min, allowed flux to burn off and solder to drip out

## Slide 20: Recovery Update, Tested Samples
A cut CLIQ lead section was also part of the overheated joint; practice for separation

## Slide 21: Recovery Update, Tested Samples
A chisel was used to mechanically separate the CLIQ lead from the NbTi lead
  Was not difficult, and did not damage the conductor

## Slide 22: Recovery Update, Tested Samples
Cut section of the overheated joint, before backfilling
Then backfilled by feeding more ribbon solder at normal temperature

## Slide 23: Recovery Update, Tested Samples
Sample was cut of the overheated joint
Joint was then set up to re-flow solder
  MOB-39 flux applied
  Heated joint to normal temp (290C)
  Solder applied to the end and sides and everything wetted without issue
A sample of the backfilled joint was then cut
Imaging from both samples just received
  May need to practice and examine the process further…

## Slide 24: Recovery Update, Tested Samples
Will need to practice and examine the backfilling operation
  (not much additional solder observed in sections)

## Slide 25: Recovery Update, 3/12/24
Overheated sample backfill test, Take 2
  Weighed joint and solder separately
  Applied MOB-39 to sample joint
  Attempted rewetting/flowing at 260 C
  Weighed backfilled joint
Attached a new CLIQ lead
  Wetted at ~260 C (weighed before and after)
  Removed CLIQ lead with heat
Attempted mechanically separating a NbTi lead
  Using a thinner blade instead of thick chisel wedge

## Slide 26: Recovery Update, 3/12/24
Overheated sample backfill test #2

## Slide 27: Recovery Update, 3/12/24
Overheated sample backfill test #2
Conclusion: <1g weight gain may be due to gas pockets where flux and solder cannot flow, and no more solder is able to be flowed

## Slide 28: Recovery Update, 3/12/24
Add new CLIQ lead to overheated joint

## Slide 29: Recovery Update, 3/12/24
Add new CLIQ lead to overheated joint (and removed it)
CLIQ lead was able to be soldered just fine; ~2.65g weight gain doesn’t have any comparison to fill quality
Also, this CLIQ lead can be mechanically detached from joint, which may indicate only wetting to overheated solder surfaces

## Slide 30: Recovery Update, 3/13/24
Tasks performed
  Mechanically separated first NbTi lead from test joint
    Used unsharpened section of 0.020” shim
  Mechanically separated second NbTi lead from test joint
    Used a beveled section of 0.020” shim
  Prep joint for re-flowing solder with the two separated NbTi leads, as well as the new CLIQ lead section

## Slide 31: Recovery Update, 3/13/24
Separated first & second NbTi leads from sample joint
Initial removal used an unsharpened 0.020” thick shim. Appeared to scratch lead
2nd layer used a slightly sharpened shim, which didn’t appear to scratch as much

## Slide 32: Recovery Update, 3/13/24
Resoldered a new CLIQ lead and the two NbTi layers

## Slide 33: Recovery Update, 3/13/24
Before & after measurements of the test joint
Compared to before and after weight measurements it shows only about 2.9g of solder was added to this joint
However, the prior test of only the new CLIQ lead showed approximately 2.6g of weight gain. e.g. very little additional solder was added to the two NbTi lead joint interfaces

## Slide 34: Recovery Update, 3/13/24
Summary of these recent tests
  No significant additional solder can be added to the overheated joint, as measured by weight
    Both flux and solder end up flowing and dripping out
  Separation of the old CLIQ lead is possible, and soldering in a new one is possible
    However the joint appears to not be as solid as with a non-overheated surface (can be mechanically separated somewhat easily)
  Separation of the NbTi lead is possible as well
    However very little solder remains after a re-soldering operation
Conclusion: It is best to leave the existing overheated NbTi splices in place w/o separation, but solder in a new CLIQ lead

## Slide 35: Recovery Update, 3/15/24
The final plan to finish:
  The overheated NbTi splices will be kept as-is w/o separation
  A new CLIQ lead will soldered in
    Old CLIQ lead will be mechanically removed
    Mechanical surface prep and standard joint cleaning
    New CLIQ lead will be soldered in
    Green putty will be used as a smart shim to package splice before cover is installed
  Standard finishing operations will be performed
    Abbreviated EQC: Hipot Coil-Structure, SeqR