## Slide 1
Switchyard & Meson Report
Michael K. Olander
AD 9:00 Meeting
21 March 2024

## Slide 2: Since Our Last Episode…
F-Sector LCW Leaks
  Repairs completed and “good enough” to restart Remanent LCW System.
    This allowed MOS 89 @ KRSS to be energized.
    We do need to access F-Sector before running beam to retrieve the F0 Crane Electronics.
  Thanks to TD, MSD, & ES&H for oversight and repair of the system
  Since restart, leaks have moved to CUB due to low heat load.
MT5E-4
  MSD able to patch with Gortex
  Thanks to MSD for the repair.

## Slide 3: Since Our Last Episode…
Enclosure B Sump Repairs
  ISD waiting for check valve.
Switchyard Vacuum Station 95 Repairs
  Waiting for sump repair to complete.
S:H202-5 LCW Leak
  Leak previously evaluated by TD, it cannot be repaired in place.
  Should not impact startup timeline.
Performed beamline walkthroughs
  F1-Manhole walkthrough & revisit some SWICs before startup.

## Slide 4: H202-5 Magnet Running with No LCW
The S:H202 magnet string is a 14 EPB (of various styles from original recipe to EDBC) dipole bend string. H202-5 is one of the older versions.
The operating point of the bend string is within 1% of the recommended RMS current for operating an EPB style dipole without LCW.
We intend to drain the LCW from the magnet, dry it out, and operate for the running period.
  The magnet will be planned to be changed out during the Summer Shutdown.
    We have spare EDBCs in inventory.

## Slide 5: To Do Before Beam
Install the check valve on Enclosure B Sump
Recover 95 Vacuum Station
Recover G1 Stub Vacuum Station (NM Vacuum)
Drain and dry out H202-5
Disconnect M00U-1 magnet from string
Finish Checkouts
Finish Pre-Start Items from SAD/ASE Review
Return to service LOTO’d power supplies
Beamline Commissioning

## Slide 6: Goal
The goal is beam to users in 5 weeks.