## Slide 1: 302.02.07 Structures Status
Magnet | Status | Notes
Pre-Series |  | 
MQXFA03 | Complete; report released | 
MQXFA04 | Complete; report released | 
MQXFA05 | Complete; report released | 
MQXFA06 | Complete; report released | 
MQXFA07b | Complete | SG Test report drafted; Prepping to ship to FNAL
MQXFA08b | Complete; report released | No coil SG data with 2nd thermal cycle
Series |  | 
MQXFA10 | Complete; report released | 
MQXFA11 | Complete; report released | 
MQXFA14b | Test complete | Fab & Test report drafts completed

## Slide 2: 302.02.07 Structures Status
Magnet | Status | Notes
Series |  | 
MQXFA09 | Disassembled | Two coils no longer available (in A14b, A15); Structures used in MQXFA11; will be renamed MQXFA24
MQXFA12b | Shell-yoke assemblies this week; adding additional SG instrumentation for tapered shim demonstration | Shims & Loading Review report draft released
MQXFA13b | Preload operations completed, EQC next | Coil 150 replaces Coil 241
MQXFA15 | At BNL, 2nd thermal cycle in process | No SG data uploaded last week
MQXFA16 | At FNAL10/13 | Fabrication Report drafts edited
MQXFA17 | CLIQ lead replaced everything signed off | Shipped to BNL 3/23
MQXFA18 | Measuring Coils, processing for CSR | Expected to be shipped direct to FNAL

## Slide 3: 302.02.07 Structures Status 2
Series Magnets (cont.)
Updated Magnet specifications to allow for 120 MPa excursions, increased from 110 MPa
  MQXFA07b, MQXFA16, MQXFA15 reload did not require 120 MPa
  MQXFA17 reached 120 MPa during preload
  MQXFA13b coil 2 reached 126 Mpa in last excursion

## Slide 4: Coils in Storage at LBNL
 |  | LE CMM | Nom. CMM | RE CMM
241 | (Was) Replacement coil for MQXFA13b (large) | ✓ | ✓ | ✓
158 | Small coil (was originally for MQXFA12b) | ✓ | ✓ | ✓
242 | Spare (was for MQXFA17 and/or MQXFA13b) | ✓ | ✓ | ✓
234 | On Hold. (Too small spare for MQXFA16) | ✓ | ✓ | ✓
240 | Arrived from BNL 12/4; CMM complete | ✓ | ✓ | ✓
248 | Arrived from BNL 12/4; CMM complete | ✓ | ✓ | ✓
243 | Arrived from BNL 2/5/24 | ✓✓ | ✓ | ✓✓
244 | Arrived from BNL 2/5/24 | ✓✓ | ✓ | ✓✓
160 | CMM Measurements on LE/RE 3x | ✓✓ | ✓ | ✓✓
161 | CMM Measurements on LE/RE 3x | ✓✓ | ✓ | ✓✓
✓✓ Averaged 3x extra measurements taken on ends

## Slide 5: 302.02.07 Structures Status
Other topics
Technicians
  New techs are getting up to speed
Bladders:
  200 pcs order fabrication and testing is complete
  Working with CERN to source tubing for their style bladders for MQXFA lengths
    Planning upgrade for HP cart to accommodate additional circuits
FY22 Procurements
  Extra ARMCO is stored in Berkeley
    BCR approved for $33k duty and shipping costs
  Additional, non-MA, procurements have been placed; ongoing for consumables
Property Transfer from LBNL to FNAL
  MQXFA07b property documents processing will start
  Transfers to happen in “bulk”
MQXFA spare parts
  Obtained new updated quotes from vendors for spares and compiled for BCR; orders paperwork being prepared

## Slide 6: MQXFA17 Recovery Update, 3/25/24
Final Update:
  The overheated NbTi splices was kept as-is w/o separation
  A new CLIQ lead was soldered in
    Old CLIQ lead mechanically removed
    New CLIQ lead was soldered in
    Green putty was used as a smart shim to package splice before cover was installed
  Standard finishing operations completed successfully
    Abbreviated EQC: Hipot Coil-Structure, SeqR
  Magnet was shipped to BNL 3/23/24

## Slide 7: MQXFA17 Recovery Update, 3/25/24
New CLIQ Lead and packaging