## Sheet1
FD1 CPA Production Readiness Review Documents
Category | Document | EDMS | File Name | Description | Comments
Systems Engineering/Mechanical Engineering | Integrated sub-system (3D) model | 2144461 | DFD-13-6000_092122.png | HVS 3D model
| Interface Documents | 2742503 | FD1 HVS Interface Documents | Contains files of CPA interfaces - in 2339392 "Requirements and Interfaces for Detector Support System (DSS) v.3" and in 2088721 "JT-HV to JT-PD Far Detector 1 Interface Control Document v2.9"
| Final fbrication drawings | 2633164 | DFD_CPA_071123.pdf | CPA Production drawings
|  | 2633164 | Donut_051023.pdf | Detail of HV Donut connection
| Part Identifier assignments | 2943054 | CPA_Part_Identifier_Assignments | Part IDs defined for CPA in HWDB
| Schema for component entries in DUNE HWDB |  |  | On its way | Hajime is putting final touches on it
| Approved installation plan | 2233449 | FD1-HD Installation Plan 9 Aug 2022(v5).docx | Also in 2943054, Assembly_and_Installation_at_SURF
Electrical Engineering | Approved Grounding & Shielding Plan | 2373456 | DUNE_FD1_HVS_Grounding_v1.2
| System wiring diagrams | 2943054 | DUNE_FD_SP_CPA_Diagram_2024-03-25-draft.pdf
| Detailed cable drawings | 2633164 | DFD_CPA_071123.pdf | Included in CPA drawing package
| Printed circuit board documentation | 2144465 v.3 | SP CPA FSS Bias Board
| Schematics | 2943054 | CPA-Schematics-2024-04-02(91).pdf | Latest version by Glenn
| Layout artwork and Gerber files | 2144465 v.3 | frameboard-endwall-gerber.zip
| Bill of materials |  |  | location? | asked Glenn about this - found in old BOE from April 2021
| Firmware/software validation | NA | NA | NA
| Electro-static discharge (ESD) procedures | NA | NA | NA
Compliance Office | Documentation of electrical and mechanical safety reviews
Compliance Office Approvals
| Plans for component procurement including procurement specifications | 2943054 | Procurement_Plans_and_Responsibilities | Division of responsibility for part procurement between CPA factories and part suppliers
Engineering codes and standards to be applied in manufacturing processes
| Plan for documentation of commercial vendor QC requirements | 2943054 | Plan_for_commercial_vendor_QC_documentation | Plan of QC tests done by vendors
Certified material test reports
Certificates of compliance
General test inspection reports
| Process for requesting and approving engineering changes during production | 2943054 | Process_for_requsting_and_approving_engineering_changes_during_production | Made this up
| Plans for critical handling of components | NA | NA | NA
Technical Coordination | Production schedule | 2943054, 2956778 | Production_Schedule, CPA Factory Production.xlsx | Schedule for production at factories
| Shipping plan and schedule | 2943054 | Material_Shipment_Schedule | Shipping CPA crates to SURF
| Plan for resources (facilities, infrastructure, and workforce) | 2943054 | Production_Status_and_Manufacturing_Procedures
| Production risks assessment and proposed mitigation strategies | 2943054 | Production_Risk_Assessment_an_Proposed_Mitigation | Several scenarios
| Delineation of responsibilities and required signoffs at each stage of shipping process | 2943054 | ShippingPlanDetails032124
Review Office | Responses to previous review recommendations | 2774172, 2796146 | FD1 HVS PDR Closeout, FD1 HVS FDR Closeout | Closeout reports from PDR and FDR
| Final testing and performance results from prototyping activities | DocDB 28412, 28325, 27382 | Cold Tests of SS Hardware for CPA Connections, Summary of NASA evaluation of Helical and Belleville Washers, Cold Test of Insulator for CPA FSS Edge | Docs of testing of hardware components
| Description of design changes ocurring after the Final Design Review |  |  | A few typos and omissions from a few drawings
Project ES&H | Production facility safety plans | 2943054 | wpc_worker_package.pdf | ANL Work Control Document (WCD)
| Hazard analyses for the production and manufacturing processes | 2943054 | wpc_worker_package.pdf | ANL WCD
Project Quality Assurance | Detailed manufacturing procedures including inspection and testing steps | 2943054 | Production_Status_and_Manufacturing_Procedures | Included in iPad app
| Shipping, handling, and storage specifications | 2943054 | Storage_Requirements_in_the_Warehouse_and_Related_QC
| QC Plan | 2943054 | QC_Details | Description of QC procedures and checklists in the iPad app
| Manufacturing traveller documents | 2943054 | QC_Details | Description of tagging system in this document
| Disposition plan for non-conforming items | 2943054 | Disposition_Plan_for_non | Plan for non-conforming items
| Plan for QC data stored in the HWDB | 2943054 | QC_Details | What QC data in HWDB is used for
| Documentation of assigned responsibilities in QC process | 2952719 | CPA Parts QC, Personnel, and Schedule Requirements | Assigns parts QC and schedules between ANL and CWM
| Drafts of detailed installation procedures including inspection and testing | 2943054 | CPAiPadappUseerGuide020224 | Included in iPad app