## Slide 1
Pressing Issues / Special Topic: Slide #2 - Elevators, Predictive Solutions, Lighting, and Power
Noteworthy Items: Slide #3 – SWA 2FLR, Abatement, TSIB, Anchor Point Inspections, Door Lights, Mystery Dumpster
Mechanical and Utility Outages: Slide #4
Active Projects and Contractors Onsite: Slide #5 & #6
Safety Success – With the Fire Department starting their walkthroughs, the big ask is to keep door access open (even if we do not use the door regularly), keep aisleways open incase of an emergency of getting out of buildings, Combustible Items need to be stored in cabinets, and general housekeeping.
Infrastructure Services Division Updates

## Slide 2
Special Topic:
IERC and Wilson Hall - Power outage for the 19th is a go
BTW 2nd FLR LED Project – Work started yesterday with a walk through with Leyden.
Predictive Solutions – The Fire Department has been doing more walkthroughs and found common concerns.
  “door blocked”
  “remove excessive transient combustible material”
  “perform proper housekeeping practices”
Elevator Update –
  MI-31, back up and running.
  MI-65, has been inspected and passed.
  Minos, under review and plan is in the works.

## Slide 3
SWA 2nd Refurbishing – MMR’s have started moving and a walkdown with the abatement company (High Efficiency Professional Abatement - H.E.P.A.) this past week to discuss work needs. ✅
C-0 Abatement – Also walked down with H.E.P.A. to discuss work planning to remediate the bathroom. This will place the bathroom out of service for a bit. ⚠
TSIB – Weather has not been good for them these past two weeks. Meade is working on truck lines within M-8.
Anchor Inspections – Contractor, Premier, has been brought on board as an inspection service through Safety. Inspections started this past week at MI-31 internal points, MI-10 exterior rotational, and NML internal. We need to work on better communication on future scheduling however its progress. ⚠
Door Lights – door lights in 3 doors have been completed. ✅
Groot Dumpster – Been tracking down the requester of a temporary dumpster for the Transfer Gallery, that has been here since May. We are looking to see if it is still needed.
Noteworthy Items

## Slide 4
Mechanical and Utility Outages
Planned Power Outages
Current Outage Schedule is populated.
Shutdowns are scheduled to begin in May.

## Slide 5
Active Projects still in motion and Contractors on Site
AD Projects:
Door EOL Replacements – Requisition for 13 doors on the eol list is in progress. Plus 4 others on a fast track working with Scott on locations like SWA, ME7, & AP0, MT Worm. No Change
E4R Door Replacement – In procurement
Office Refurbishing – We have some movement on BTE/W carpet replacements. We are getting the finances worked out currently. No change
Exterior Ladder EOL replacements – Currently 24 ladders are targeted. SOW is being developed. Meeting with Safety Planned for next week.
Roof Repairs in progress: MS6, MI-8, TG, MS4, and SWA. – Roofing Repair company (M. Cannon) is working through the list of roof repairs. The Scheduler/Planners are working with different groups now.
New Roofs – HAB is coming along, Minos/Village Gym/Fuel Station are next up and just waiting on different phases of the projects to firm up dates.
Prairie Burns – Prairie burns have started again. There were 2 this past week.
NTF Safety Project – Walkdown with Safety, DSO, and RAD showing DOE what we are planning to do to install a permanent safety rail. HA is being approved.

## Slide 6
Active Projects still in motion and Contractors on Site
AD Projects:
Potential next Projects – APOTH Door & Frame Replacement (waiting on quote), A0 cleanroom sanitary line replacement (performed walkdown and waiting on quote), MI Building Concrete Coatings, C0 Service Building (in beginning phase). – No Change
Metal Roof Coatings – SOW of work is being developed; project will have to go out to bid due to size. – No Change
Lighting Work/Upgrades – CMTF have been halted due to other lab priorities. 2nd Floor BTW started 4.4.24.
Foundation Leaks – MT6/MC2/Wilson Hall – SOW is in progress.
MI-8 Building Signage – Working to get this fix
And More…

## Slide 7
Road Closures
Closures from Fermilab today or R&G site
  Lab closures
  Closures close to WH