## Slide 1
Tom Diehl (FNAL), Greg Rakness (FNAL)
Friday 9am AD meeting
05-Apr-2024
Mu2e report
https://indico.fnal.gov/event/64204/

## Slide 2: Transport Solenoids
Upstream Transport Solenoid (TSu)
  All stands welded to floor plates. Elevation needs to be adjusted, then metrology
  Welding on access platform to cryo services to resume
Downstream Transport Solenoid (TSd)
  All stands welded to floor plates. Elevation needs to be adjusted, then metrology
  Leak checking fixture removed from solenoid end, getting ready to wire the connectors tree

## Slide 3: Solenoids infrastructure
Insulating vacuum
  Control cables pulled to the pipe chase alcove
  3 turbo pumps installed, 4th turbo being refurbished
Solenoids power supplies
  Work continues in the power supply room intermittently
Controls and monitoring
  Feedbox + Transfer line – connector tree wiring resumed
Helium vent lines
  Feedbox to vent header installation ongoing

## Slide 4: Equipment infrastructure
Equipment Cooling Water
  Cut into CUB complete
  Installation of piping ongoing in mechanical room and sidewalk
Compressed air lines
  Installation in West wall relief and Production Solenoid area ongoing
    Will use AD scanner in pipe chase alcove and RHR to install more anchors. HA approved to work overhead.

## Slide 5: Detector subsystem infrastructure
Detector external stands
  Inspection of top surfaces of top portions complete
Tracker chiller
  Installation of piping ongoing
Tracker and Calo cables and fibers
  Installation continues
Data Acquisition
  Construction Readiness Review held: repurposing nodes from Muon g-2
Calorimeter DT generator
  ORC held 04-Apr  following up on action items