## Slide 1: Muon Campus Operation Report
Jim Morgan
Friday 09:00 Operations Meeting
April 5, 2024

## Slide 2: Muon Campus status
KPS5A PFL Repair
Intentional Accelerator
Standby Period
MC-1 Controlled Access
Study – Alternative M5 optics
G-2 Trolley Run
<------------Week Days -------------------
Study – M1-M3 Optics
ESS1 & ESS2 Electrostatic Septa
  ESS1 was transported to NWA on Tuesday, now in test cave
  Vacuum pump-down underway
  High voltage conditioning begins next week
  ESS2 assembly has been paused, will resume at A0 Clean Room next week
  New main A0 Air Conditioning unit expected to be tested next week
Working towards permission for beam operation, beginning sign-offs
AP-0 A/C work continued
LCW leak on header fitting behind Q206
Some progress on finishing D30 mechanical work
Reconnected most of cabling in D30 that was removed for planned work
Performing tunnel inspections of water valves and cabling

## Slide 3: ESS1 vacuum pump-down at NWA

## Slide 4: Leak behind Q206

## Slide 5: M4 Line components being reinstalled
PWC900 goes here

## Slide 6: ESS2 awaiting vacuum spools

## Slide 7: Upcoming work
ESS1 and ESS2
  ESS1 high voltage conditioning expected to start Wednesday at NWA
  ESS2 assembly will resume at A0 Clean Room
  Portable A/C unit for Clean Room working well, main A/C unit nearly ready
  Installation of new A0 Clean Room A/C units probably months away
Need to close up D30 vacuum and pump down
  Vacuum spools for prototype ESS2 need to be installed
  Vacuum spool already installed at ESS1 location
  M4 line above Q206 being reinstalled
  Vacuum leak check and pump-down will follow
AP-0 A/C work continues
  Access to AP-0 Water Cage and rad fence area simplified while not running beam
Hope to resume beam operation later this month
  Beginning start-up sign-offs
  Need to re-core Delivery Ring, Extraction & M4 Enclosures from Shutdown keys
  Still need to safety test these three enclosures