## Slide 1
LBNF Hadron Absorber – Installation Planning and Integration
Jonathan Williams
TSD Topical Meeting
18 April 2024

## Slide 2: Outline
Introduction
  LBNF Overview
Absorber Design Overview
Installation Planning
  Welds & Component Stacking
Integration Activities
  Thermocouples
  External Crane
  Interfaces
  Worker Access
  FNAL CAD vs. Construction Prints/Models

## Slide 3: LBNF Overview

## Slide 4: Long-Baseline Neutrino Facility
Make the neutrino beam for DUNE
Protons on a graphite target --> focus pions --> decay to neutrinos
What happens to the protons? Everything else?

## Slide 5: LBNF-30: Absorber Complex
Beamline
Decay Pipe
Hadron Absorber
Muon Monitors
& Shielding
Muon Kern
Access Hatch
Service Building

## Slide 6: Absorber Requirements
Intercept primary proton beam
  2.4 MW @ 120 GeV: 1.2s cycle time (0.7s with ACE?), 1.5E+14 protons per pulse
  Rated for 2 full-power accident pulses, assumes no hit on target or baffle
Beam permit interlock
  Active detection, limit accident pulses to 2 (MuMS, thermocouples in pile)
Serviceability & Accident Resiliency
  30-year design life, core must be serviceable (replaceable modules), have morgue space
Structural Integrity
  Interface with decay pipe
Radiological Safety
  Interventions and Operations - ALARA

## Slide 7: Design Overview

## Slide 8: Bunker & RAW Pan
Bunker
  Morgue: 4 core modules, 2 hadron monitors (HADES)
  Air inlet & exhaust
  Water supply manifold
Stainless steel pan (1/4” / 6mm thick) to catch water leaks from core
  Leveling during assembly is crucial
    Grout layers on underlying steel layer
  Embeds in wall to attach sides of pan

## Slide 9: Outer Steel Shielding
Steel plates & slabs (lots of 9.11” steel) – 1.2 million pounds (545,000 kg)
130 Blue Blocks, 20,000 lbs (~9,000 kg) each, 2.6 M lbs (1,180,000 kg)

## Slide 10: Core Modules & Supports
Steel T-Block (air-cooled)
  Absorber based on NuMI target shield pile
Aluminum core blocks (water-cooled)
  Staggering along beam direction – wide/narrow blocks
Spoiler
Mask
Al Core
Steel Core
HADES (left)
Pre-Spoiler Air Box (right)
Module Supports
Ongoing revisions!
Changes here

## Slide 11: Air Channels & Blue Block Supports

## Slide 12: Core Modules & Supports
Spacer plates between supports maintain air gap
  Leveling screws on modules
Bring in modules after chase is complete
  Take time to align/level each module to ensure spacing

## Slide 13: On-Axis View

## Slide 14: Core Blocks

## Slide 15: Core Blocks
Prototype Core Block – Engineer for scale

## Slide 16: Core and Shielding – Active Cooling
1310 gpm water @ 80 F (27 C), 5-7 ft/s in passages, 80 gpm core, 40 gpm mask (229 kW @ 2.4 MW)
25,000 CFM air, 32” water column, 5 mm gap, 15m/s velocity (244 kW @ 2.4 MW)
Water manifold has leftover blank ports

## Slide 17: Component Assembly & Installation Planning

## Slide 18: How do you build a ship…
Absorber Bunker Assembly: ~8000 tons (7200 metric tons)

## Slide 19: … in a bottle?
Open-air access hatch
  All components lowered via external crane
Installation bottleneck
  Limited space downstairs for storage
    Just-in-time delivery
    Hard to install components in parallel
Receiving Stand

## Slide 20: Core Module Assembly
Core module water loops are gundrilled, with welded-on supply lines
  Assemble vertically: 1G position for aluminum welds wherever possible
Store vertically, then transport to Absorber Hall
Assembly Stand
Storage Stand (20x G-Blocks, reuse for Absorber)
Down-Shaft Receiving Stand

## Slide 21: Module Transport
Rotating strongback/transport cradle
Rotation fixture at hatch and storage location, transport flat by trailer
Rotation Stand & Transport Frame
*Old Model
*Old Model
*New Model

## Slide 22: Water Line Welding
Need rigorous qualification of aluminum welds
  Can’t radiograph core module/elbow welds – need destructive inspections
    Procurement started on test articles for procedure development

## Slide 23: Outer Shielding Installation
Weld joints between plates
  6”-long, ½” or 5/8” PJP groove welds based on plate thickness
  HaDES supported by upstream wall
  Sidewalls mostly restrained by blue block stacks
Assembly model – future work
  Catalogue parts by size - Bunker walls are hard limit, everything has to fit
    Blue block dimensions are (+.25”/-.75”)
      Worst blue blocks get assigned to the Muon Kern
    Cambered plates/slabs – but new vendor may mitigate
  Filler plates to close off any gaps from undersize parts

## Slide 24: NuMI Target Shield Pile
NuMI Target Shield Pile Installation
3-high Blue Block stack
  LBNF Absorber has 5-high stacks
    Blue blocks modeled oversize, shimmed to fit and level
NuMI Target Shield Pile Mockup

## Slide 25: Installation Overview
114 modeled steps, ~800+ major component lifts

## Slide 26: Integration Activities

## Slide 27: Core Thermocouples – Cable Routing
Cable routing from TC block
  Rad-hard cable inside bunker
  Patch panel to complete run to Instrumentation Room with normal TC cable
  Probably on crow’s nest (downstream end of Decay Pipe shielding

## Slide 28: External Crane – The Road to Neutrino Science is Paved With Good Intentions…
Long, long ago, in an age of budgets gone by:
  Absorber had a service building with an internal crane
In the Second Age: Descoped, smaller building, external mobile crane – saved $$$$
  Makes installation & interventions more difficult
  Much more subject to weather delays
The Third Age: We need a 500-ton capacity mobile crane
  Boom reach + load, truck access to congested area
  Quoted for ~10 months of crane rental: $$$$
  Getting crane to site a major challenge
The Fourth Age: open air bridge crane

## Slide 29: Decay Region / Absorber Interface
Thermal Expansion of Decay Pipe
  200m length – lots of steel and concrete to expand with beam heating
  6” (~15 cm) expansion allowance
  Expansion coefficient for poured concrete ~ 10 µm/m*C °
    200m, 10 C° = 1 cm expansion
Expansion joints on walkways
Air seal between decay pipe and hall
Helium fill pipe routing
Worker access to clear top of decay shielding
6” gap
LBNF-30
Foundation
Decay Pipe
Concrete Shielding

## Slide 30: Worker Access & Safety
Ladders, portable stairs
Lots of welding in a relatively small area
  Smoke eaters & ventilation fan positioning
  Exhaust down blue block channel
  Absorber Hall air supply during install
Fall protection/prevention – where do we need scaffold, grate covers, pit covers, barriers, guardrails, life safety tie-off points?
  Initial meeting with ES&H
  Ongoing work with integration group
  VR “Holodeck” (see next slides)

## Slide 31: Virtual Reality lab – Holodeck @ BEG

## Slide 32: Integration Model Exploration

## Slide 33: Looking up the barrel of LBNF

## Slide 34: Questions?

## Slide 35: Backup

## Slide 36: Concrete Blocks
48x “G”-blocks, 24ft x 3ft x 1.5ft (7.32 m x 0.91m x 0.46m)
  Includes 10x heavy mix concrete at top upstream end (extra boron)
“T”-shaped blocks for downstream face
  Provide labyrinthing
G-Blocks make an air seal over pile
  Air supply for cooling
  Isolate absorber/morgue air volume from Hall
  Need to redo caulking after interventions

## Slide 37: Radiation Modeling
FNAL MARS group has been extensively modeling the Absorber
  Recent changes to air supply duct, modeling residual dose in air
Scale is mSv/hr
Beam on (2.4 MW) prompt dose
Beam off (110 d irr., 4 hr cooling) contact residual dose
  DUNE-DocDB-17021-v5

## Slide 38: Heat Deposition
DUNE-DocDB-17064, S. Striganov
*Data for 2.4 MW operation
mW/cm3

## Slide 39: 2.4 Megawatts or Bust
Future-proof active cooling systems - design for 2.4 MW
    Maintain all temperatures within material limits – 100 C fatigue limit for 6061-T6 core blocks, 230 F for anti-corrosion paint on steel
Absorb secondary particles and radiation
  Steel backstop, muon kern downstream
How to detect bad beam quickly?
  224 thermocouples (in beam) in core module 2
  Scaled-up NuMI system (4 TCs)
  dT/pulse limit: <1 degree normal, 16-90 deg for accidents
  Water line could be hit by beam: modeling work
Thermocouple Core Module

## Slide 40: Thermocouple Layout

## Slide 42: Challenges & Some Solutions
How to minimize worker dose?
  Remote crane operations, minimize touch labor on top of absorber
  (water line connections & wiring only)
Graphics: V. Sidorov
Conceptual stacking layout for HADES access

## Slide 43: HADES Retractive System