## Slide 1: Muon Campus Operation Report
Jim Morgan
Friday 09:00 Operations Meeting
April 12, 2024

## Slide 2: Muon Campus status
Study – Alternative M5 optics
Study – M1-M3 Optics
ESS1 & ESS2 Electrostatic Septa
  ESS1 high voltage conditioning began Wednesday at NWA
  ESS2 assembly has been paused while other work took place in the A0 Clean Room
Working towards permission for beam operation, beginning sign-offs
  Half-way through beam sign-offs
  Finishing vacuum work in D30 straight section
  Finishing punch-list items from shutdown work
  Power supply inspections
  Plan to r-core Delivery Ring, Extraction and M4 Enclosures to operational keys
AP-0 A/C work continued
Performing tunnel inspections of water valves and cabling

## Slide 3: ESS1 high voltage conditioning at NWA
ESS1 P.S. Voltage
Spark Detector
ESS1 P.S. Current
Ion Gauge

## Slide 4: Muon Campus in Mu2e mode

## Slide 5: D30 Vacuum work
Final area to be pumped down

## Slide 6: Final vacuum interval to be pumped down
BVH301
ESS2 & BVH203

## Slide 7: Downstream D30 and upstream M4 Line pumped down
BVH203
BVH209 & BV907

## Slide 8: Upcoming work
ESS1 and ESS2
  ESS1 high voltage conditioning continues at NWA
  ESS2 assembly will resume at A0 Clean Room
Need to finish up D30 vacuum work
  Working towards pumping down final area not at vacuum, which includes ESS2
  Hope to be finished with mechanical work next week
AP-0 A/C work continues
  Access to AP-0 Water Cage and rad fence area simplified while not running beam
Hope to resume beam operation later this month
  Working on beam sign-offs
  Plan to re-core Delivery Ring, Extraction & M4 Enclosures from Shutdown keys next Tuesday beginning at 16:00
  Still need to safety test these three enclosures
  Will start nagging people to remove LOTO locks at the end of each day