## Slide 1
Tom Diehl (FNAL), Greg Rakness (FNAL)
Friday 9am AD meeting
12-Apr-2024
Mu2e report
https://indico.fnal.gov/event/64296/

## Slide 2: Last week at the Mu2e building (1/2)
Metrology done on TSu and TSd
  Ready to begin welding on TSu-TSd mechanical interconnect
Receiving components at the building for connections to cryogenic transfer lines
  Preparing to make cryo connections in parallel with mechanical interconnect
ORC approval for DT generator now in the hands of PPD
  Personnel not available next week for tests, so this will likely push to week of 22-April

## Slide 3: Last week at the Mu2e building (2/2)
Working to understand the planarity of the external stands
  (External stands support Tracker & Calorimeter when they are extracted from the Detector Solenoid bore)
  Vendor data are inconsistent with FNAL observations
Figuring out lift logistics between AD, APS-TD, and PPD for M4 work and power supply work, respectively
  Excellent inter-directorate teamwork
No action on Tracker cabling last week.
  Working through consequences of Voluntary Separation Program
  Plan to resume week of 15-April