## Slide 1: LBNF - Beamline – Target Complex
Horns
  Redesign of Horns B & C outer conductors
    Design and modeling has just finished
    Investigated vendors’ capabilities
    Will start with designer to redo many drawings
  Friction Stir Welding
    Vendor 0:SDSMT reworked horn stripline failed x-ray quality – will continue for doing vibration studies…eventually a nice display piece
    Vendor 1: small German company sample piece passed xray and mechanical testing; sending Test Stand stripline stub for welding; will follow with Horn A Prototype stripline
    Vendor 2: PNNL to do sample pieces; agreement has been sent to procurement
  Investigation into spider support within horn and possible spark issue due to people working on outer conductor redesign
  Large ceramic insulating ring – Kyocera has given a budgetary estimate at nearly twice it was five years ago.
  Assembly of Prototype hangers is nearly completed
  Looking into thermocouple electrical standoff for conductor monitoring
LBNF Beamline Highest priority

## Slide 2: LBNF - Beamline – Target Complex
Horns Power Supply
  Many procurements in process
  Issues with chokes continue; fixes are being implemented
Water systems
  Test Stand Skid preparing drawings and documents for procuring vendor to build skid
  Nearing the completion of drawing sets for Horn B & Horn C RAW systems
  Newly assigned engineer is now familiar with Water Cooling Panel RAW system; await designer to be assigned.
  Design of controls for water systems has come to a stand still.
  Gas control system prototype installation @ C0 and ORC completed; instrumentation and control tested.