## Slide 1: LANL LAr Cryostat
Ramsey 2/1/2013

## Slide 2: Cryostat design criteria
Physics requirements
  Accommodate as large a TPC as possible within budget
  Allow optical access to the liquid argon volume for laser calibration system
  Shape considered
Mechanical
  Provide mechanical provisions for instrumentation as well as cryogenic services
  Maintain transportability
  User safety

## Slide 3: Major design revision
Based on input from UCLA collaborator Hanguo Wang
Significant improvement to system robustness and reduced risk associated with TPC work
  Minimized disturbance of cryogenic and instrumentation connections when accessing the TPC
  No large cryogenic seals
  Larger argon volume
  Larger instrumented volume/total volume ratio
  Enables all TPC wire planes to be mechanically identical (hexagonal TPC)
Change is supported by simulation work (Kevin Yarritu)

## Slide 4: Schedule and cost impacts of design change
Procurement of the cryostat is a major milestone in the LDRD project
Original plan was to be prepared to place cryostat order at the beginning of FY13
Cryostat delivery currently expected to arrive by end of August, 2013, based on expected bidding and delivery times
Though new cryostat cost is higher than the original, the cost increase is within the contingency as originally presented

## Slide 5: Overview of current design
Capacity: ~7700 L
External dimensions
  Flange diameter – 111”
  Work deck height - ~101”
All cryogenic and instrumentation connections made through top head
Work deck for worker safety and convenience
LIQUID ARGON VOLUME
WORK DECK
VACUUM JACKET
TOP HEAD
DEWAR ACCESS PORTS
VME CRATES
TPC ASSEMBLY
BAFFLE
ASSEMBLY
Notes: Add labels for major components

## Slide 6: Overview (continued)
Top Head Port layout
  8X 12” instrumentation/services ports (1 unsubscribed)
  1X 18” port (currently unsubscribed)
  6X 3” ports (5 currently unsubscribed)
6X TPC
INSTRUMENTATION
1X CRYO SERVICES
EMERGENCY VENT
1X HV FEEDTHROUGH

## Slide 7: Overview (continued)
Preliminary drawings have been prepared for cryostat RFQ
Vendor will provide final drawings for LANL approval prior to commencing with fabrication

## Slide 8: Safety
Pressure safety
  Design work has been done in coordination with LANL pressure safety personnel
  Cryostat design uses all conventional features, and will thus be an ASME Section VIII Division 1 pressure vessel
    ASME certification provides an independent QA check on the design and fabrication
    Can also ease approval overhead when vessel is transported to other labs
  Vacuum jacket relief per CGA-341
  Liquid volume relief via burst disk/vent pipe
Work deck
  Included to provide safe access to top ports for workers
  Mounts to the top of the cryostat
Inner Volume Surface Area (m2) | 15.920 | Wetted IVC Surface of Liquid Volume |  |  | 
Heating Rate (W/m2) | 1800 | Cryogenics 52 (2012) pp 331-335 |  |  | 
Latent Heat of Evap (J/kg) | 16081 |  |  |  | 
Total Heat Input (W) | 28656 |  |  |  | 
Mass Flow Rate (kg/s) | 1.782 |  |  |  | 
Flow through Straight Vent Pipe |  | STP Gas |  |  | 
Diameter (m) | 0.161 | 6" Schedule 10 Pipe (6.357" ID) |  |  | 
L (m) | 20 | length estimate |  |  | 
Flow Area (m2) | 0.0203 |  |  |  | 
STP Density (kg/m3) | 1.784 |  |  |  | 
STP Flow Rate (m3/s) | 0.999 |  |  |  | 
Vsonic @STP (m/s) | 283.75 | per DUC Design Doc, App. C |  |  | 
Average Flow Velocity (m/s) | 49.06 |  |  |  | 
Mach Number | 0.17 | <.3 - Incompressible |  |  | 
STP Viscosity (Pa-s) | 0.0000752 | NIST |  |  | 
Reynolds Number | 187400 |  |  |  | 
Friction Factor (Moody) | 0.0320 | e/D=.006 |  |  | 
K1 (Straight Vent Pipe) | 3.975 | Crane, 1999 |  |  | 
dP (Pa) | 8535.93 | Darcy Formula |  |  | 
dP (psi) | 1.24 |  |  |  | 
Additional Ks (STP) and Resulting DP | K | dP (Pa) | dP (psi) |  | 
Sudden constriction to vent pipe | 0.5 | 1073.7 | 0.16 |  | Crane, 1999
90° radiused tubing elbows | 0.64 | 8245.7 | 1.20 |  | (r/D=1), quantity estimated at 6
Fike Axius Rupture Disc | 0.45 | 966.3 | 0.14 |  | Ref Fike Technical Bulletin
Abrupt exit | 1 | 2147.3 | 0.31 |  | Crane, 1999
Total dP (psi) | 3.040 |  |  |  | 

## Slide 9: Assembly/maintenance(continued)
TPC may be accessed by lifting the insert, removing the dewar, and placing the insert on a support stand

## Slide 10: Assembly/maintenance(continued)
Process may be reversed to re-insert TPC

## Slide 11: Procurement process and status
Define cryostat requirements (physics/mechanical) | COMPLETE
Create preliminary design | COMPLETE
Preliminary drawings | COMPLETE
Coordinate with LANL pressure safety | COMPLETE
Obtain budgetary quote from vendor | COMPLETE
Compile procurement documentation | COMPLETE
Exhibits D (SOW) and H (Q/A) | COMPLETE
Form 410 approval (pressure safety) | COMPLETE
Purchase Request | COMPLETE
LISC (Laboratory Integrated Stewardship Council) Approval | COMPLETE
Buyer assignment | COMPLETE
Formal RFQ | IN PREPARATION
Bidding process | 
Contract award | EXPECTED BY FEB 28th, 2013
Fabrication | 
Vendor provides final fabrication drawing for LANL approval | 
Materials order | 
Machining/welding | 
QA check | 
Delivery to LANL | EXPECTED BY AUGUST 30TH, 2013

## Slide 12: Questions?

## Slide 13: Projected heat load - backup
Note: cryostat vendor to provide heat load estimate with final drawings for LANL approval
Calculated Heat Load Summary | 
Liquid Argon Prototype | 
Ramsey 1/2013 | 
Argon Volume Rad Load (W) | 30.25
TPC Supports (W) | 55.01
L Ar Volume Support (W) | 202.66
Instrumentation Wiring (W) | 13.56
HV Conductor Wiring (W) | 0.34
Viewport Light Load (W) | 2.40
Laser Heat Load (W) | 0.90
Total Heat Load (W) | 305.11