## Slide 1
Summer Shutdown 2024

## Slide 2: Shutdown Parameters
Start Shutdown
  Duration
    10 Weeks
  Beam Off
    Friday July 12th @0001 hrs
    Configuration Control
    PESD will be performing LOTO during the day.
  Preparing enclosure
    Sunday-Friday July 14th – July 19th
      Configuration Control, Rad Survey, Re-coring, issuing of shutdown keys
  Start of tunnel work
    Tuesday July 16th in Booster/ MI8. Rest of areas will be opened as surveys are completed.
  End of tunnel work
    Week of Monday September 23rd
  HEP
    Monday October 4th

## Slide 3: Electrical work
The current schedule is for 2 separate teams:
Week 1-2 Team 1 and 2: Main Injector Dual PA.
Week 3-4 Team 1 and 2: MI 8 Collimators.
Week 5-7 Team 1: Booster Collimator.
Week 5-6 Team 2: Linac
Week 8 Team 1: Meson/ ESH
Week 9-10 Team 1: Muon Campus
Week 7-10 Team 2: MI 20 upgrades
As you can see there is not a lot of down time for the electricians. Talk to Paul ASAP if you are missing something.

## Slide 4
Shutdown 2024 Timeline
Crew Marching orders
Determine Jobs
Plan phase 1: Define schedule
Execute Shutdown
Close out
Plan phase 2: Finalize Schedule
JAN
FEB
MAR
APR
MAY
JUN
JULY
AUG
SEP
OCT
NOV
DEC
Milestone 1
Define Shutdown Coordinators.
Milestone 2
ID Jobs to the 90% level.
Milestone 3
First pass resource level Schedule.
Milestone 4
Milestone 5
Milestone 6
Milestone 7
Second pass resource level Schedule.
Final resource level Schedule.
Start Shutdown.
Complete shutdown.
Milestone 9
Milestone 8
Complete
Startup.
Return HEP
Define Scope
Plan
Execute
Close out
HEP
Dec
Shutdown Boot Camp
Work Planning
  HA’s
  Dose Plan
  Permits
  Etc..
Timeline of events
Work List Entries
Expectations
General Task Approval process
Work In HRA
Activities planned
AD All Hands
Exterior Divisions All Hands
By end March, All Trades work Procurements need to be in Procurements hands…
By May, Final Power Outage schedule
ISD Job imported in the Shutdown (~700 tasks)
Mid April

## Slide 5: Planning Stages
Planning Milestones
  Kick off meeting (completed)
  Set Major Jobs (completed)
  T&M/Fixed price packets
  Set Alignment Tasks
    Input into their system (end of April)
    Survey requests can be submitted to the alignment group on the worklist link.
  Finalizing ISD work in and around Tunnel Enclosures (Underway)
  Finalize Service Building Outages (early May)
  Set Maintenance tasks (mid of May)
    FESS and Machine activities
  Fit tasks with our Manpower (mid May)
  Resource leveled schedule
    Primary (mid April)
    Final (mid/end May)
  DO NOW Please label jobs in the work list “Summer shutdown 2024:…”