## Slide 1: Muon Campus Operation Report
Jim Morgan
Friday 09:00 Operations Meeting
April 19, 2024

## Slide 2: Muon Campus status
Study – Alternative M5 optics
Study – M1-M3 Optics
Working towards permission for beam operation
  Vacuum work in D30 finished and equipment removed from the tunnel
  Switched to operational two pump LCW operation at CUB
  Power supply inspections completed, working on mitigating findings
  Finished Credited Controls labeling in Pre-Vault and AP-0 Vault walls
  Completed last known tunnel work, finishing with Prototype ESS HV termination
  Readied PWC’s and ion chambers for operation, checking gas flow and high voltage
  Worked on issue discovered with AP-30 vacuum controls
  ES&H re-cored Delivery Ring, Extraction and M4 Enclosures to operational keys
  These three enclosures secured on Thursday, all enclosures now secured
  Half-way through beam sign-offs
ESS1 & ESS2 Electrostatic Septa
  ESS1 high voltage conditioning continued at NWA, now around 71 kV
  ESS2 assembly resumed in the A0 Clean Room
AP-0 A/C work continued
  Completed installation of refrigerant lines and ducting
Technical Division personnel worked on reconfiguring water inlets on some LQ quadrupoles in the downstream M4 Line

## Slide 3: ESS1 high voltage conditioning at NWA
ESS1 P.S. Voltage
Spark Detector
ESS1 P.S. Current
Ion Gauge
Operational Voltage with 12 cm foil to cathode distance

## Slide 4: ESS1 beam dimensions and foil to cathode distance

## Slide 5: Upcoming work
Hope to resume beam operation next week
  Working on beam sign-offs (6/12, but several ready for signatures or close to it)
  Delivery Ring, Extraction and M4 Enclosure interlocks testing today
  May do some power supply testing before setting up to run beam
ESS1 and ESS2
  ESS1 high voltage conditioning continues at NWA
  ESS2 assembly continues in A0 Clean Room
AP-0 A/C work paused while awaiting controls sub-contractor
  Will need access to AP-0 Water Cage and rad fence area and will require beam off to Muon Campus
  Estimate six days of work needed for system to be operational