## Slide 1: Muon Campus Operation Report
Jim Morgan
Friday 09:00 Operations Meeting
April 26, 2024

## Slide 2: Muon Campus status
Study – Alternative M5 optics
Study – M1-M3 Optics
Working towards permission for beam operation
  Power supply inspections completed; mitigated findings needed for start-up
  Readied PWC’s and ion chambers for operation, checking gas flow and high voltage
  Interlocks techs tested all safety enclosures last Friday, waiting on rad monitors
  Discovered discrepancy in SAD/ASE Credited Control documentation regarding AP-30 penetrations and MC-1 rad detector
  7/12 beam sign-offs (including Muon and Ops signatures, which come last)
Other work done preparing for beam start-up
  Checked profile monitor motion-control and high voltage to PWC’s
  Updating BBM for Mu2e operation and newer toroid electronics
  Testing logic modifications to 30 sector vacuum controls
ESS1 & ESS2 Electrostatic Septa
  ESS1 high voltage conditioning continued at NWA, nearing operational voltage
  ESS2 foil plane installation completed on frame
AP-0 A/C work stalled again
  Waiting for controls sub-contractor to show up
Technical Division personnel worked on reconfiguring water inlets and rad hardening the last three LQ quadrupoles in the M4 Line

## Slide 3: ESS1 high voltage conditioning at NWA
ESS1 P.S. Voltage
Spark Detector
ESS1 P.S. Current
Ion Gauge
Operational Voltage with 12 cm foil to cathode distance
Conditioning target voltage

## Slide 4: Penetrations in D30 tunnel
Delivery Ring

## Slide 5: Upcoming work
Hope to have signing party next week
  Waiting on Interlocks testing to be finished
  Need to resolve SAD/ASE documentation discrepancies
  Working on beam sign-offs (7/12, but several ready for signatures or close to it)
  May do some power supply testing before setting up to run beam
ESS1 and ESS2
  ESS1 high voltage conditioning continues at NWA, plan to go to 90 kV
  ESS2 being checked for foil plane straightness, then will be installed in tank
AP-0 A/C work paused while awaiting controls sub-contractor
  Will need access to AP-0 Water Cage and rad fence area, turning off beam to Muon Campus
  Estimate six days of work needed for system to be operational
Make updates to Muon Campus BBM
  Eliminate mode for beam to AP-0 Target
  Switch to newer toroid electronics and use M:TR105B for input