## Slide 1: Magnets 302.2.03 Cable Fabrication
Ian Pong – LBNL (L3 and CAM)
Mike Naus – LBNL (L3 and CAM deputy)
HL-LHC AUP DOE IPR – July 23rd–25th 2024

## Slide 2: Outline
Scope, Interfaces, Dependencies & Team
Achievements since Rebaseline Review
Procurement Status
Schedule
Cost and Schedule Performance & VAR Reports
BCRs since Rebaseline Review
QA/QC
Risks
ES&H
Summary

## Slide 3: Functional Requirement Specifications
ID | Description
R-T-03 | The MQXFA magnet must be capable of operating at steady state providing an integrated gradient of 556.9 T in superfluid helium at (HeII) bath at 1.3 bar and at a temperature of 1.9 K
R-T-16 | The MQXFA magnet coils and quench protection heaters shall pass the hi-pot tests specified in Table 2.
Specification for Conductor (US-HiLumi-doc-40)
Specification for Cable (US-HiLumi-doc-74)
  Define performance and length of conductor
  Address FRS R-T-03
Specification for Cable Insulation (US-HiLumi-doc-75)
  Defines glass fiber braiding for cable insulation
  Addresses R-T-16
FRS (US-HiLumi-doc-36)
Charges #2, #3

## Slide 4: WBS 302.2.03: Scope
All completed, 4 failed/on hold cable
US-HiLumi-doc-39
Charges #1, #3

## Slide 5: WBS 302.2.03: Interfaces
US-HiLumi-doc-219
Not changed since CD-3
Charge #3

## Slide 6: WBS 302.2.03: Team
302.2
MQXFA Magnets Fabrication
L2: G. Ambrosio
(M. Baldini, P. Ferracin)
302.2.01
Magnets Integration and Coordination
L3/CAM: G. Ambrosio
(M. Baldini)
302.2.04
Coil Parts, Materials and Tooling Procurement
L3/CAM: M. Yu (A. Nobrega)
302.2.05
Coil Fabrication at FNAL
L3/CAM: A. Nobrega (M. Yu)
302.2.06
Coil Fabrication at BNL
L3/CAM: J. Schmalzle
(M. Anerella)
302.2.07
Structure Fabrication and Magnets Assembly
L3/CAM: S. Prestemon
(D. Cheng)
302.2.03
Cable Fabrication
L3/CAM: I. Pong (M. Naus)
302.2.02
Strand Procurement
L3: L. Cooley (V. Lombardo)
CAM: V. Lombardo
Control Account
US HL-LHC Accelerator Upgrade Project: 302.2 MQXFA Magnets Fabrication
Core Members:
Ian Pong
Mike Naus (deputy)
Andy Lin
Elaine Buron
Jean-Francois Croteau
Assisting Members:
Li Wang (cryo)
Hugh Higley (Retiree)
Dan Dietderich (Retiree)
US-HiLumi-doc-104
Charge #2

## Slide 7: WBS 302.2.03: Achievements since Rebaseline
Scope completed!
Higher yield than assumed.
Charge #1
Chart: Cables (LARP + Fabrication)
| LARP + Accepted | In Fabrication | To be Fabricated | Rejected
 | 112 | 0 | 0 | 5

## Slide 8: WBS 302.2.3: Cost and Schedule Performance & VAR Reports
CPI and SPI stable and very close to 1.00
No VAR reports since COVID Rebaseline
Charge #2
Cumulative to Date |  |  |  |  |  |  |  | 
Budget | Earned | Actuals | SV | SV (%) | CV | CV (%) | SPI | CPI
$ 6,388,783 | $ 6,378,633 | $ 6,377,522 | $ (10,149) | -0.16% | $ 1,110 | 0.02% | 1.00 | 1.00

## Slide 9: WBS 302.2.03: BCRs Approved Since Baseline
BCR # | Description | Cost ($k) | Sch. (days)
0331 | Fabrication of 2 Additional Cables | 141,669 | 0
0306 | Fabrication of 2 Additional Cables | 124,221 | 0
BCR #0331 and #0306 each added two cables
BCR #0311 AUP Project Rebaseline after March 2023 ESAAB Approval
Charge #2

## Slide 10: WBS 302.2.03: QA/QC
MIP approved by CERN (EDMS 1866230)
AUP Quality Plan (Doc 903)
Three failed cables at time of manufacture
  Wire crossover (P43OL1112)
  Roller bearing failure (P43OL1171)
  Mid-run bay brake activation (P43OL1175)
One impacted cable at time of coil winding
  1 on-hold cable (P43OL1260)
  1 rejection (P43OL1239)
  Related to wire excess lubricant causing mechanical instability during coil winding. See also: US-HiLumi Docs. 4172, 4318
Charge #1

## Slide 11: WBS 302.2.03: Risks
Charge #6
Three threats
One opportunity
One relevant project-wide threat
Risk-ID | Title | Risk Rank
RT-302-2-03-001* | Number of cables fails to meet specifications | Medium
RT-302-2-03-004* | Failure of insulation contractor to deliver on time | Low
RT-302-2-03-003 | Significant breakdown of cabling machine | Low
Opportunity-ID | Title | Risk Rank
RO-302-2-03-001 | Mapping optimization allows leftover from wire spools to be converted to a cable UL | Medium
Risk-ID | Title | Risk Rank
RT-302-1-005 | Need to replace key personnel | Low
* These risks have a separate COVID component in the risk register to account for additional probability/impact due to COVID pandemic.
Risks retired upon completion of task

## Slide 12: WBS 302.2.03: ES&H
Regular meetings at LBNL, minutes & roster kept in Google Drive with access control
WPC, Procedures, HAR (§9.1), etc. are in place
No injury-causing accident for >25,000 labor-hr!
Fire sprinkler leak in 2019
  Causal Analysis Report made by the LBNL PIMD, EHS, and IA&I.
COVID control effective: no onsite transmission
Lab protocols and guidelines continually updated per DOE and CDC guidance
Charge #5

## Slide 13: WBS 302.2.03: Summary
302.2.03 discrete activity is completed
Cost and schedule well controlled
No VAR reports since COVID Rebaseline
This task could not have been completed without the dedication and contributions from all the team members, including former post-docs, engineers, interns, and technicians, as well as AUP and LBNL management, supporting staff from ATAP division operations, the EHS, OCFO, and Procurement division.
THANK YOU ALL!

## Slide 14: Team Work

## Slide 15: Discrete Activity Completion

## Slide 16: 50% Milestone Completion

## Slide 17: Backup Slides
You should keep the pie-charts and tables from the CAM e-Toolbox as backup slides in case someone asks questions

## Slide 18: 302.2.03 Resource Type Breakdown
77% Labor, 23% M&S
M&S Includes contractors (braiding vendor), travel, shipment, etc.
Lab
Logo
Example from 302.2.03
Plots to be provided by PO
To be Updated
Charge #2

## Slide 19: 302.2.03 Estimate Quality
Conceptual is related to the RRR measurements
  FNAL has been measuring RRR up to earlier this year
  LBNL’s new system is undergoing benchmarking approval
Preliminary is mostly related to Insulation
  Master Agreement is being placed to lock down the price throughout AUP
The quality of estimate has been updated for CD-2/3b
Lab
Logo
Example from 302.2.03
Plots to be provided by PO
To be Updated
Charge #2

## Slide 20: 302.2.03 FTE Breakdown
From 5/31/18 forward
  Does not include FY18 Actuals
Lab
Logo
Example from 302.2.03
Plots to be provided by PO
To be Updated
Charge #2

## Slide 21: 302.2.03 Cost Performance Report
BAC = $5.658M
No thresholds crossed in Current Period Cost
No thresholds crossed in Cumulative to Date
Cumulative SPI = 0.9, CPI = 1.05
Example from 302.2.03
Plots to be provided by PO
To be Updated
Charge #2