## Slide 1: Cryo Assembly, Cold Mass Status
A. Vouris
Cryo Assy L2 Meeting
April 29, 2024

## Slide 2: Cold Mass Tooling & Design Status
WorkStation Equipment
  Status
    End Can
      Lead End – Pallet jack cart drawings and note for 2nd unit
      Order additional pallet jack w/ extended forks
    Cold Mass drawings
      Working through redlines for next batch of drawing mods
        dwg for revisions: Magnet Model updated in all drawings
          F10103605 – Released/printed
          F10151260 – Released/printed
          F10178090 – Capillary tube install update – in que
          F10172809 – Pressure test drawing default updates from lower dwg
          Update Drawing tree - as needed after final revisions
    Additional tooling:
      Metrology: adjust/re-survey Welding Station – Rails adjusted and now w/in +/- .04

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Engr Analysis & Note:
    Detailed procedures complete
      traveler CM-04 released
  Cold Mass Welds
    Welding:
      Fronius – adding power cut off at machine per safety requirements
      Calibration plates RT’d complete (passed) – forwarded to J. Seyl
      Welder Qualification plates: passed – new welder (Tyler qualified)
      Borescope - Rental quote received from 1st vendor (380.00 +50/day, 1520.00 +200/wk, 3800 + 500/mo)
      Borescope – Req submitted – certifications resolved & continuing on with approvals.

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass
  CM-02 - See R. Rahbel talk
  CM-03
    Electrical Check complete - End covers fit/tack complete
    Circ weld grinding
    Elbow welding complete
    SSW complete and results reviewed
    Saddles tacked – Metrology report received this morning will review today
    longitudinal Welds – repair complete w/ exception of under 2 clamps
    UT vendor notified – May 8th or sooner
    Fitting/mach/welding flare fittings to fit – (HT-X flares 4x welded complete)
  CM-04 (MQXFA-08b & MQXFA-14b)
    Metrology 1st Survey complete
    SSW work complete and results rec’d – preliminary check on results show all good!
    Beam tube installed complete
    Buss installed – Loop installation complete
    Test loop movement confirmed - bus lock length to be milled
    2nd Ht-X install complete (cleaned and leak test completed prior to install)
    NEW SSW confirmed misalignment between magnet: adjusted last week and follow up SSW verified
    New Metrology Survey to confirm adjustment in process

## Slide 5: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Final 2 items for procurement:
      Tack Blocks – in QCR reviewed and dispositioned – Reviewed rework of first few and passed. Vendor will proceed to repair the balance including second batch returned
      Lower Saddles, cold mass – reviewing QCRs
      Production N-lines - leak test 100% complete
      Formed Plates in stock at FNAL for CM-05, CM-06 and CM-07
      CM-06 thru CM-10 & Spare Shell Plate Machining PO (REQ #355609) – PO awarded del dates confirmed starting June 1 for 1st set and 45 days additional per set: waiting for notification on CM-05 shells complete to swap with CM-06 shells (pickup -05 and deliver -06)
      Shell Plates for CM-08 & CM-09 shipped to forming vendor on Tuesday, Feb. 6
      CM-05 – CM-10 & Spare Saddle – at vendor for rework/inspection (no updates) adding thread check on all parts (100%) -
      CM-05 – CM-10 & Spare Tack blocks – fill in work matching parts for assembly check – mostly complete (fill in work)
      Shim material for units CM-04 thru CM-08. at VMS to Water Jet cut and roll in process this week
    Magnet 16
      Inspection Complete
    Q1-Q3 Bus production
      Units up to CM-10 plus 1 spare are complete
      1 Spare Buss – waiting for housing parts