## Gantt Chart
Monitoring Gantt chart
PROJECT TITLE |  | Monitoring
PROJECT MANAGER |  | Alex, Pierre, Marco |  |  |  |  | DATE |  | 2023-06-13
WBS NUMBER | TASK TITLE | WHO? | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | 2023 | [27 empty] | 2024 | [51 empty] | 2025
[7 empty] | June |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January | February | March | April | May | June | July | August | September | October | November | October
[7 empty] | 12-16 | 19-23 | 26-30 | 2023-07-03 | 10-14 | 17-21 | 24-28 | 2023-04-01 | 2023-11-07 | 14-18 | 21-25 | 2023-01-28 | 2023-08-04 | 11-15 | 18-22 | 25-29 | 2023-06-02 | 9-13 | 16-20 | 23-27 | 2023-03-30 | 2023-10-06 | 13-17 | 20-24 | 2023-01-27 | 2023-08-04 | 11-15 | 18-22 | 2023-05-01 | 2023-12-08 | 15-19 | 22-26 | 29-2 | 2023-09-05 | 12-16 | 19-23 | 2023-01-26 | 2024-08-04 | 11-15 | 18-22 | 25-29 | 2024-05-01 | 2024-12-08 | 22-26 | 2024-03-29 | 2024-10-06 | 13-17 | 20-24 | 27-31 | 2024-07-03 | 10-14 | 17-21 | 24-28 | 2024-05-01 | 2024-12-08 | 15-19 | 22-26 | 2024-02-29 | 2024-09-05 | 12-16 | 19-23 | 26-30 | 2024-06-02 | 9-13 | 16-20 | 23-27 | 2024-04-30 | 2024-11-07 | 14-18 | 21-25 | 2024-01-28 | 2024-08-04 | 11-15 | 18-22 | 25-29 | 2024-05-02 | 9-13 | 16-20 | 23-27 | 2024-03-30
1 | Streamer |  |  |  | #REF!
1.1 | Publisher and Subscriber ERS | MR | 2023-05-12 | 2023-07-14 |  | 100%
1.2 | Protobuf message schema distribution ERS | PD,JF | 2023-06-10 | 2023-07-14 |  | 100%
1.3 | Update of microservices to use the ERS Streamer | MR, PD, JF,BK |  | 2023-07-14 |  | 100%
1.4 | Evaluation and improvement of ERS interfaces and ERS schema | MR/CCM |  |  |  | 50%
1.4.1 | Review and update of what is publihsed eventually on postgreSQL | CCM |  | 2029-09-29 |  | 25%
1.5 | R&D on OpMon schema and on Opmon Interface | MR/CCM | 2023-12-12 |  |  | 100%
1.6 | Implement OpMon schema and Interfaces | MR | 2023-12-12 |  |  | 85%
1.7 | Adapt the rest of the code to new interfaces | MR/CoreSW/CCM/NewStudent? |  |  |  | 0%
1.8 | Protobuf message schema distribution Opmon | MR |  |  |  | 50%
1.9 | Presentation at CCM meeting for discussion | MR | 2024-01-01 |  |  | 25%
1.11 | Publisher and Subscriber Opmon | MR | 2024-02-20 |  |  | 90%
1.12 | Update of microservices to use the OpmonStreamer | MR,PR |  |  |  | 0%
2 | Services
2.1 | Broker literature review | MR/PR |  | 2023-09-15 |  | 100%
2.2 | Alternative broker R&D | MR/PR? |  |  |  | 100%
2.3 | Fake publisher developer daq_application development | MR |  |  |  | 0%
2.4 | System scaling tests including fake publisher developer | MR |  |  |  | 0%
2.5 | Review current database technology and structure | MR/PR |  |  |  | 20%
2.6 | R&D on databases etc. | MR/PR |  |  |  | 20%
2.7 | Repeat system scaling tests | MR/GLM |  |  |  | 0%
3 | Visualisation
3.1 | Dashboard management (prod & dev instances etc.) | MR/PR | 2023-08-01 | 2023-09-29 |  | 0%
3.2 | FD/ND separation | MR/ND people |  |  |  | 0%
3.3 | Review dashboard management | CCM/Infrastructure |  |  |  | 0%
3.4 | Continuous developer support | MR/NewStudend?? | 2023-01-01
4 | Supervisor
4.1 | First automated action demonstration | MR/PL |  |  |  | 0%
4.2 | Write out documentation | MR |  |  |  | 0%
4.3 | Presentation at a General DAQ meeting | MR |  |  |  | 0%
4.4 | System experts to code their automated actions (CoreSW) | CoreSW |  |  |  | 0%
4.5 | System experts to code their automated actions (Timingh) | Timing |  |  |  | 0%
4.6 | System experts to code their automated actions (Trigger) | Trigger |  |  |  | 0%
4.7 | Etc. | All subgroups |  |  |  | 0%